# Liberia Peace Building Fund

# QUARTERLY STATUS REPORT Jan – March 2010

| Recipient UN Organization: | UNDP | PBF Priority Area: To Promote peace and resolve Conflicts | Priority Area 2: Critical Interventions to promote peace and resolve conflicts |
| --- | --- | --- | --- |
| Implementing Partner(s): | YMCA, LNP, UNMIL, Ministry of Transport, Bureau of Immigration and Naturalization |
| Project Number: | PBF/LBR/D-5 (00071058) |
| Project Title: | Supporting Peaceful Reintegration of High Risk Youths into their Communities through Facilitating Rural Transport Livelihood Opportunities |
| Total Approved Project Budget | US$250,000.00 |
| Project Objective and Scope | To enhance the socio-economic reintegration of high risk youths operating informal transport services (motorcycle) To promote mechanism for resolving conflict among motorcycle riders, the community and the Police To ensure motorcyclist receive training on highway Code and other safety measures compliance with rules and laws while riding thereby promoting human safety and live |
| Funds Committed: | $250,000.00 | Percentage of Approved: | 100% |
| Funds Disbursed: | $105,383.00 | Percentage of Approved: | 42% |
| SC Approval Date: | 22nd March 2009 |
| Expected Project Duration: | 18 Months | Forecast Final Date: | 2010 | Delay (Months): | n/a |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| Monitoring and evaluation visits conducted in Bomi and Bong Counties. | Separate field visits conducted in Bomi (2 in Tubmanburg) and Bong (3 in Gbarnga) Counties and discussions held with the police and motor cyclists and observed improved relationship •Fewer beneficiaries as compared to number trained were observed to be wearing safety helmets. •Community members spoken to during visit expressed that attitude of most motorcyclists who participated in training has improved as a result of the intervention. •Police officers said case load of traffic accidents due to reckless riding reduced couples of weeks after the training but has since jumped again. Challenges -The YMCA remains challenges in raising the 37% cost to complement t the project budget. -UNDP's delay remittance of the next trench has also interrupted schedules and dimpled moral of teams for the project. -Unresolved issue of increased cost of license fees by the Ministry of Transport is affecting relationship and the credibility of the partners to the beneficiaries. - Girls especially hesitate to wear safety helmets for fear of messing up their hair styles. |  |
| Relationship Center built in Tubmanburg. | Relationship building center set up in Tubmanburg under the project is not being fully utilized due to its location (accessing space at a central locations was not possible as there are no public land available in the center of the city. -Gbarnga the YMCA local team is yet to identify a central location to construct a Relationship Center despite commitment of local authorities. | On-going |
| Partnership | - March 2010, the YMCA and the Liberia National Police conducted training in road safety for 25 staff of the National Volunteer Program. The staff are to use motorcycles to support their work in rural communities. -Comic Relief through Y Care International, UK, Liberia YMCA’s UK based partner organization agreed in January to cover portion of wages for peer educators support to follow up activities. | Completed On-going |
| Challenges | -Difficulties the YMCA faces in raising the remaining 37% project cost. -UNDP's delay to remit the next trench has interrupted schedules and dimpled moral of teams for the project. -Unresolved issue of increased cost of license fees by the Ministry of Transport is affecting relationship and the credibility of partners to the beneficiaries. |  |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| Well-organized mode of transport with safety standards and respect for traffic rules established and operational | Improving attitude of motorcycle riders’ to comply with traffic rules/ procedures in communities covered to ensure public safety is leading to improved relationship between them, the police and the communities. This is leading to improvement in behaviour towards passengers and the general public thus making the public to now have some level of confidence in the motorbike riders | Improved relationship now exist between the public and motorbike riders. However, feedbacks from some riders’ refusals by some female passengers to wear helmets. Enforcement of safety regulations by police is also weak. |
| Capacity of the motorcycle union to manage the institution and membership enhanced | This exercise has over the period improved the management aspect of motorbike riders’ unions in the communities covered thus contributing to an improved relationship and communication and at the same time reducing the potential for violent actions, which are caused by poor relationship among the motorcyclists, their commuters and the law enforcement agents | 2 local motorbike riders unions were strengthened and are gradually improving on services to their membership and communities. Union in Gbarnga especially seem more organized and engaged with its membership |
| Peaceful co-existence in community between motorcycle riders, taxi drivers, police and communities improved | This has contributed to an enhanced level of communication between the motorbike riders, taxi drivers and community members | Communication and improved behaviour are gradually paving friendly relationships among the motorbike riders, taxi drivers and general public. This would be scaled up by increased public awareness initiatives of the YMCA using local media. Awareness for utilization of Community R/ship PB Centers funded by project will be enhanced to promote utilization by community and other stakeholders for community development purposes |

Qualitative achievements against expected results:

Overall, activities of the peaceful reintegration of high risk youths into communities through rural transport have created a peaceful environment demonstrated by a reduced level of community fracas and clashes between motorcyclists and members of the general public as well as the law enforcement agents in the communities covered by the project thus far. This positive action resulted from the strategic nature of communications exchanged and advocacy campaigns together with joint meetings and training sessions that were conducted creating an improved and friendly working environment between the police and motorcycle riders on the one hand, and a reduction in the number of traffic accidents involving motorcycles and riders on the other hand. In addition, the capacity building exercises of this project has also led to an improved partnership amongst trainers and trainees, and bike riders vis-à-vis commuters thereby reducing confrontations.

Appendix A

Detailed Work Plan for 18 Months of Project Implementation – 2009 to 2010

| Outcome/Output | Activities | Inputs | Budget | Delivery Date |  |
| --- | --- | --- | --- | --- | --- |
| Component 1: Component 1: Training & Empowerment |  |
| Motorcycle riders are trained and prepared to conform to traffic rules and safety standards Police and Motorcycle riders have improved relationship in addressing common problems Improved capacity of the motorcycle union to register members, conduct training and authentication, provide identity and engage in awareness and advocacy | 10 motorcyclist mobilization meetings held in target areas, 2 per location. 5 leadership-training workshops conducted with bike rider associations – 1 in each location. 10 technical training meetings with, motorcyclists and other key transport unions – 2 in each location; Code of conduct developed, with provisional requirements for admission to the association 5 conflict management, problem-solving and advocacy trainings conducted with the leadership of bike rider associations – 1 in each location. 5 local community radio stations are hired, one in each location, to provide public awareness support to the reintegration and peace-building efforts. | -Training workshops -Training modules; - Visibility & safety materials -Local & national media coverage -harnessing of local stakeholders’ support | See financial report | 2-5 Months | Re: Case ID 21940 |
| Component 2: Behavioural Change, Peace Education |  |
| Knowledge of peace education, with basic information on appreciating the society Peer mediation training to serve as peace ambassadors among their colleagues | 10 local radio talk shows (2 in each location) facilitated every month with motorcyclists, community leaders, police authorities and transport union to discuss reintegration opportunities and challenges 5 drama performances in each location every month demonstrating accidents, unprofessional driving, etc and the intervention measures to adopt to avoid conflict; Develop and produce a variety of stickers depicting messages for road safety; Develop an identification system for motorcyclists that will be targeted under this Project (plate number and jackets with number that matches the plates; | -Training of Beneficiaries & Mediators - Stationery - Logistics - Training modules - Public awareness - Production of visual Aids |  | 2-5th Month |  |
| Component 3: Establishment of Community Relationship-building Centers (CRBC) |  |
| Bike riders and the commuters alike have a place at each parking lot to address complaints | Construction of CRBC; Training of 40 peer mediators to manage the CRBC | -Training of mediators to man the booths - Stationery - Logistics - Training modules - Public awareness - Production of visual Aids |  | 2-5th Months |  |

| Date | 6 Months Benchmarks | Indicators of Progress |
| --- | --- | --- |
| First 6 Months | Identification, mobilization & orientation of bike rider leadership; Hold baseline survey; Technical trainings held by the Police with bike riders Code of conduct developed Conflict management & advocacy training 40 peer- peace mediators trained to manage community relationship building centers Community radio stations provide support to the program Establishment of the community relationship-building centers(CRBC) | Listing and addresses of bike rider leaderships in target locations; Baseline survey report; Training Report; Code of Conduct document produced and shared; Training report of 40 selected peer peace mediators; Partnership Agreement with local radio stations; Reports on the completion and functionality of the 25 CRBCs Regular reports from the field; Monitoring reports |
| Second 6 Months | Stakeholders begin holding talk shows on local radio stations; Drama performances are held to promote peace Production of stickers and other signs for improved riding; Develop identification system for the riders association | Airtime contract with selected radio stations; Contract and recordings of drama performances; Number and kind of stickers produced for distribution; Number and kind of identity developed for bike riders; Regular reports from the field. Monitoring reports |
| Remaining 6 Months | Continue with follow-up technical trainings Commence workshop trainings in advocacy Continue with relationship building activities Continue with drama performances, radio talk shows, etc Conduct impact assessment/evaluation of the project; | Regular reports; Training Reports; contract and recordings of drama performances; Project Evaluation |