# Liberia Peacebuilding Fund

# QUARTERLY STATUS UPDATE AS OF DECEMBER 31, 2009

| Recipient UN Organization: | UNDP | PBF Priority Area: To Promote peace and resolve Conflicts | Priority Area 2: Critical Interventions to promote peace and resolve conflicts |
| --- | --- | --- | --- |
| Implementing Partner(s): | YMCA, LNP, UNMIL, Ministry of Transport, Bureau of Immigration and Naturalization |
| Project Number: | PBF/LBR/D-5 (00071058) |
| Project Title: | Supporting Peaceful Reintegration of High Risk Youths into their Communities through Facilitating Rural Transport Livelihood Opportunities |
| Total Approved Project Budget | US$250,000.00 |
| Project Objective and Scope | To enhance the socio-economic reintegration of high risk youths operating informal transport services (motorcycle) To promote mechanism for resolving conflict among motorcycle riders, the community and the Police To ensure motorcyclist receive training on highway Code and other safety measures compliance with rules and laws while riding thereby promoting human safety and live |
| Funds Committed: | $250,000.00 | Percentage of Approved: | 100% |
| Funds Disbursed: | $105,383.00 | Percentage of Approved: | 42% |
| SC Approval Date: | 22nd March 2009 |
| Expected Project Duration: | 18 Months | Forecast Final Date: | 2010 | Delay (Months): | n/a |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| Motorcyclist mobilization meetings and technical training meetings held in target areas | 4 motorcyclist mobilization meetings held in two target areas/locations | Completed |
| Leadership training workshops conducted with bike rider associations code of conduct developed | 2 two-day leadership training workshops conducted and bike rider associations module of operandi developed and functional 2 three - day technical training sessions held with 700 motorcyclists Code of conduct along with provisional requirements for admission to the association developed | Completed |
| Conflict management, problem-solving and advocacy trainings conducted | 2 one-day conflict management problem-solving and advocacy trainings with the leadership of bike rider associations successfully conducted | Completed |
| Media and outreach activities to raise public awareness established | 2 local community radio stations hired and 3 print media to provide public awareness support to the reintegration and peace-building efforts, and supported by UNMIL radio | Completed |
| System with visibility and safety standards improved | 3 local radio talk show and 3 UNMIL radio interviews (Coffee Break x2, and Day-Line Liberia held with motorcyclists, community leaders, and police authorities to discuss reintegration opportunities and challenges | Completed |
| Communication and peaceful conflict resolution enhanced | 655 reflector jackets with riders tracking numbers produced and distributed. | Completed |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| Well-organized mode of transport with safety standards and respect for traffic rules established and operational | Motorcycle riders’ compliance with traffic rules/ procedures to ensure public safety has led to improved relationship between them, the police and the communities. This has also resulted to motorbike riders changing their behaviour towards passengers and the general public thus making the public to have some level of confidence in the motorbike riders | Fairly good relationship now exists between the public and motorbike riders |
| Capacity of the motorcycle union to manage the institution and membership enhanced | Capacity building has over the period improved the management aspect of motorbike riders’ union thus contributing to an improved relationship and communication and at the same time reducing the potential for violent actions, which are caused by poor relationship among the motorcyclists, their commuters and the law enforcement agents | 2 local motorbike riders unions were strengthened and are gradually improving services to their membership and communities |
| Peaceful co-existence in community between motorcycle riders, taxi drivers, police and communities improved | This has contributed to an enhanced level of communication between the motorbike riders, taxi drivers and community members | Communication and improved behaviour are gradually paving friendly relationships among the motorbike riders, taxi drivers and general public |

Qualitative achievements against expected results:

Overall, activities of the peaceful reintegration of high risk youths into communities through rural transport have created a peaceful environment demonstrated by a reduced level of community fracas and clashes between motorcyclists and members of the general public as well as the law enforcement agents in the communities covered by the project thus far. This positive action resulted from the strategic nature of communications exchanged and advocacy campaigns together with joint meetings and training sessions that were conducted creating an improved and friendly working environment between the police and motorcycle riders on the one hand, and a reduction in the number of traffic accidents involving motorcycles and riders on the other hand. In addition, the capacity building exercises of this project has also led to an improved partnership amongst trainers and trainees, and bike riders vis-à-vis commuters thereby reducing confrontations.

Appendices

Appendix A

Detailed Work Plan for 18 Months of Project Implementation – 2009 to 2010

| Outcome/Output | Activities | Inputs | Budget | Delivery Date |  |
| --- | --- | --- | --- | --- | --- |
| Component 1: Training & Empowerment |  |
| Motorcycle riders are trained and prepared to conform to traffic rules and safety standards Police and motorcycle riders relationship in addressing common problems improved Capacity of the motorcycle union to register members, conduct training and authenticate, identity and engage in awareness and advocacy enhanced | 10 motorcyclist mobilization meetings held in targeted areas, 2 per location 5 leadership-training workshops conducted with bike rider associations – 1 in each location Conduct 10 technical training meetings with motorcyclists and other key transport unions – 2 in each location Develop code of conduct with provisional requirements for admission to the association Conduct 5 conflict management, problem-solving and advocacy trainings with the leadership of bike rider associations – 1 in each location Hired 5 local community radio stations to provide public awareness support to the reintegration and peace-building efforts - 1in each location | -Training workshops -Training modules - Visibility & safety materials - Local & national media coverage - Harnessing of local stakeholders’ support | Financial report | 2-5 Months | Re: Case ID 21940 |
| Component 2: Behavioural Change, Peace Education |  |
| Knowledge in peace education with basic information on appreciating the society enhanced Peer mediation training to serve as peace ambassadors among their colleagues conducted | Discuss reintegration opportunities and challenges using 10 local radio talk shows (2 in each location) every month with motorcyclists, community leaders, police authorities and transport union Conduct 5 drama performances in each location every month demonstrating accidents, unprofessional driving, etc. and the intervention measures to adopt to avoid conflict Develop and produce a variety of stickers depicting messages for road safety Develop an identification system for motorcyclists (plate number and jackets with number that matches the plates) | -Training of Beneficiaries & Mediators - Stationery - Logistics - Training modules - Public awareness - Production of visual Aids |  | 2-5th Month |  |
| Component 3: Establishment of Community Relationship-Building Centers (CRBC) |  |
| Bike riders and the commuters alike have a place at each parking lot to address complaints | Construction of CRBC Train 40 peer mediators to manage the CRBC | -Training mediators to man the booths - Stationery - Logistics - Training modules - Public awareness - Production of visual Aids |  | 2-5th Months |  |

| Date | 6 Months Benchmarks | Indicators of Progress |
| --- | --- | --- |
| First 6 Months | Identification, mobilization & orientation of bike rider leadership Hold baseline survey National Police conduct technical trainings for bike riders Code of conduct Develop conflict management & advocacy training Train 40 peer- peace mediators to manage community relationship building centers Community radio stations provide support to the program Establishment of the community relationship-building centers(CRBC) | List and addresses of bike rider leaderships in target locations Baseline survey report Training Report Code of Conduct document produced and shared; Progress report Training report of 40 selected peer peace mediators Partnership Agreement with local radio stations Reports on the completion and functionality of the 25 CRBCs |
| Second 6 Months | Stakeholders begin holding talk shows on local radio stations Drama performances are held to promote peace Production of stickers and other signs for improved riding; Develop identification system for the riders association | Selected radio stations identified Recordings of drama performances Number and kind of stickers produced for distribution Number and kind of identitification card developed for bike riders Regular reports from the field produced Monitoring reports produced |
| Remaining 6 Months | Continue with follow-up technical trainings Commence workshop trainings in advocacy Continue with relationship building activities Continue drama performances, radio talk shows, etc Conduct impact assessment/evaluation of the project | Regular reports Training Reports contract and recordings of drama performances Project Evaluation |

Appendix B

# Text boxes

Some guiding principles

The reintegration assistance is based on the principles of participation and inclusion; ownership and commitment; need-orientation; flexibility; partnership and sustainability

Core business

Promote/build social bond (trust, respect for rule of law and positive’ networks)

Promote access to transportation service in the community

Cornerstones

Reconciliation/Cohesion				Organized livelihood opportunities

Enhanced Community Transport service 		Capacity building

Civic Education/Code of Conduct			Public Safety

Socio-economic reintegration; capacity to sustain livelihood (income generation, quality life) enhanced

Trust/Confidence building and community Cohesion

Civic education, cohabitation and	 acceptance

Positive changes (behaviour, attitudes, perception, expectations etc)

Psychological support

Access to safety information (code of conduct, Law Enforcement etc)

Agent of Positive change in the community

Rights/responsibilities

Respect, social justice

Self-confidence

Human security and enabling Peaceful environment

What the Beneficiaries gain from the programme?

Positive changes in (behaviour, attitudes, perception, community participation and citizenship)