SIERRA LEONE

PEACEBUILDING FUND

PROJECT STATUS REPORT

30 JUNE 2009

| Project No & Title: | PBF/SLE/E-1 Support to Government’s Capacity for monitoring and coordination of the Peace Building Fund |
| --- | --- |
| Recipient UN Organization: | UNDP | Priority Sector: | Capacity Building of Public Administration |
| National Authority: | Ministry Finance and Economic Development (MOFED) |
| Location: | Freetown |
| Project Cost: | USD 348,125 |
| SC Approval Date: | 15 July 2008 | Starting Date: | August 2008 | Completion Date: | July 2009-Delayed |
| PBF Outcome and priority area | Priority 4. Rebuilding essential government capacity Outcome 13: technical capacity building |
| Project Description: | The Ministry of Finance and Economic Development (MOFED) is the Government institution responsible to oversee PBF projects in Sierra Leone. The PBF calls for national ownership with Government in the lead to initiate and oversee the envisaged peace building interventions. This project will set up a Peace building Secretariat in the MOFED to increase its capacity to plan, monitor and evaluate peace building programmes, among others those funded by the PBF. It is envisaged that the Secretariat will focus on the PBF project monitoring in the first year, after which capacity and experience has been generated to broaden the peace building planning and monitoring to the wider program portfolio of the Ministry of Finance and Development. |
| Immediate Objectives: | Increased Government’s leadership/ownership of the PBF process; Increased capacity for Government oversight of the Peacebuilding programmes; and Improved public awareness and engagement on the PBF and it’s activities |
| Project Progress as at June, 2009 |
| Funds disbursed: | USD 136,815.19 |
| Delivery rate: | 39% |
| Outputs delivered: | PBF Secretariat established, staffed and fully functional at the Ministry of Finance and Development Internet connectivity established to provide information to the public on the progress and achievements of the PBF projects to peace consolidation and stability. Monitoring capacity of the Government enhanced through provision of 2 vehicles to ensure quality results are delivered. The PBFS in concert with the PBF-SCO has undertaken one monitoring trip and two advocacy drives on the four regions (N,S,E&W) |
| Achievements and challenges | Heavy reliance on PBF with no guarantee of funds from the Government. Thus the concern for sustainability of the project Management responses include: The Ministry of Finance and Economic Development is seeking ways with other related stakeholders in ensuring continued support for the Secretariat. The Secretariat has still not been able to perform the task of PBF project monitoring as expected. There appears to be internal problems within the Ministry, and between the Ministry and UNDP that is hampering the work of the Secretariat The PBF staff have thus not been paid for over 5 months. This has seriously rendered them redundant. |