SIERRA LEONE

PEACEBUILDING FUND

PROJECT STATUS REPORT

31 MARCH 2010

| Project No & Title: | PBF/SLE/I-1 Emergency Support to the Energy Sector |
| --- | --- |
| Recipient UN Organization: | UNDP | Priority Sector: | Energy |
| National Authority: | Ministry of Energy and Power and National Power Authority |
| Location: | Freetown, Bo and Kenema |
| Project Cost: | USD 9,000,000 |
| SC Approval Date: | 15 July 2008 | Starting Date: | August 2008 | Completion Date: | Extended to Dec 2009 |
| PBF Outcome and Priority area | Priority 4. (Re-)building of essential government services Outcome 12: Early economic recovery |
| Project Description: | The project aims to contribute to national peace and security by supporting Government‘s effort in providing increased and regular electricity supply to the cities of Freetown, Bo and Kenema. The project provides resources for the supply of fuel, lubricants and rehabilitation of thermal plants at the National Power Authority (NPA) and the Bo-Kenema Power Station (BKPS). |
| Immediate Objectives: | Contribute to increased employment/income opportunities for urban families in Freetown, Bo and Kenema by revitalization of energy based SMEs through increased and sustained power supply. Contribute to increased public revenue base for Government with increased capacity to support poverty related programs. Contribute to a reduced feeling of neglect and disillusionment due to lack of adequate power |
| Project Progress as at March, 2010 |
| Funds disbursed: | USD 8,880, 000 |
| Delivery rate: | 98.67% |
| Output delivered: | Electricity in Freetown has been sustained through funding for procurement of fuel, lubricants and other inputs for the period October - December ($3.5mexpended for 2 months October/November). Security, Peace and increased economic activities sustained during the festive season Rehabilitation of 1 generator in Kingtom Power Station completed Energy output increased from 25MW to 31MW. 4 Operational Vehicles, 6 motorbikes and office equipment have been procured and logistics capacity of NPA enhanced for maintenance and installation activities. Government was able to increase revenue collection by $314,000 in February. |
| Achievements and challenges: | For Bo-Kenema Power Station, provision of fuel was differed and budget for rehabilitation of generator was halved by the decision of Project Board. This will prevent sustainable provision of electricity in Bo-Kenema which has been promised. Un-clarity at the beginning on institutional arrangement for payment of vendors delayed early processing of first invoices. Management arrangements/steps taken include: UNDP Management secured the cooperation of the WB Office to provide guidance in the entire process to ensure accountability and transparency of the entire process. Payments are still outstanding for spares for Bo-Kenema. The supply of fuel to Bo-Kenema seems to be greatly challenged and very unlikely due to Government meddling. Government has requested such funds ($240,000) to be transferred to the Finance Ministry. UNDP awaiting original vendor receipts to issue payment. Bo-Kenema still to provide bank guarantee for UNDP to pay vendor an advance for the rehabilitation of its thermal plants |