SIERRA LEONE

PEACEBUILDING FUND

EMMERGENCY PROJECT STATUS REPORT

30 SEPTEMBER 2009

| Project No & Title: | PBF/SLE/J-1 Supporting the Implementation of the Joint Communiqué through an Independent Investigation into Allegations of Rape and Sexual Violence against Women at the SLPP Headquarters on 16 Mar 2009. |
| --- | --- |
| Recipient UN Organization: | UNDP | Priority Sector: | Democracy and Good Governance |
| National Authority: | Justice Bankole Thompson Commission of Enquiry |
| Location: | Freetown |
| Project Cost: | USD 29,463 |
| SC Approval Date: | June 2009 | Starting Date: | July 2009 | Completion Date: | August 2009 |
| PBF Outcome and Priority area | Priority 2: Good governance and national reconciliation. Outcome 6: national reconciliation |
| Project Description: | In March 2009, Sierra Leone was hit by the biggest eruption of violence since the end of the war between the two main political parties –the ruling APC and the opposition SLPP that lead to injuries, loss of property and alleged rape of SLPP supporters. The UNIPSIL and UNCT brokered peace talks that resulted in the signing of a joint communiqué which attempted to address the key issues brought forward by both parties. The communiqué amongst others condemned all forms of violence and political incitement. Amongst 16 issues of attention, the communiqué categorically condemned any form of sexual violence and without prejudice to any prior police investigation, recommended that the President establishes and independent enquiry to investigate all allegations of rape and sexual violence. |
| Immediate Objectives: | l. "investigating the allegations of rape and sexual, abuse against women which occurred at the Headquarter f the. Sierra Leone People’s arty on l6th March 2009" 2. ,,To identify the persons involved in the substance of the allegations and to determine whether any breach of the law occurred" 3. "To recommend the action to be taken against persons who committed any breach of the law" |
| Project Completed in September 2009 |
| Funds disbursed: | USD 29,463 |
| Delivery rate: | 100% |
| Outputs delivered: | The UNPBF provided funds to ensure That office space for the commission was rehabilitated Commissioners were recruited and remunerated Logistics-Vehicles, computers, stationary etc were provided Transport refunds to witnesses provided |
| Achievements and challenges | The commission concluded its enquiries and has submitted its report to the President. The report concludes that although violence was committed against some supporters e.g bodily harm etc; the commission could not establish that any form of rape occurred based on the evidences received by the commission. |