Liberia Peace Building Fund

QUARTERLY STATUS REPORT AS OF 31 MARCH 2010

| Recipient UN Organization | United Nations Population Fund (UNFPA) | PBF Priority Area: 3 | Strengthening State Capacity for Peace Consolidation |
| --- | --- | --- | --- |
| Implementing Partner(s) | SGBV Crimes Unit, Ministry of Justice, and Ministry of Gender and Development, Government of Republic of Liberia |
| Project Number | UJA05 |
| Project Title | Strengthening Prosecution of SGBV Offences |
| Total Approved Project Budget | US$792,857.00 |
| Funds Committed | US$792,857.00 | Percentage of Approved: |  |
| Funds Disbursed | US$515,261.00 | Percentage of Approved: | 65% |
| SC Approval Date | March 2009 |
| Expected Project Duration | 18 months | Forecast Final Date: | 30 September 2010 | Delay (Months) |  |

| Outputs: | Progress: | % of planned | Expected Progress for Upcoming Month: |
| --- | --- | --- | --- |
| Operational plan for prosecution of SGBV Crimes Developed by MOJ | Completed-Operational plan developed, published and disseminated in q2 | 100% |  |
| SGBV Crimes Unit physically established and staffed and prosecution by the Unit commences | The establishment of SGBV Crimes Unit, employment of staff, training of staff on data base management and printing of prosecution manuals completed in 2009; Prosecution of SGBV cases began in 2009 and the process is ongoing; One trial was successfully completed; One trial is ongoing; 5 cases were indicted during the reporting period; 36 survivors were supported with supportive services | 100% | All cases that will be assigned by Criminal Court “E” are prosecuted Prosecution manuals are disseminated Plans to conduct public perceptions, attitudes and knowledge on SGBV undertaken are developed. |
| SGBV Crimes Unit prosecutors, investigators and victims officers are effectively trained in procedural and substantive areas to enhance prosecutorial effectiveness of SGBV Crimes | Assisted in the facilitation of one quarterly prosecution training in Sinoe County, organized by the Ministry of Justice |  | Training for prosecutors and local police officers of the Women and Children Protection Sections are held |
| Public Education and Awareness of the SGBV Crimes Unit’s work and issues of SGBV Crimes commences, in collaboration with partners | The development of public awareness materials on the Unit work is in progress No community forum or public education was held during this period. In collaboration with the GBV Taskforce, the SGBV Crimes Unit attended and participated in 6 coordination meetings |  | At least 3 community forums are held Public discussions and forums on SGBV issues and the work of the Unit are held on local radio stations SGBV activities are coordinated in collaboration with GBV Taskforce |

Qualitative Achievements Against Expected Results:

Outputs 1: The Operational plan was developed by the SGBV Crimes Unit in collaboration with WACPs of LNP in 2009. The operational plan has continued to serve as working document for the SGBV Crimes Unit. Outputs 2: The SGBV Crimes Unit was officially established, staffed and began prosecution in 2009. Since its inception, the SGBV Crimes Unit investigators, victims support advocates and prosecutors continued to use their training skills to build up SGBV cases for prosecution. For this reporting period, 1 (one) trial was successfully completed and the perpetrator was convicted; and there is one other trial ongoing. At the same time, the SGBV Crimes Unit indicted perpetrators in 5 (five) different cases of SGBV crimes. All the victims and witnesses in the above cases were able to appear before the grand jury during February term of court to assess their cases. After grand jury assessment, 4 of these cases got true bill and 1 case got bill of ignoramus. With true bill, it means that there are probable causes for the SGBV Crimes Unit to prosecute and the case with bill of ignoramus cannot be prosecuted at this time because it lacks insufficient evidence. The successful prosecution of SGBV cases in Montserrado County has begun to create awareness among community members that sexual violence is a crime and that perpetrators of such crimes must be held accountable. The prosecution of SGBV cases will continue in the coming months. In order to strengthen and improve prosecution of SGBV Crimes, the SGBV Crimes Unit will be disseminating prosecution manuals developed and printed in 2009 among relevant stake holders. The SGBV Crimes Unit is also contemplating on starting a public on perceptions, attitudes, and knowledge on SGBV activities. In addition to prosecution, 36 survivors of sexual violence crimes were supported by the Unit through basic counseling, referral for other supportive services and court representation. Outputs 3: The Ministry of Justice quarterly prosecution training workshop was held in Greenville, Sinoe County from 31 January to 3 February 2010. Two (2) prosecutors from the Unit conducted sessions on Trial Advocacy. The Chief Prosecutor, along with the Minister of Justice, Hon’ble Christiana Tah and Madam Benetta Warner, Head of the Women and Children Protection Section attended a two day summit on Global Partnership to End Violence Against Women organized by Vital Voices, the Avon Foundation for Women and the U.S. State Department from 10-12 March 2010. The summit marked the first step in the organization’s joint commitment to transform women’s lives through innovative solutions and “best practices” strategies to combat the scourge of violence against women. No in-house training activity, community forums and school based awareness sessions were held for staff of the Unit during this quarter due to the late arrival of funds for the quarter. Outputs 4: There was no public awareness or forum held during this quarter. There was a delay in receiving fund to conduct activities. However, the SGBV Crimes Unit is currently conducting an assessment through the 24hrs hotline incoming calls to map areas of high incidences of sexual violence. This activity will enable the Unit to identify potential survivors, perpetrators, and other potential risks to appropriately design public awareness activities through sensitization and radio programs. In collaboration with national GBV Taskforce, The SGBV Crimes Unit continued to collaborate with other partners and government ministries to ensure that sexual violence against women, men and girls in post conflict Liberia is minimized; and that the perpetrators of crimes are held accountable and punished. For this period, The SGBV Crimes Unit attended and participated in 6 coordination meetings including GBV Taskforce meetings, Health and Psychosocial Pillar meetings and Child Protection network meetings to discuss issues of protection for women, men and children of Liberia.

Challenges:

There is a problem for the SGBV Crimes Unit to adequately respond to cases emanating from areas outside Monrovia such as Caresburg, Todee, Bensonville RIA highway, Po River etc due to budgetary constraints. For cases outside Monrovia, the Unit is required to make regular vehicle movements in and out to attend to victim or mobilize witnesses for trial, bring witnesses to Monrovia in advance to attend court trials, provide lodging and feeding for witnesses while in Monrovia for trial which were not budgeted for in the project document. Lack of budgetary allocation to support victims with special needs during trial. Many witnesses who often come to the court to testify have to spend their days in full in court without food. During and after trial, many witnesses may need restitution services, relocation and resettlement allowance, educational support and livelihood options to prevent further violence. There are no specialized institutions with adequate services available in Montserrado to respond to victims with such needs. Court officials in magisterial courts are still charging fees to victims and their families in processing their cases through criminal court “E”. This action by magisterial courts is intimidating and scaring to the victims and their family members thereby discouraging reporting where people may not have money to go to court. Prosecuting cases with juvenile perpetrators: sexual violence cases with juvenile perpetrators are handled in a specialized court known as “Juvenile Court”. For juvenile cases, the trial procedures are different and the Unit is not fully represented during trials. Since the insertion of the SGBV Crimes Unit, there has been no juvenile case successfully prosecuted in the juvenile court. Lack of interviewing space for victim: currently, the SGBV Crimes Unit does not have an ideal space to conduct basic counselling for victims with special needs. In order to maintain confidentiality and ensure victims centered approach, there is a need to have a well furnished interview space separate from the main office. Many case files lack identifying information to trace witnesses and their locations .Some cases occurred from 2004 to 2007 and the Unit cannot trace their initial Respondents No training and outreach activity was held during this quarter as funding for the first quarter 2010 (January –March) was not received until the end of the quarter. Some case files lack identifying information to trace witnesses and their location. Some cases occurred from 2004 – 2006 and the Unit cannot trace initial Respondent. The lack of investigative skills of the police to conduct proper investigation. Police most times do not visit crime scenes and give crime scene reports, because of inadequate or no logistical support. Lack of Emergency Victim Support. There is often no money to respond to emergency cases such as feeding for victims, clothing etc.

End.