# Peacebuilding Fund (PBF)

# Immediate Response Facility

# (BURUNDI)

# Project Summary

| Recipient UN Organization: | UNDP | PBF Priority Area: | Strengthen national capacities to promote coexistence and peaceful resolution of conflict |
| --- | --- | --- | --- |
| Implementing Partner(s): | Independent National Electoral Commission |
| Project Number: | PBF/IRF-18 (Burundi) |
| Project Title: | Emergency Support to the Burundi Electoral Process |
| Total Approved Project Budget: | 3,000,000 USD |
| Location: | All the country |
| SC Approval Date: |  |
| Project Duration: | 8 months | Starting Date: | 1st May 2010 | Completion Date: | 31st Dec. 2010 |
| Project Description: | The project aims at solving critical aspects of the electoral process that need to be addressed as they are recognized as capable of having catalytic impact on the ongoing electoral process. |

| Peacebuilding Impact: | Institutions in charge of the electoral administration are strengthened and have the capacity to organize and manage electoral processes that respond to internationally recognized standards of quality. Citizens of Burundi, notably women, are able to exercise their rights to accomplish their civic duty to choose their representatives, and to be elected to the decision-making bodies. |
| --- | --- |
| Outcome(s): | Enhanced capacity of decentralized ID issuance centers to deliver quality service to men and women Increased number of women candidates in different elections, and of women elected Unbiased coverage of different phases of the process is carried out by the media The legislative election ballots paper and envelopes are produced on time for all lists of candidates through the reduction of the electoral funding gap |

| Outputs and Key Activities: | Outputs: 1 million potential voters, (at least 50% of women) get an ID, participate in the electoral process Women account for at least 30% of all elected officials at national and local level; All radio, TV, and print media implement the PACAM 4 million ballots paper are available for distribution through reduction of the electoral funding gap Activities: Provide 129 ID issuance centers with equipment, forms, supplies, and trained support staff Raise level of awareness on women participation and train women as voters, candidates, observers and agents for peace and after their election Implement a media synergy for 2010 campaign and election coverage Provide legislative election 4 millions of ballot papers and envelopes |
| --- | --- |
| Indicator and Benchmarks: | Number of ID delivered; Proportion of women who get their ID At least 50 % of voters registered are women; % of elected women in decision making positions % of joint coverage programs presented by the media Number of ballot papers and envelopes produced and distributed |
| Procurement: | IT; typing machines; camera photo kits; supplies; ballot papers and envelopes |