Annex A

Work Plan for: Supporting Gender Equality and Women’s Rights in Timor-Leste

Period: 2008 to 2009.

| JP Outcome 1: Improved protection of women and girls through the establishment of legal frameworks and mechanisms to uphold their rights. |
| --- |
| UN Organisation-specific Annual Targets | UN organization | Activities | Time Frame | Implementing Partner | Budget |
|  |  |  | Q4 08 | Q1 09 | Q2 09 | Q3 09 |  | Source of Funds | Budget Description | Amount (USD) |
| JP Output 1.1: Legislation passed and national action plans developed to prevent and combat Domestic Violence and human trafficking |
| Promulgation of the Domestic Violence Law and its implementation supported. | UNFPA | Advocacy & technical support for DV law and Penal Code adoption and promulgation. | x |  |  |  | SEPI, MoJ, MSS DNRS; PRADET; Rede Feto; JSPM; Fokupers; PNTL VPU; Referral Network of support partners in the five districts. | MDG TF | [Contracts] Meetings with NGO partners Design of Briefing Kits for MPs, key line ministries and civil society Production of IEC materials on DV law Consultations for MPs, key line ministries and civil society on the DV law Media launch on DV law Workshops with Ministries on NAP on GBV | 8,000 |
| National Action Plan on Domestic Violence developed and implemented. |  | Develop NAP on Domestic Violence; |  | x | x | x |  | MDG TF |  |  |
|  |  | Consultations with key stakeholders at national and district levels and task forces for development of NAP on domestic violence. |  | x | x | x |  | MDG TF |  |  |
| National Action Plan on Human Trafficking developed and its implementation supported. | IOM | Assist ITWG to assume leadership. | x | x | x | x | MoDS; MoFA; MoF; MoJ; MoE; MoSATO; MSS; SoS Migration and Overseas; SEPI; NGOs and service providers. | MDF TF | [Personnel] Meetings with ITWG participants Documentation and communications Project staff and administrative assistance Training workshops (inclusive of venue rental, food and beverage, technical assistance and IEC ma Terials | 51,029 |
|  |  | Technical support to the ITWG. | x | x | x | x |  | MDG TF |  |  |
|  |  | Establish interagency, multi-sectoral, and broad based stakeholder forum & quarterly networking meetings. | x | x | x | x |  | MDG TF |  |  |
|  |  | Assist the GoTL to establish a task force for drafting NAP on anti-trafficking and train task force members. | x | x | x | x |  | MDG TF |  |  |
|  |  | Task force members drafting session held; and community consultations held. | x | x |  |  |  | MDG TF |  |  |
| JP Output 1.2: Capacity building programme developed to upgrade the knowledge and skills of government officials, NGOs and CBOs involved in implementing action plans related to combating domestic violence and human trafficking at national and local levels. |
| National capacity building programme on human trafficking developed and implemented. | IOM | Training for ministries and TF members on drafting, implementing, monitoring NAP. | x | x | x |  | MoFA; MoSATO; MSS; PNTL VPU; NGOs and service providers. | MDG TF | [Personnel] Training workshops (inclusive of venue, rental, food, travel assistance and IEC materials) Project staff and administrative assistance | 24,527 |
|  |  | Advocacy with ministries, legal sector, CSOs. | x | x |  |  |  | MDG TF |  |  |
| National capacity building on GBV in place. | UNFPA | Develop Standard Training Module on Domestic Violence | x | x |  |  | SEPI; MoJ; JSMP/VSS; PRADET; Fokupers; Rede Feto; local/district administration; suco leaders; PNTL VPU; TLPDP; UNPOL | MDG TF | [Contract] Development Printing of DV Training Module for Police. | 1,000 |
|  |  | Training of Police on the Domestic Violence Legislation; and | x | x |  |  |  | MDG TF | [Contract] Training for the Police Academy , including Training of Trainers (TOT) on DV Legislation; and | 11,000 |
|  |  | Training of the Legal Sector on the Domestic Violence Legislation. | x | x | x | x |  |  | [Contract] Development and printing of Training Module for DV Law for Legal Sector; and Training seminars/workshops on the DV Law | 7,000 |
| Staff members of PNTL VPU & community police are aware of and practice their obligations to protect women and children against GBV | UNICEF | Training on the rules and procedures & other relevant laws & policies for women and children’s protection e.g. DV Law, Penal Code | x | x | x | x | UNFPA; the Church & other religious; national & INGO DNRS/MSS; Child Protection and Women’s Units; PNTL VPU & UNPOL. | MDG TG | [Contract] Support for trainings at district and national levels for all VPU and Community Police Officers on the Rules of Procedure, Child Protection and Gender-based Violence. | 10,000 |
| Capacity of local authorities to prevent trafficking, DV, sexual assaults increased. | UNFPA | Training of suco councils and district administrators on DV legislation. | x | x |  |  | SEPI; MoJ; JSPM/VSS; PRADET; Fokupers, Rede Feto, District Administration officials, suoo leaders, VPU TLPDP & UNPOL. | MDG TG | [Contract] Consultations with key partners on the development of the content of the module for Suco Councils and District Administration Training seminars/workshops for Suco Councils and District Administration on the DV Law Printing of Training Module for DV Law for Suco Councils and District Administration | 4,000 |
| Capacity of local authorities to prevent trafficking increased | IOM | Train suco councils and state administrators in 5 districts on human trafficking, appropriate responses, community project design implementation and monitoring. | x | x | x | x | Suco councils and MAEOT | MDG TG | [Personnel] Training workshop (inclusive of venue, rental, food, beverages, travel assistance and IEC materials) District level office set up, operation and maintenance and communications Project staff and administrative assistance | 82,765 |
|  |  | Provide suco councils on on-going support both technical and financial, in development, implementation, and monitoring of local counter-trafficking initiatives in 5 districts. | x | x | x |  |  | MDG TF |  |  |
| JP Output 1.3: Information, education and communication strategies developed and implemented on domestic violence and human trafficking at national and local levels |
| Socialization Campaign on GBV, child protection laws and policies and referral pathways conducted. | UNFPA | National Socialization Campaign on DV Legislation (targeting key actors: police, prosecutors, judiciary, Chefes do sucos). | x | x | x | x | SEPI, MoJ, DNRS, PRADET, Rede Feto, Fokupers, JSMP, VPU/PNTL, Referral Network of support partners in the Baucau, Covalima Dili, and Oecussi. | MDG TF | [Contract] Roadshow – Media Campaign (TV and Radio in 16 districts) Production of IEC and posters, leaflets Production of booklets on the DV law in several languages including Tetum and Portuguese) | 60,000 |
| Awareness of anti-trafficking messages and means of self-protection increased in all districts. | IOM | Annual public information campaigns targeting not less than 5 districts per year. | x | x | x | x | MoF, MAEOT, MSS, PNTL, VPU, NGOs and service providers. | MDG TF | [Contract] Design and production of IEC materials Focus group discussions and travel District level office set up, operation and maintenance | 63,881 |
|  |  | Annual pre and post campaign awareness assessment in each selected district. | x | x |  |  |  | MDG TF |  |  |
|  |  | Media training workshops in each district capital. | x | x |  |  |  | MDG TF |  |  |
| Children, women, families, communities and their leaders, demonstrate increased awareness of children and women’s rights to protection from GBV. | UNICEF | Community-based advocacy campaigns and social mobilization on GBV against children and women in all districts; and | x | x |  |  | SEPI, MoJ; MoH; DNRS within Ministry District Administration, members Suco Councils, VPU PRADET , Rede Feto, Fokupers, JSMP, Referral Network of support partners in the Baucau, Suai and Oecussi districts; UNMIT Justice (Corrections) and UNDP Prison Project. | MDG TF | [Contract] Advocacy materials, project support and technical staff costs [Contract] Printing and translation of IEC materials | 23,000 |
|  | UNFPA | Develop and distribute advocacy materials. | x | x |  |  |  | MDG TF |  | 10,000 |
| Controlling Violent Behaviour for offenders in all prisons. | UNFPA | Implementation of ‘Controlling Violent Behaviour Training Programme for Violent Offenders in prisons. | x | x | x |  | MoJ, UNDP Prisons Advisory Unit and UNMIT Corrections Unit. | MDG TG | [Contract] Printing and translation of further amendments to training manual TOT and follow-on training on anger management programme conducted in all prisons | 8,000 |
| JP Output 2.1: Improved implementation of ongoing conditional cash transfer schemes. |
| Technical Support provided for improving the design and implementation of ongoing conditional cash transfer (CCT) schemes of the Ministry of Social Solidarity | UNDP | Hire a team of consultants to develop M & E framework and develop an identification mechanism of beneficiaries and establish a comprehensive database system. | x | x |  |  | MSS, MoF, MoE, MoH | MDG TF | [Personnel] Consultancy | 70,000 |
|  |  | Hire a consultant to draft a decree law of social protection scheme. | x | x |  |  |  | MDG TF | [Personnel] Consultancy | 56,000 |
|  |  | Develop an innovative means of cash payment/distribution to reduce its risk and corruption. |  | x | x | x |  | MDG TF | [Personnel] Consultancy | 26,000 |
|  |  | Assist the scheme to further strengthen the identification mechanism. |  | x | x | x |  | MDG TF | [Personnel] Consultancy | 44,260 |
| JP Output 2.2: National and local referral mechanisms and services established and/or strengthened for the protection of victims of domestic violence and human trafficking. |
| Referral services for women and child survivors, and reporting mechanisms, strengthened. | UNFPA | Builds PRADET’s administration and financial systems as well as to provide support to proposal development, projects reporting to sustain project activities. | x | x | x | x | PRADET Timor Lorosae | MDG TF | [Personnel] UNV Contract | 67,500 |
|  |  | Provides programmatic and technical issues on domestic violence to PRADET staff. | x | x | x | x |  | MDG TF | Per Diem and airfares for every four to five months lasting five to six weeks. |  |
|  |  | Five national staff of PRADET who manages the only forensic examination room in the country and for support staff to run the project | x | x | x | x |  | MDG TF | [Personnel] Contracts for five national staff. | 17,160 |
|  |  | Maintenance and travel cost for PRADET activities. | x | x | x | x |  | MDG TF | [Supplies] Contract with PRADET to provide travel, maintenance of vehicle and other operational costs | 5,460 |
|  |  | Grant to JSMP Victim Support. | x | x |  |  | JSMP | MDG TF | [Contract] Operational cost of running referral programmes. | 50,000 |
|  |  | Grant to Fokupers Safe House Programme. | x | x |  |  | Fokupers | MDG TF | [Contract] Operational cost of running referral programmes. | 30,000 |
|  |  | Finalisation of and piloting the Medical Forensic Protocol. | x | x |  |  | MoH | MDG TF | [Contract] Training of doctors and other health care professionals on forensic protocol. | 17,000 |
|  |  | Child-sensitive Referral Protocols and Data Collection. | x | x |  |  | MSS | MDG TF | [Contract] Consultations with partners on development of referral protocols; Training to partners on protocols and data collection standards. | 4,000 |
| National referral guide on roles, responsibilities. | IOM | Update mapping of services. Workshop for service providers. Meetings to develop MoUs on referral & procedures. SOP manuals produced and distributed. IEC materials for service providers and victims produced and distributed. Annual training and service monitoring workshops. | x | x | x | x | MoFA; MoSATO; MSS; PNTL VPU; NGOs and service providers. | MDG TF | [Contract/Personnel] Consultant, travel, communications, project staff and administrative assistance | 55,111 |
| SOP on referral of trafficking. |  |  |  |  |  |  |  | MDG TF |  |  |
| At least bilateral 4 MoU signed. |  |  |  |  |  |  |  | MDG TF |  |  |
| Health, legal, and psychosocial support services for victims of domestic violence in the five districts. | UNICEF | Strengthen National and District Referral Networks. | x | x | x | x | MSS Directorates of Social Reinsertion, Child Protection & Women’s Units: PNTL VPU; Faith-based institutions, local and INGOs. | MDG TF | [Contract] Planning with Social Services, NGO and UN partners to design and implement a strategy for comprehensive victim services, including shelter. Develop action plan for shelters and guidelines for management). Support Shelters and Victim Services at district level, in partnership with MSS. [Personnel] Support to Child Protection Working Group and Networks | 100,000 12,000 |
| Case Management and comprehensive direct assistance provided to 60 survivors of trafficking. | IOM | Operate shelter in Dili by designing/delivering comprehensive services (medical & psychological care, temporary accommodation, education & income generation & domestic international return & reintegration). Develop/implement management & skills transfer plan with progressive handover to local partner | x | x | x | x | National Directorate for Social Reinsertion (DNRS), PNTL, VPU, Immigration Department, Alola Foundation, PRADET, Fokupers, Santa Bahkita, relevant NGOs and service providers. | MDG TF | [Contract] Food, security, rent, utilities International case and shelter management expert, shelter project staff and administrative assistance | 178,567 |
| JP Output 3.1: Tools on gender sensitive planning and gender responsive budgeting developed to increase the knowledge and skills of senior government officials, members of local assemblies and local council members |
| Gender-Disaggregated Beneficiary Assessments; Gender sensitive budget analysis, etc contextualised in a Timorese setting. | UNIFEM | Establish a working group from Women’s Caucus, Parliamentary Committees, academia. | x | x | x |  | MoF, SEPI, MoH, MoE, National Parliament and UNDP. | MDG TF | [Personnel] Contractual services of Consultants (SSA). Travel, meeting and reporting costs. Contractual Services Travel Costs | 39,300 35,020 |
|  |  | Assessment of MoF, pilot ministries, and SEPI staff and other ministries’ capacity. | x | x | x |  |  | MDG TF |  |  |
| Increased knowledge and skills among partners on GRB and budget template formulated and executed. | UNIFEM | Develop/implement training, TOT and advisory work; policy development with MoF, MSS, Women’s Caucus & Committees at the National Parliament. | x | x | x |  | MoF | MDG TF | [Personnel] Contractual services of Consultants (SSA). Travel, meeting and reporting costs. Contractual services of Consultants (SSA). Travel, meeting and reporting costs. Contractual services of Consultants (SSA). Travel, meeting and reporting costs. | 70,990 36,810 29,200 |
|  |  | Develop budget formulation and execution template. | x | x | x |  |  |  |  |  |
|  |  | Develop mechanisms for regular updates on budget implementation and undertake regular data collection. | x | x | x |  |  |  |  |  |
| JP Output 3.2: Civil society (NGOs, Women’s groups, CBOs, academia) trained on gender sensitive planning and gender responsive budgeting to advocate for, scrutinize and monitor public expenditures. |
| Capacity of NGOs / CSOs & academic institutions strengthened. | UNIFEM | Identify academic institutions and NGOs. | x | x | x |  | Academic institute yet to be identified. |  | [Contract] Contractual services of Consultants. Travel, meeting and reporting costs. [Contract] Contractual services of Consultants. Travel, meeting and reporting costs. | 24,120 20,000 |
|  |  | Prepare/conduct training. | x | x | x |  |  |  |  |  |
|  |  | Institutions analyze budget by GRB both at national and target district level, present findings, finalize report. | x | x | x |  |  |  |  |  |
|  |  | Develop/conduct training NGOs on advocacy for GRB. Follow up on action plans of NGOs. |  |  |  |  | Women’s NGOs (Proposals from Rede Feto and its NGO members). |  | [Contract] Contractual services of Consultants. Travel, meeting and reporting costs. | 21,750 |
| JP Output 3.3 Gender responsive budgets prepared and pilot tested in selected line Ministries and suco councils. |
| Application of GRB in three line ministries – MoH, MoE, MSS | UNIFEM | Application of GRB in three line ministries – Health, Education, MSS |  |  | x | x | MoF |  | [Contract] Contractual services of Consultants. Travel, meeting and reporting costs. | 17,500 |
|  |  | Baseline assessment of capacity and gaps of suco councils |  |  | x | x | UNIFEM, MoF, MAEOT |  | [Personnel] Contractual services of Consultants (SSA). Travel, meeting and reporting costs. | 19,620 |
|  |  | Prepare training design and conduct training on GRB for suco councils |  |  | x | x | UNIFEM, MoF, MAEOT |  | [Personnel] Contractual services of Consultants (SSA). Travel, meeting and reporting costs. | 18,102 |
|  |  | Review and coordinate with local structures in budget formulation |  |  | x | x | UNIFEM, MoF, MAEOT |  | [Personnel] Contractual services of Consultants (SSA). Travel, meeting and reporting costs. | 5,112 |
|  |  | Facilitate discussion & presentation of GRBs |  | x | x |  | UNIFEM, MoF, MAEOT |  | [Personnel] Contractual services of Consultants (SSA). Travel, meeting and reporting costs. | 34,319 |
| Programme Management Unit: Effective implementation of the Joint Programme and the Programme Management Committee through a Programme Management Unit |
| Effective coordination function for Joint Programme ensured | UNIFEM | Day-to day JP management. | x | x | x | x |  |  | Personnel/Consultancy Workshops (Inception Mid-term Review, Annual review) Meeting costs (NSC, PMC) Communication, Travels, Equipment, Supplies | 95,250 10,000 6,000 17,120 5,000 |
|  |  | Implementation support; integrating work plans, budgets; reports. | x | x | x | x |  |  |  |  |
|  |  | Overall monitoring and evaluation, reporting mechanisms. | x | x | x | x |  |  |  |  |
|  |  | Progress and financial reports. | x |  |  |  |  |  |  |  |
|  |  | Manage the asset inventory. | x | x | x | x |  |  |  |  |
| Total Planned Budget 1,714,646 |
| Including* | Total for UNDP | 209,998 |
|  | Total for UNFPA | 321,128 |
|  | Total for UNICEF | 155,150 |
|  | Total for UNIFEM | 540,578 |
|  | Total for IOM | 487,792 |

* f the Joint Programment and signature of all parties involved or following the Annual/Regular reviewexample in reviews and agr* The Total Planned Budget by UN Organization should include both programme cost and indirect support cost