Final Narrative (+progress) report

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization(s) |  | Sector(s)/Area(s)/Theme(s) |
| --- | --- | --- |
| WHO D2-16a UNICEF part of this joint project, D2- 16 b is still ongoing, this report is thus a progress report for UNICEF and final narrative WHO |  | (old Cluster D) Health and Nutrition SOT |

| Programme/Project Title |  | Programme/Project Number |
| --- | --- | --- |
| Strengthening Immunizations Services in Iraq |  | D2-16a Atlas project number: 66896 Atlas award number: 54896 |

| Programme/Project Budget |  | Programme/Project Location |
| --- | --- | --- |
| UNDG ITF: | Total USD 8,162,830, WHO USD (6,221,828), UNICEF USD 1,941,002 |  | Region (s): | All over Iraq |
| Govt. Contribution: | 25 millions for vaccine for 2006, difficult to estimate other recurrent cost ) |  | Governorate(s): | All over Iraq |
| Agency Core: | 798,369 |  |  |  |
| Other: UNICEF | 2,860,000 |  | District(s) | All over Iraq |
| TOTAL: | USD 34,880,197 |  |  |  |

| Final Programme/ Project Evaluation |  | Programme/Project Timeline/Duration |
| --- | --- | --- |
| Evaluation Done No Evaluation Report Attached No |  | Overall Duration May 2006 – 30 June 2008 Original Duration May 2006 – April 2007 Programme/ Project Extensions The project was extended until 30 June 2008 D2 16b (UNICEF) is still ongoing |

- Provide a brief introduction to the programme/ project (one paragraph)

The project will strengthen Immunization services in 2006/2007 by expanding access to immunization service through supplementary immunization activities (campaigns) as well as the support of routine out reach activities to marginalized, difficult to reach and underserved population. Provision of urgently needed vaccine, auto-disabled syringes and other immunization related supplies for routine and supplementary immunization activities as well as capacity building for mid-level and peripheral level staff in addition to accelerated/disease surveillance and control activities.

- List programme/project outcomes and associated outputs as per the approved Project Document.

- Maintain poliomyelitis free status during 2006 and 2007 all over Iraq.

- Measles cases reduced by more than 90% compared to 2004.

- Achieve routine infant coverage of 90% by all essential vaccine at the national level and at least 80%, in every district.

- National laboratories for measles and poliomyelitis were fully accredited by WHO as members in the global network for measles and poliomyelitis. The 2 laboratories were fully equipped; provided with reagents and supplies, staff trained and both laboratories Polio free status maintained for the seventh year in a raw in the presence of high quality surveillance.

- List the UN Assistance Strategy Outcomes, MDGs, Iraq NDS Priorities, ICI benchmarks

relevant to the programme/ project

The project is in line with the UN strategy outcomes, By 2010, health and nutrition related programs enhanced to ensure 20% increase in access to quality health care services with special focus on vulnerable groups

The project is also in line with MDGs, Goal 4: Reduce child mortality and Goal 6: Combat HIV/AIDS and other diseases.

The project is also in line with NDS priorities; Reduce child and maternity death.

ICI relevant benchmarks: Design and carry out specific policies including reforms and investments toward achieving the Millennium Development Goals

d.	List primary implementing partners and stakeholders including key beneficiaries.

The primary implementing partners are Ministry of health and UNICEF. Key beneficiaries are women and children

- Report on the key outputs achieved and explain any variance in achieved versus planned results. Who have been the primary beneficiaries and how they were engaged in the programme/ project implementation?

- Technical support for disease surveillance and planning, implementing and monitoring of vaccination activities sustained.

- Supporting planning, implementation and monitoring of national immunization days.

- Support MoH to move from aggregate surveillance to measles case based surveillance.

- National Measles Laboratory (NML) and National Polio Laboratory (NML) capacity for testing and confirming measles and polio cases as well as isolating measles and polio viruses strengthened and both laboratories recognized as members of WHO network of accredited laboratories.

- Report on how achieved outputs have contributed to the achievement of the outcomes and explain any variance in actual versus planned contributions to the outcomes. Highlight any institutional and/ or behavioural changes amongst beneficiaries at the outcome level.

High quality surveillance for EPI target disease was achieved through WHO extensive and continuous support in the area of disease surveillance.

Reaching and vaccinating more than 90% of children against poliovirus  maintained the polio free status in the country.

Mothers are parents are better oriented regarding the importance of vaccinating their

- Explain the overall contribution of the programme/ project/ to the ICI, NDS, MDGs and Iraq UN Assistance Strategy.

The program succeeded in maintaining polio free status which is one of the major childhood crippling and killing diseases, thus contributed to reduction in child mortality and morbidity

- Explain the contribution of key partnerships including national, international, inter-UN agency, CSO or others towards achievement of programme/ project results.

The UN has had to be innovative in the modalities adopted on how to operate in Iraq. The deterioration of the security situation, high turnover of staff and the paradox of humanitarian and developmental assistance are factors that have led to the use of cross border operations.

The responsibility of enhancing and improving health indicators falls heavily on the MOH, but it is recognized that the actions undertaken by other ministries also have a great impact on successful implementation. Hence, WHO works closely with Ministries of: Education, Higher Education, Environment, Municipalities and Public Works, Agriculture, Interior, Finance and Planning.

Through the programmatic approach adopted by the UN in Iraq, WHO as the leading agency in health, works in close collaboration with all the other Health Cluster members including UNICEF, WFP, UNFPA, UNIDO UNOPS, IOM and UNIFEM. This collaboration occurs at the planning and implementation stages to ensure consistency and continuity and to prevent overlapping.

During this period WHO has been actively engaged with USAID and other international organizations.

WHO as the leading agency in the health and nutrition cluster acts as the secretariat for the Health cluster working group biweekly meetings. These meeting are led by the MOH with the [participation of the international organizations and donors. During these meeting different policies are discussed, proposals are endorsed

- Highlight the contribution of the programme/ project on cross-cutting issues:

- Were the needs of particularly vulnerable or marginalised groups addressed?

Delivering the vaccine through out reach and house to house visits is the best guarantee of reaching the hardest to reach..

During planning, implementation, monitoring and evaluation of out reach activities and NIDs; special attention will be given to reaching the hard to reach and the marginalized population. Out reach activities and House to house immunization with special attention to marginalized groups is guarantee to equity and attention to the poor and the hard to reach.

How did men and women benefit from the programme/project?  How were gender inequalities handled?

Reducing the circulation of EPI targeted diseases among children will reduce the probability of transmission of the disease to younger and older household contacts, thereby reducing the overall occurrence of these killer diseases in community as a whole..

Delivering the vaccine through out reach and house to house visits is the best guarantee of all children irrespective of sex.

- Were environmental concerns addressed including environmental impact/risk assessment where relevant?

Special attention will was given to injection safety; particularly disposal of used needles and empty vials is a paramount issue of immunization programme in Iraq. The 4000,000 used syringes and needles as well as 500,000 empty vials will be appropriately disposed off mainly by incineration. If incineration is unavailable open burning and proper dumping will be a last resort. One of the functions of supervisors is to monitor how used needle, syringes and empty vials are disposed off.

- Were there any specific issues in relation to the security situation?

The project is planned at UN security phase four in Iraq, which is why it mainly counts on national capacity implementation. The security issues are handled through UNDSS security advisory notes. WHO national staff, through the guidance of the WHO international staff based in Amman, will continue to maintain their low profile and observe both agency security guidelines and UNDSS security restrictions on the movement of national staff in Iraq.

All members of immunization teams will be well known and trusted members of the same community he/she is to immunize; this will reduce security risks and facilitate acceptance and cooperation of the targeted population.

- Did the project contribute to employment generation (gender disaggregated)?

35% of the vaccination team will need hired vehicles for movement from village to village, therefore during the 10 days of the campaign there will be an increased income for the 3500 vehicle drivers and owners whose vehicles will be used during the campaign.

All the out reach activities will need one hired vehicle per week  to conduct out reach visits, this will generate jobs for one day each week for 12 months for 500 vehicle owners who will be hired to carry out this activity.

- Provide an assessment of the programme/ project based on performance indicators as per approved project document using the template in Section IV

See Sector IV

- Report on any assessments, evaluations or studies undertaken relating to the programme/ project and how they were used during implementation. Has there been a final project evaluation and what are the key findings? Provide reasons if no evaluation of the programme/ project have been done yet?

Internal review of Polio eradication activities was conducted by independent reviewers which were selected from experienced medical schools staff. The selected staff were trained and provided with standard protocols for field activities that include all hospitals with special emphasis on children hospitals. Internal review findings and recommendations was discussed and agreed upon with MoH concerned staff. Special training and orientation sessions were designed for surveillance staff to assure understanding of and enable management of identified deficiencies and draw backs.

One internal review was conducted in 2004 and another in 2006. (Annex 1)

Annual accreditation of national polio, and national measles laboratories, as part of the global network for these laboratories, is following WHO international standard procedures. This includes sending of unknown panels for crosschecking and re testing all positive samples and a percentage of the negative samples. Both laboratories are now accredited and their results are recognized by the WHO global network.

Polio and measles incidence is monitored according to international standards. Performance of surveillance activities are controlled by international experts and weekly feedback is sent to all surveillance staff at all levels.

In addition, a monthly system of monitoring vaccination coverage among infants, as well as the availability of vaccines and the status of the cold chain system is now in place.

EPI coverage survey was carried out in June 2007 in Kurdistan region. The survey results shows that EPI programme in the three Governorates has a good capacity in reaching under one children. Nevertheless, there is a need to further strengthen the programme to reduce miss-opportunities and drop-out rates through; increasing and sustaining routine immunization services provided at health centers; supporting sustained out-reach and mobile immunization services specially for remote rural areas; enhancing EPI staff capacity; focused social mobilization campaign to raise knowledge about the importance of immunization specially TT for women and the importance of adhering to the immunization schedule set for children

- Indicate key constraints including delays (if any) during programme/ project implementation

Rapid turn-over of counterpart staff has adversely affected co-ordination and consequently delay the implementation process.

Increase in price of raw materials, fuel, oil and other basic commodities raised the value of local contracts unfavourably and limited the scale of the interventions.

Border closures for several days impeded the timely delivery of supplies

Insecurity have limited health staff access to some communities and resulted in the death of 2 paramedical staff while transferring vaccines in AL-Khalis (Dilyala Govenroarte)

- Report key lessons learned that would facilitate future programme design and implementation.

Despite the difficult security situation that followed the war; WHO and UNICEF have supported MoH in the conduction of 2 rounds of house to house national immunization days with polio vaccine and 2 measles campaigns; all these campaigns were successful in reaching and vaccinating more than 95% of the targeted population. These campaigns lead to the maintenance of polio free status in Iraq and prevented the occurrence of measles epidemics during the last 3 years.

Investment in EPI system is the most cost effective approach in health in Iraq. WHO and UNICEF are working hard with MoH to take full responsibility of routine immunization, during the past year MoH for the first time purchased all vaccine for routine immunization, this cost MoH this year around 25 million dollars. MoH  will have to invest more money next year by procuring improved vaccine which have less side effects and are more  stable than the traditional vaccines under use. In addition  each vial of the improved vaccines will have a temperature monitor to ensure that every single dose administered is fully potent.

WHO is working now with MoH to study the burden of pneumonia, middle ear infection and meningitis caused by Haemophilus influenzae type b organism, the objective is to work out the needed base line data and cost effectiveness data to justify the introduction and measure the impact of Hib vaccine in the EPI. The procurement of this new vaccine is expected to cost MoH around 100 million $US.

In conclusion WHO and UNICEF are working step by step to assist MoH shoulder all vaccine procurement as well as the recurrent cost of running and improving routine EPI program, however, UNICEF and WHO will definitely need to support supplementary immunization activities till routine EPI coverage reaches at least 80% in every district

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| IP Outcome 1 Maintain poliomyelitis free status during 2007 all over Iraq. |
| IP Output 1.1 Support MoH to conduct 4 rounds of house to house polio National Immunization Days (NIDs) targeting 4.7 million under 5 children in each round. | Indicator 1.1.1 % of under 5 children reached and vaccinated through house to house visits during NIDs | Only 70% of under 5 children are vaccinated against poliovirus through the routine vaccination Programme | More than 90% of under 5 children vaccinated by 2 doses of oral polio vaccine through house to house visits | More than 90% of under 5 children vaccinated by 2 doses of oral polio vaccine through house to house visits | No variance | Routine MoH reports verified by national WHO and UNICEF staff as well as UNICEF MICS 3 survey |  |
|  | Indicator 1.1.2 Absence of poliomyelitis cases in the presence of good surveillance | No polio case was reported in the pervious 5 years | Maintain poliomyelitis free status | Poliomyelitis free status was maintained during 2006-2008 | No variance | Routine MoH reports and results of testing stool samples verified by field staff and retesting positive cases in WHO reference laboratories |  |
| IP Outcome 2 Measles cases reduced by more than 90% compared to 2004 |
| IP Output 2.1 Vaccinate more than 80% of infants in every district by measles vaccine through defaulter tracing and out reach activities | Indicator 2.1.1 % of infants vaccinated against measles vaccine in 2007 disaggregated by district | during 2007 only 76% of infants received measles vaccine | During 2007 more than 80 % of infants should receive measles vaccine | During 2007 only 69% of children received measles vaccine | 2007 witnessed severe deterioration of security that limited the access of children and women to immunization posts, not only that but also there were shortages in all vaccines all over the country due to problems of vaccine distribution. | WHO and UNICEF national staff reports and monthly reports received from MoH and provinces |  |
| IP Output 2.2 Support MoH to conduct one house to house measles campaign 3.9 million under 9-59 months old children in each round. 10,000 house to house immunization teams and 1500 MoH supervisors will plan, implement and monitor this activity | Indicator 2.2.1 % of children vaccinated against measles during the campaign | By the end of 2007 only 60% of children received measles vaccine | By the end of 2007 around 92% of targeted children received measles vaccine | By the end of 2007 only 92% of targeted children received measles vaccine | No variance | Routine MoH reports and results of testing stool samples verified by field staff and retesting positive cases in WHO reference laboratories |  |
| IP Outcome 3 Achieve routine infant coverage of 90% by all essential vaccine at the national level and at least 80%, in every district. |
| IP Output 3.2 Logistic support to out reach activities | Indicator 3.1.1 % of outreach vaccination teams provided with logistic support | 10% of outreach vaccination teams have logistic support | 70% of vaccination teams were provided with the needed logistic support By the end of 2007 | 40% of vaccination teams were provided with the needed logistic support By the end of 2007 | Deterioration of security in 2007 prevented out reach teams activities in many districts. |  |  |
| IP Output 4.1 National Measles Laboratory (NML) and National Polio Laboratory (NML) fully accredited and recognized as members of WHO network of accredited laboratories. |
| IP Output 4.1 WHO provide all needed equipment, chemical, kits and supplies and raise the capacity of the national staff to the needed international standards | Indicator 4.1.1 NML and NPL achieve >80% in the global annual measles and polio laboratories accreditation tests | Each laboratory must achieve 80% to be accredited | Both laboratories were fully accreted by WHO in the years 2006 and 2007 | Both laboratories were fully accreted by WHO in the years 2006 and 2007 | No variance | The accreditation is done through the sending unknown panel test to polio and measles laboratories all over the world and based on the concordance of the results of each lab with the results of the reference laboratory each lab is given a mark, to pass the proficiency test the lab must achieve 80% or more. |  |

# Text boxes

# FINAL NARRATIVE REPORT

- PURPOSE

- ASSESSMENT OF PROGRAMME/ PROJECT RESULTS

III. EVALUATION & LESSONS LEARNED

IV. INDICATOR BASED PERFORMANCE ASSESSMENT