Ninth Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: WFP |  | Old Cluster: A – Agriculture, Food Security, Environment and Natural Resource Management |
| --- | --- | --- |
|  |  | New Sector: Agriculture and Food Security |

| Project No. and Project Title: A6-03 Enhancing the Iraqi Institutions’ capacity in monitoring and targeting the most food insecure and vulnerable segments of Iraqi population. |  | Report Number: ATLAS Project Number: 66930 ATLAS Award Number: 54930 |
| --- | --- | --- |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 July – 31 December 2008 |  | USD $ 1,022,457 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Ministry of Planning and Development Cooperation (MoPDC) – COSIT & KRSO |  | Nationwide coverage, all 18 governorates. |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| Ministry of Planning and Development Cooperation (MoPDC) Central Organisation for Statistics and Information Technology (COSIT) Kurdistan Regional Statistics Office (KRSO) World Food Programme (WFP) National Development Strategy (NDS) Millennium Development Goal (MDG) Ministry of Health (MoH) Nutrition Research Institute (NRI) |  | Project Duration: December 12, 2007 – December 12, 2008 Programme/ Project Extensions - none This project was operationally closed during the reporting period, on December 12, 2008. |

# NARRATIVE REPORT FORMAT

# Purpose

a.	Provide the main objectives, outcomes, outputs of the programme/project

Development Goal

Strengthen the capacity of Iraqi institutions, namely the Central Organisation for Statistics (COSIT) in the Ministry of Planning and Development Cooperation, to carry out food security and vulnerability analysis and develop a monitoring tool which will, in turn, contribute to better targeted interventions concerning reconstruction, implementing social safety nets and development activities in Iraq, as well as to the reduction of food insecurity.

Immediate objectives

- Assist MOPDC/COSIT in improving their capacity in monitoring and targeting food insecure and most vulnerable segments of the population including the unemployed.

Outputs:

- A food security monitoring tool established and functioning which generates analyses and reports on a regular basis

- Enhanced capacity of the government in food security and nutrition monitoring and analysis and, subsequently, development of safety net strategies strengthened through the provision of training and equipment.

- Staff trained, capable and equipped to carry out Food Security and nutrition programming.

- Participation of all stakeholders regarding Food Security interventions maximized.

- Iraqi partners' ability to perform spatial and geographic analysis enhanced. Geographic dimensions of food insecurity, poverty and malnutrition better understood and analysed.

b.	Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq, MDGs, Iraq NDS and ICI

The National Development Strategy (NDS) is established on 4 major pillars, the third of which is "Improving the quality of life". This requires the enactment of "a social safety net program for the poor and vulnerable".

This WFP assistance to Iraq specifically addresses this requirement of the NDS through building the capacity of the Ministry of Planning and Development Cooperation and giving them the necessary tools to build its own food safety net programme.

This project also addresses the first Millennium Development Goal: “Eradicate extreme poverty and hunger”.  The safety net would target the most vulnerable residents for food assistance, eradicating hunger.

- Human Resources

a.	National Staff & Consultants: Provide the number and role (operation/programme)

93 national staff including 64 based inside Iraq (programme and logistics staff).  The 29 staff in Jordan and Syria are also comprised of programme and logistics staff as well as ICT, administration, finance, HR, security and drivers.

b.	International Staff: Provide the number and role (operation/programme)

14 international staff, including two senior advisors based in Baghdad and Erbil, plus 2 management, 1 finance/administration, 1 security, 3 logistics, 4 programme, 1 public information

- Methods of Operating

a.	Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

WFP implemented this project directly with the Ministry Planning and Development Cooperation’s (MoPDC) Central Organisation for Statistics and Information Technology (COSIT) and the equivalent in the north – the Kurdistan Regional Statistics Office (KRSO).

b.	Provide details on the procurement procedures utilized and explain variances in standard procedures.

All procurement followed WFP’s standard procurement procedures.

c.	Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

This project supports a Post-Food Distribution Monitoring system that tracks the impact of food assistance at the household level.  Monthly reports should be produced by each of Iraq’s 18 governorates giving up to date information on the food security situation at the governorate level.

d.	Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

The overall food security situation inside Iraq was assessed in the WFP/GoI Comprehensive Food Security and Vulnerability Analysis (supported under the ITF project D2-22).  The results of this survey showed that the food security situation had improved inside Iraq since the last survey was conducted in 2005, but that there are still pockets of food insecurity and vulnerability.  The full report can be accessed at:  http://documents.wfp.org/stellent/groups/public/documents/ena/wfp192521.pdf

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries. Please also fill the table in section VI on six monthly performance indicators assessment.

| 1.1 M&E system development | Post-Food Distribution Monitoring System developed. Associated databases designed | % of planned | 100% |
| --- | --- | --- | --- |
| 1.2 Mechanism established | M&E reports now received from all 18 governorates | % of planned | 100% |
| 2.1 Training of Trainers | 18 people from COSIT and KRSO, 20 WFP national staff, and 9 cooperating partner staff trained in the PFDM system | % of planned | 100% |
| 3.1 Training | Training of food security analysis and nutrition have been completed | % of planned | 100% |
| 4.1 Dialogue with stakeholders | Internal and external stakeholders consulted on targeting | % of planned | 100% |

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

The immediate objective of this project were achieved during the reporting period

- Assist MOPDC/COSIT in improving their capacity in monitoring and targeting food insecure and most vulnerable segments of the population including the unemployed.

The planned activities (detailed above) were completed during the reporting period, leading to the design and establishment of a Post-Food Distribution Monitoring system with regular inputs from all 18 governorates.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

This project moved quickly due to the high level of interest from GoI counterparts.  The principal constraint resulted from delays in the approval process of IRFFI funds.  The GoI expressed their commitment to this project in February 2007, but funds were only received in December 2007.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

This is the first time that WFP has worked with the Kurdistan Regional Statistics Office (KRSO) and bringing them together with their counterpart, the Central Organisation for Statistics and Information Technology (COSIT), who WFP has been working closely with since 2003.  In order for this nation wide M&E system to be successful, COSIT and KRSO need to work closely together and share information.  Establishing contact between these two bodies has been WFP’s principal goal during this project.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The database was designed to consider cross-cutting issues such as gender and employment status.  With this tool, the GoI partners will be able to assess levels of food insecurity disaggregated by gender and employment status.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2009 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

This project was operationally closed on December 12, 2008.  The future workplan comprises financial closure of the project.

- Six monthly Performance Indicators assessment

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| IP Outcome 1 - Assist MOPDC/COSIT in improving their capacity in monitoring and targeting food insecure and most vulnerable segments of the population including the unemployed. |
| IP Output 1.1 M&E system developed | Indicator 1.1.1 Post-Food Distribution Monitoring System developed. Associated databases designed | 0 | 100% | 100% |  |  |  |
| IP Output 1.2 Mechanism established | Indicator 1.2.1 Number of monthly reports received | 0 | 18 | 18 |  |  |  |
| IP Output 1.3 Training | Indicator 2.1.1 Training of trainers: 18 people from COSIT and KRSO, 20 WFP national staff, and 9 cooperating partner staff trained in the PFDM system | 0 | 47 | 47 |  |  |  |
|  | Indicator 2.1.2 Roll out training: Number of governorates receiving roll-out training | 0 | 18 | 18 |  |  |  |
| IP Output 2.2 Dialogue with stakeholders | Indicator 2.2.1 Internal and external stakeholders consulted on targeting | 0 | 100% | 100% |  |  |  |

# Text boxes

Report Formatting Instructions:

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Attach any available photos relevant to the project.