Ninth Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organisation: UNAMI/ UNEAD (technical) UNOPS (implementing agency) |  | Old Cluster: Governance |
| --- | --- | --- |
|  |  | New Sector: Governance Sector Outcome Team |

| Project No. and Project Title: G11-16 Support to Electoral Observer Groups in Iraq Phase III |  | Report Number: 2 Atlas Project Number 66969 Atlas Award Number 54969 |
| --- | --- | --- |

| Reporting Period: |  | Project Budget |
| --- | --- | --- |
| 1st July – 31st December 2008 |  | USD 6,243,599 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Participating UN Organizations UNAMI/UNEAD UNOPS Other International Organizations Friedrich-Ebert-Stiftung (FES) Amman Centre for Human Rights Studies (ACHRS) |  | Iraq, Baghdad and 18 Governorates - Jordan, Amman |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| List the main abbreviations and acronyms that are used in the report. ACHRS Amman Center for Human Rights Studies FES Friedrich-Ebert-Stiftung IECI Independent Electoral Commission of Iraq (former IHEC) IHEC Independent High Electoral Commission of Iraq UNAMI/IEAT United Nations Assistance Mission to Iraq/International Electoral Assistance Team |  | 12 months Starting Date 24 Jan 2008 |

# NARRATIVE REPORT FORMAT

# Purpose

# This project was developed to provide support to Iraqi national Election Observer networks through the training to 20,500 Electoral Observers and Media Monitors, in observation, reporting skills and media monitoring, and, at a later stage to facilitate the work of the observers during the next electoral event in Iraq.

# To guarantee impartiality and independence the project has been implemented through two Non-Governmental Organisations (NGOs): Friedrich-Ebert-Stiftung (FES) and Amman Centre for Human Rights Studies (ACHRS) which organised the training of 20,500 observers and media monitors and will facilitate their deployment during the upcoming Voter Registration.

Main Objectives:

# The project identified as immediate objectives:

- Support election observation networks through Training of Trainer (ToT) capacity building workshops on election observation and media monitoring in Amman and cascade training on these topics in Iraq.

# Facilitate the work of electoral and media observers during an actual electoral event through the provision of mobilisation allowances for elections observers and media monitors on next electoral events.

Outcomes

An enhanced implementation of electoral processes in Iraq in line with UNCT Goal 4 (Promote good governance and democratic processes, assist to uphold the rule of law and establish a human right regime) granted by independent monitoring of the processes.

Outputs

  - 80 personnel from Iraqi national observer groups will have received ToT at workshops in Amman on election observation and reporting skills.

  - 20 personnel from Iraqi Media Monitoring groups will have received ToT at a workshop in Amman.

  - 20,000 national electoral observers will have attended 800 training workshops on electoral observation and reporting skills delivered by those trainers who attended the courses in Amman.

  - 500 media monitors will have attended 20 workshops delivered by those trainers who received training on media monitoring during electoral processes.

  - 20,500 electoral observers and media monitors will have been mobilised and will have received an allowance to cover food, transportation and communication on Election Day.

Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq

For the Electoral processes in 2005, the UN assisted the Iraqi authorities and the IECI through a range of projects including the provision of Support to the Elections Process, Support to the Elections, Technical Assistance to IECI, Support for Fair, Safe and Professional Media Coverage and Logistics Support to the IECI. In addition two ‘Support to Observer Group’ projects were organised (Phase 1 and Phase 2) with the first one providing support to Observer groups for the January 2005 elections and the second for the referendum in October 2005 and the second legislative election in December 2005.

With the SCR 1770 the United Nations confirmed and reinforced their assistance to Iraq and their support to the government and to the IHEC. Alongside the direct measures that are currently being delivered to enhance the capacity of the IHEC, it is necessary to ensure that the upcoming electoral processes are perceived as transparent and legitimate both by the actual voters and the international community. Therefore it is essential to support national independent electoral observation networks enabling them to effectively monitor the forthcoming electoral processes planned for 2008/9.

- UN Millennium Development Goals

This project is not immediately related to the achievement of the MDGs, although it will partially contribute to MDG 8 “Develop a global partnership for development” where this includes a commitment to good governance as electoral observation is a key element in the creation of a stable and transparent political system in Iraq. In particular, where the project provides for interactions between international and local NGOs this will contribute in strengthening local capacities to international standards.

- Joint Needs Assessment

Before developing assistance projects to assist in the 2005 Electoral processes, UNAMI/IEAT developed a detailed and effective concept paper to establish and promote democratic electoral processes while simultaneously developing sustainable capacity to manage the electoral systems and processes.

Subsequently the outcomes of Electoral Observation Projects I and II have been reported on and evaluated in the relevant Lessons Learnt Exercises (for Phase I in New York and for Phase II in Cyprus). As a result the Tripartite Agreements between UNOPS, UNAMI/IEAT and the implementing partners were developed to include and reflect better inter-partner coordination and monitoring of in-country workshops and mobilisation.

- Iraqi National Development Strategy

Under the National Development Strategy, democracy was recognised as a cornerstone of good governance as it provides an enabling environment for Iraqi’s diverse people to interact in a participatory and transparent manner. The monitoring of electoral processes is key in ensuring transparency, adherence to international standards and respect of democratic rights.

Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

Under the funding arrangements between UNAMI, UNOPS and the UNDG/ITF, UNOPS acts as Executing Agency, whereas overall technical supervision is with UNAMI.

FES and ACHRS are the implementing partners to UNAMI and UNOPS under the provisions of individual Tripartite Agreements prepared by UNOPS.

The overall financial management of the project rests with UNOPS, the recipient of the funds from UNDG/ITF. UNOPS is responsible for financial monitoring of the activities (incl. those carried out by implementing partners).

- Human Resources

  - National Staff & Consultants: Provide the number and role (operation/programme)

1 part time Finance Assistant - Operation

1 part time Admin Assistant - Operation

  - International Staff: Provide the number and role (operation/programme)

1 part time Project Manager   -  Programme

- Methods of Operating

Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

FES and ACHRS developed the training programme and methodology for election observation and reporting skills and, in coordination with networks of Iraqi NGOs, they selected participants to ToT workshops to be conducted in Amman and subsequently organised outreach sessions in all Governorates of Iraq.

Once the training phase was completed, decision was made to deploy the observers during the Voter Registration Update (15 July - 15 August 2008). To ensure effective monitoring, FES and ACHRS, in coordination with the partner Iraqi NGOs, selected among them the Registration Centres to cover and the observers to deploy. The period was extended by one week to 22 August.

Final narrative and financial reports were prepared at the end of the monitoring exercise and the results shared with the IHEC.

UNAMI reviewed progress and final narrative reports, UNOPS reviewed progress and final financial reports and will prepare progress and final narrative and financial reports for UNDG/ITF and UNAMI.

Provide details on the procurement procedures utilized and explain variances in standard procedures.

The project did not entail any major procurement. The implementing partners took care of all organisational aspects (incl. selection of workshops premises, hiring of necessary equipment/materials, etc.). All expenses so far were accounted for with original receipts/invoices.

Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

UNAMI is responsible for monitoring the technical aspects of the project; therefore, the implementing partners shared and sought approval from UNAMI for the training programme and methodology, sought endorsement in the selection of the participants to the ToT workshops and in the selection of the observers and their geographical distribution.

In addition UNAMI has been monitoring the ToT workshops, will be following up on the observation and has been revising progress narrative reports and the final reports of the training phase.

UNOPS also monitored the ToT workshops and has been revising progress financial reports and the final reports of the training phase.

Furthermore FES and ACHRS have been monitoring the outreach sessions, receiving feedback from the participants to ensure quality and effectiveness of the trainings carried out by the people they have been preparing in Amman during the ToT workshops.

Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries. Please also fill the table in section VI on six monthly performance indicators assessment.

| 20,500 electoral observers and media monitors mobilised and received an allowance to cover food, transportation and communication during the electoral event. | 100% of planned Completed in 3rd quarter |
| --- | --- |

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

n/a

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

The project was not subjected to any significant delay.

However, the Voter Registration period was extended by the IHEC and this presented a potential challenge as funding was only available to mobilise Observers for the original designated period.  The observers and observer networks offered to volunteer for the additional hours of required observation.

There was no adjustment in strategy but it was recognised that the NGO partners offered enormous flexibility and support to provide the VRU process with legitimacy and independent observation.

Lesson learned from the observation of the VRU is intended to be used to develop a comprehensive monitoring plan for the forthcoming elections.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The project partners, UNAMI, UNOPS, FES, ACHRS, have been working closely together throughout the implementation phases to ensure coordination, maximise resources and impact. The implementing partners, in particular, have been providing continuous feedback and detail of their work which was a precious help to monitor the activities and ensure successful and timely achievement of the outputs.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Security

Electoral observation has as ultimate goal that of creating a transparent electoral framework, a factor which plays a relevant role in the country stability and security.

Gender

In Iraq, the participation of women in the public/political arena is limited. However the implementing partners have been trying to the extent possible to have a relevant representation of women in the trainings. ACHRS’ statistics on gender participation are not yet available at the time of reporting (the organisation started the activities after the other implementing partner), but FES’ reports show that 52% of the participants to the ToTs were female. As for the outreach sessions, FES coordinated them , but they were organised by their partner Iraqi NGOs, the turnout was less impressive, only an average of 10% of participants were female. Nevertheless it must be borne in mind the security concerns and the social restrictions faced by women when travelling inside the country and when participating to public events.

Final statistics on gender will be included in the next six-month progress report.

Human Rights

Electoral observation aims at improving the transparency and the efficiency of the electoral processes hence encouraging the population to take part in elections and exercise their political rights, which are integral part of human rights. Furthermore, it is envisaged that improved electoral processes will facilitate fair elections and prevent abuses and will therefore bring benefit especially to the less represented groups, such as marginalised parts of society, disadvantaged and vulnerable people.

Employment

The project does not have a direct impact on local employment. However by preparing trainers and then training 20,000 observers and 500 media monitors, the project provided with new technical skills a significant number of NGOs members, who will certainly benefit from the newly acquired abilities.

Environment

Not applicable

- Future Work Plan

  - Summarize the projected activities up to the end of June 2009 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

N/A

- Activities were completed in the fourth quarter of 2008 post final approval of narrative and financial reports.

- Six monthly Performance Indicators assessment

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Means of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| IP Outcome 1 |
| IP Output 1.1 n/a already completed | Indicator 1.1.1 |  |  |  |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| IP Output 1.2 n/a already completed | Indicator 1.2.1 |  |  |  |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| IP Outcome 2 Objective as per project document: Facilitate the work of electoral and media observers during an actual electoral event through the provision of mobilisation allowances for elections observers and media monitors on next electoral events. |
| IP Output 2.1 20,500 electoral observers and media monitors will mobilised and received an allowance to cover food, transportation and communication on Day of electoral event. | Indicator 2.1.1 n/a completed |  |  |  |  |  |
|  | Indicator 2.1.2 Disburse allowances to these observers | N/A | Disburse allowances to 20500 observers | Allowances disbursed to 20500 observers signatures | 20500 signatures, telephone numbers/ IHEC ID numbers – final report | 400 additional observers volunteered, making the total number of observers mobilized by the project 20900 |
|  | Indicator 2.1.3 Collect, compile and make available the electoral observers’ reports and the media monitors’ reports |  | Receipt of compiled final reports from NGOs | Receipt of compiled final reports from NGOs | Quality of reports cross checked and verified by UNOPS and UNAMI./NGOs internal audit |  |
|  | Indicator 2.1.4 Obtain feedback from the observers and users of this service as to its relevance and usefulness |  | Receipt of statistically significant feedback | Received feedback from both partners. | Physical receipt of feedback |  |

# Text boxes

Report Formatting Instructions:

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Attach any available photos relevant to the project.