Sixth Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNDP |  | Cluster (E), Infrastructure Rehabilitation (E3-04) |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| Project No.: E3-04 - 00046959 Project Title: Emergency Rehabilitation of Karama Water Treatment Plant – Line I |  | 3 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 |  | US$ 2,955,875 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| UNDP/Mayoralty of Baghdad/Baghdad Water Authority |  | Baghdad City |
| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| Mayoralty of Baghdad: MoB Baghdad Water Authority: BWA Pre-Qualification: P/Q Request for Proposal: RfP Expression of Interest: EoI Director General: DG Video Conferencing: VC |  | 14 months |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Key Immediate Objectives:

- Increase production of Karama Water Treatment Plant in Baghdad by 10MGD.

- Increase reliability and long term operation of Karama water treatment plant.

- Water Quality monitoring and testing laboratory of the plant capable of conducting daily, weekly and monthly tests according to international testing standard procedures.

Outputs:

- Production increased by additional 10 MGD of potable water- enough to reach the 1,000,000 or so residents on the Karkh side of Baghdad, specifically Kadhimiya area and a few quarters in Rasafa.

- The reliability and long-term operation of the whole of Karama water treatment plant is improved by 40%.

- The staff of MoB, BWA and Karama WTP has the capacity to manage the potable water system.

- A functioning Water laboratory.

- Staff trained in water testing techniques

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The project is designed to contribute to the following objective:

National Longer-Term Priority or Goals:

To reduce the percentage of people without access to safe drinking water and sanitation by 50% by 2015 (MDG/ICSD) and to contribute significantly to reaching the infant mortality rate and nutrition MDG.

High-Level/Cluster Outcome by the End of 2007:

Decentralised management with strong public private partnerships and community involvement (particularly women) achieving water and sanitation service approaching 1980s levels (urban 350 lcd, rural 250 lcd)

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

UNDP’s implementing partners are the MoB and the BWA. All project related arrangements including preparation of P/Q documents and RfP for consultants, appointment of the consultant and contractor…etc is and shall be carried out in close collaboration with the counterparts. The counterparts will play an active role during all project development phases from initial conceptualisation through final handing over.

UNDP procured the required consultancy services through its procurement unit through a competitive bidding process. A call for EoI has been advertised on the UNDP website and all known local consultants, to UNDP’s procurement unit, were advised. Following short-listing of consulting firms; an RfP was sent to successful consultants and following a lengthy process a national consulting firm has been appointed.

The appointed consultant is preparing all technical material and documents necessary for inclusion within the bidding documents. UNDP will carry out all foreseen works procurement activities through a competitive bidding process in close collaboration with the counterparts.

All technical materials (scopes of work, drawings, Bills of Quantities…etc.) will be reviewed by the counterparts. In addition, certificates of completion will be issued only upon agreement of the counterparts via official written letters of acceptance.

The consultant shall furthermore supervise and monitor all construction activities and report on a weekly and monthly basis to UNDP. The counterparts shall furthermore play an active role during construction activities by assisting the consultant as deemed necessary.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

- Total Approved Budget: US$ 2,955,875

- UNDG ITF Funds Received: US$ 2,955,875

- Other Resources Available to the Project: None

- Amount Disbursed Until End of Reporting Period (i.e. Dec. 2006): US$ 67,700.00

- Amount Committed Until End of Reporting Period (i.e. Dec. 2006): US$ 412,389.38

- Incremental Amount Disbursed to Date (i.e. April 2007): US$ 250,000

- Incremental Amount Committed to Date (i.e. April 2007): US$ 49,715.00

- Incremental Projected Disbursements by 30 June 2007: US$ 168,915

- Incremental Projected Commitments by 30 June 2007: US$ 2,543,485

- Amount Available to the Project Until the End of Reporting Period: US$ 2,543,485

Planned Areas of Expenditures Until End of Reporting Period: Personnel, Travel, Miscellaneous, Security and Agency Management

(See also separate detailed financial report.)

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

N/A

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

Budget Lines Utilization: All funds under the various budget lines have been committed except for those under the Contracts, Training and Equipment budget lines.

See separate expenditure report.

  - Indicate other funding sources, if applicable.

N/A

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

N/A

  - Project expenditures for the 1 July to 31 December 2007 period.

N/A

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

No National Staff

  - International Staff: Provide details on the number and type (operation/programme)

1 International Project Manager

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

Due to the prevailing security situation and restrictions placed on the movement of UN staff over the majority of Iraq, local contractors, team of engineers and architects were chosen to implement the project.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Procurement is made through competitive process by the experienced UNDP -Iraq procurement office, which demonstrated performance over the last few years and is a major asset on which this project has already built and from which it benefited. In case too few competitors respond or are eligible for the task at hand, waiver may be sought to contract without competitive bidding.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

The implementation is ongoing and works are monitored regularly. This ensures that the sub-contractors for various technical works comply with the scope, work plan and Bill of Quantities as contracted.

In addition, UNDP’s technical team are fully engaged in advising and guiding the contractors throughout the implementation phase. The implementing agents are paid by UNDP in arrears based on predetermined milestones, which are independently verified by UNDP’s Consultant upon receipt of payment request invoices from the contractor. Payments are subject to the progress of works and the submission of all supporting documentation by the contractor and independent consultants including monthly progress reports, before, during and after with photographs of the works and on-site cameras, etc.

  - Report on any assessments, evaluations or studies undertaken.

The Phase I deliverables reflected the full extent and magnitude of shortages of the entire treatment plant (i.e. Lines I, II and III) and established most of the necessary documentation for the plant, which was not available.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

Until the End of Reporting Period (i.e. June 2007):

- Completion of Phase I of the consultancy services, namely assessment of the Karama Water Treatment Plant, Line I rehabilitation requirements.

While UNDP’s scope of work was limited to rehabilitation of Line I of the treatment facility and having realized the deteriorated condition of Lines II and III and larger impact both lines bring to the population of Baghdad city and based on BWA’s request, UNDP decided to include rehabilitation of portions of both Lines II and III within the scope of the project. This additional scope has undergone full assessment and design and shall be accommodated within the implementation scope of work should available budgets allow.

While procuring the services of the project, National consultant has fully assessed all plant elements and thus prepared a comprehensive diagnosis for the entire plant. Furthermore, the project designs, drawings, technical specifications, bills of quantities…etc have been prepared for the entire plant components requiring rehabilitation and not just for the current project scope. These shall be readily available to the counterparts to fully inform them of current plant related problems and bottlenecks, help in seeking additional funding, help in scheduling downstream interventions…etc.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

The end of design works is a major step in  the rehabilitation

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Until the End of Reporting Period (i.e. June 2007):

- Issue of Expressions of Interest calling for contractors to express their interest in participating in the works bid.

- Completion of the consultancy assignment and delivery of all project assessments, designs, drawings, bills of quantities, scope of work…etc for Lines I, II and III of the treatment plant.

- Verification of all project cost estimates by an independent international quantity surveyor.

- Evaluation of the received contractors’ Expressions of Interest and establishment of project pool of pre-qualified contractors.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

Reasons for Delayed Delivery:

- Security situation impact on: conducting meetings with counterparts, carrying out site visits and verification activities, reluctance of consultants to engage under current situation.

- Continuous change of BWA DGs (three times in less than 5 months): impacts include having to re-launch familiarization of DG with the project, objectives, activities…etc, loss of communications during the change periods, loss of interest by DGs aware of near post holder changes…etc.

- Increasing UNDP’s scope of work to include rehabilitation of portions of Lines II and III of the treatment plant.

Implementation Constraints:

Security situation and frequent change of counterparts’ senior staff.

Lessons Learned from Addressing Implementation Constraints:

Relying on teleconferencing, VC…etc for communications. Maintaining close relations with counterparts to be on top of issues as they emerge. Maintaining close contacts with local business associates to forecast and predict forthcoming events and changes. Maintain a consistent and continuous reporting system to counterparts to avoid loss of formal communications.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

Key Partnerships: Mayoralty of Baghdad (MoB) and the Baghdad Water Authority (BWA)

Inter-Agency Collaboration:

UNDP works in close collaboration with WHO, UNICEF and UNESCO

Impact on Results: Comprehensive identification of the required laboratory equipment, Optimal determination of the most suitable training programmes and venues.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The project is not designed to create employment opportunities under the labour intensive implementation modality. However, project implementation will result in:

- Creating and sustaining numerous employment opportunities for the National Consultant

- Creating and sustaining numerous employment opportunities for the National Contractor

- Indirectly creating and sustaining numerous employment opportunities for all project related sub-contractors, suppliers, vendors…etc

- Capacity building of the BWA staff will result in Enhancing the Employment Terms, Conditions and Future Opportunities

- Future Work Plan

  - Summarize the projected activities up to the end of December 2007.

Outcomes Expected Within the Six Month Reporting Period:

Award of the works contract and completion of some 10% of project works.

Partial completion of the implementation.