Sixth Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| United Nations Development Programmes |  | E - Infrastructure Rehabilitation (E3-06) |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| Project No.: E3-06 - 00048847 Project Title: Emergency Water, Sanitation and Health Support for Southern Iraq. |  | 5 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 |  | US$ 4,919,519 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| UNDP/Ministry of Municipalities and Public Works, Basrah Governorate, Town Councils of Umm Qasr, Safwan, Shouaiba, Khor Zubair Abu Al Khaseeb and Zubair |  | Basrah Governorate, Towns of Umm Qasr, Safwan, Shouaiba, Khor Zubair, Abu Al Khaseeb and Zubair |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| Ministry of Municipalities and Public Works: MMPW Basrah Governorate: BG Town Council: TC Pre-Qualification: P/Q Request for Proposal: RfP Invitation to Bid: ITB Video Conferencing: VC |  | 6 months |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Key Immediate Objectives:

In Um Qasr, Safwan, Khor Al-Zubair, Shuaiba, Zubair and surrounding areas:

- Water infrastructure will supply adequate potable and raw water.

- Public Health risks from poorly maintained sewage system, strewn garbage, organic waste build up and disease vectors proliferation will be reduced.

- Public awareness of water, sanitation and public health issues will increase.

- Temporary emergency employment will be provided to unskilled and semi skilled vulnerable and unemployed people, including women. An institutional structure capable of sustaining and running the “water and sanitation units” within the communities targeted will be prepared.

- Establish long-term water and sanitation assessment for Safwan and neighbouring localities.

Outputs:

- 1,000 and 1,500 cubic metres per day of treated and raw water respectively will be available for the inhabitants of Um-Qasr and Safwan.

- A management structure established, capable of delivering potable water and disposing of waste water safely.

- Sludge build- up and blocked lines reduced/eradicated.

- Removal of 200 tons per day of garbage from the concerned municipal areas to safe dumping grounds.

- Reduced disease vectors.

- People (60%) will understand and be aware of the importance of, and be able to implement strategies to minimise their risks to, public health hazards.

- 3031 jobs will be created for a total of 260,210 man-days through the IREP program, in addition to the jobs created through the activities of the local contractors/consultants.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

National Longer-Term Priority or Goals:

To reduce the percentage of people without access to safe drinking water and sanitation by 50% by 2015 (MDG/ICSD) and to contribute significantly to reaching the infant mortality rate and nutrition MDG.

High-Level/Cluster Outcome by the End of 2007:

Decentralised management with strong public private partnerships and community involvement (particularly women) achieving water and sanitation service approaching 1980s levels (urban 350 lcd, rural 250 lcd)

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

UNDP’s implementing partners are MMPW, BG and relevant TC’s. All project related matters such as needs assessments, modification of scope, definition of other contributors, identification of bottlenecks, etc., are carried out in close collaboration with the counterparts. The counterparts will play an active role during all project cycle phases from initial conceptualisation through final handing over.

UNDP has procured all required services, contracts, equipment, etc., through its procurement unit through a competitive bidding process. Procurement of consultancy services was carried out through issuance of an RfP for local consultants. Procurement of equipment has been carried out through issuance of ITB’s. All procurement activities have been advertised on UNDP website and local newspapers coupled with UNDP advice to the known providers. Procurement of all project equipment was based on UNDP in-house developed designs, specifications and documentation due to the tight project delivery period.

All technical materials (scopes of work, drawings, Bills of Quantities, etc.,) for the works have been reviewed and approved by the counterparts. In addition, certificates of completion are issued only upon agreement of the counterparts via official written letters of acceptance. UNDP decided to engage with the counterparts in a Letter of Agreement modality to implement part of the works associated with the RO plants for the purpose of building the capacity of counterparts in issues related to procurement, technical and financial evaluation, project management, operation and maintenance, etc.

In addition to preparation of all required designs, drawings, specifications and bills of quantities for the works, the project consultant is supervising and monitoring all construction activities and reports on a weekly and monthly basis to UNDP.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

See separate detailed financial report

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

N/A

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

See separate detailed financial repor

  - Indicate other funding sources, if applicable.

N/A

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

The scope of rehabilitation has been broken-down into phases to be addressed separately as submitted to Steering committee.

  - Project expenditures for the 1 July to 31 December 2007 period.

N/A

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

None at this stage

  - International Staff: Provide details on the number and type (operation/programme)

One (1)

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

Due to the prevailing security situation and restrictions placed on the movement of UN staff over the majority of Iraq, in addition to the unique security conditions in Basrah City local contractors and team of engineers and architects were chosen to implement the project.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Procurement is made through competitive process by the experienced UNDP -Iraq procurement office which demonstrated performance over the last few years is a major asset on which this project has already built on and from which it benefited. In case too few competitors respond or are eligible for the task at hand, waiver is sought to contract directly.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

The implementation is ongoing and works are monitored regularly. This ensures that the sub-contractors for various technical works (electrical, plumbing, carpentry, masonry, etc, comply with the Bill of Quantities of the projects.

In addition, UNDP’s technical team are fully engaged in advising and guiding the contractors throughout the implementation phase. The implementing agents are paid by UNDP in arrears based on predetermined milestones, which are independently verified by UNDP’s Consultant upon receipt of payment request invoices from the contractor. Payments are subject to the progress of works and the submission of all supporting documentation by the contractor including monthly progress reports, before, during and after photographs of the works, etc.

  - Report on any assessments, evaluations or studies undertaken.

Fully-Fledged water and sanitation assessments for the towns of Umm Qasr, Safwan, Shouaiba and Khor Zubair, including recommendations for future interventions and environmental impact assessments.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

Until the End of Reporting Period (i.e. June 2007):

- Employment opportunities were provided for 1,646 labourers resulting in creation of 48,690 workdays of employment.

-  Seven (7) sub projects to install water distribution networks in Khor Zubair and Shuaiba towns were initiated.

- Short-, medium- and long-term situation analysis and assessment for the water and sanitation situation in the project area completed.

-  Increased access to safe potable water achieved.

- Adequately equipped warehouses with sufficient spare parts and consumables for 2 years of operation established for Khor Zubair and Safwan respectively.

- Sustainable water and sanitation service level addressed through provision of spare parts, consumables, adequate water storage facilities…etc.

-  Removal of 400 cubic metres per day of garbage from the concerned municipalities areas to safe dumping grounds.

-  Removal of 200 cubic metres per day of sewage from the concerned municipalities.

Variance

The entire project has undergone redesign for the following reasons:

- Fulfil MMPW’s request for concentrated project focus on supply of physical infrastructure assets.

- Meeting changed requests by TCs due to recent interventions by other international contributors.

- Meet community needs based on an in-depth socio-economic study carried for the project area.

Accordingly, the project was redesigned to include the following:

- Drilling of 2 groundwater wells producing some 5,400 cubic metres per day (cum/d) of raw water, which were not part of the original scope,

- Supply of 2 RO plants producing 3,600 cum/d of potable water as opposed to 2,500 cum/d in the original scope, The RO process has been designed to achieve superior treated water quality, higher than WHO standards, which was never available to these towns before,

- Supply of spare parts and consumables for the RO plants adequate for sustaining the provided assets for a minimum period of two years, which were not part of the original scope,

- Supply and construction 2 elevated water storage tanks accommodating 1,000 cubic meters of water, which were not part of the original scope,

- Supply, installation, construction…etc of all RO plant sites associated works including civil works, electrical supply, stand-by power generation…etc, which were not part of the original scope, in addition to the possibility of supplying electrical power supply to nearby residential areas,

- Supply of 4 water tankers as opposed to 2 tankers in the original scope,

- Supply and construction of 63 water distribution points complete as opposed to 42 distribution points in the original scope,

- Supply of 6 water tankers as opposed to 4 tankers in the original scope,

- Connection of several residential areas in the towns of Shouaiba and Khor Al-Zubair to the municipal water distribution networks, which was not part of the original scope.

In the design of the RO plants, all lessons learned through background projects in Umm Qasr town and others have been incorporated, where process engineering was completely revised to meet the mandatory WHO potable water quality standards and ensure high impact of UNDP’s interventions.

Following the redesign of the project, the geographic coverage of the project was also enlarged to cover the towns of Umm Qasr, Khor Al-Zubair, Safwan, Shouaiba and Al-Zubair serving a total population of some 680,000 capita as opposed to 200,000 capita of the original scope. Furthermore, and with the purpose of meeting the urgent water supply requirements, the IREP contribution to the project was rerouted to cater for connecting several districts within the towns of Khor Al-Zubair and Shouaiba to the water distribution networks, all design changes that ensure an increased number of beneficiaries among some of the most vulnerable communities in the South.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Activities and Impact

Until the End of Reporting Period (i.e. June 2007):

- Completion of the consultancy assignment.

- Delivery of all project equipment (i.e. RO plants, spare parts, consumables, water tankers, sewage tankers, solid waste containers, solid wastes skip loaders, water storage tanks, stand-by power generation sets, transformers, etc.)

- Completion of water distribution points construction.

- Connection of several residential areas in the towns of Shouaiba and Khor Al-Zubair to the municipal water distribution networks, which was not part of the original scope.

- Progress of 75% and 60% on the construction of Khor Zubair and Safwan RO plants respectively.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

Reasons for Delayed Delivery:

- Delayed delivery of the funds: funds were transferred to UNDP as of mid December 2005.

- Security situation impact on: conducting meetings with counterparts, carrying out site visits and verification activities, reluctance of consultants to engage under current situation.

- Changes in project design introduced by MMPW resulted in the need for procuring non-manufacturer standard, shelved items such as RO plants, which require a total manufacture period of 4 months.

Planned Areas of Expenditures Until End of Reporting Period: Personnel, Travel, Miscellaneous, Contracts, Security and Agency Management

Implementation Constraints: Security situation.

Lessons Learned from Addressing Implementation Constraints: Relying on teleconferencing, VC, etc., for communications. Relying more on national consultants for carrying out activities normally carried out by UNDP.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

Key Partnerships: City councils targeted by the project activities and MMPW

Inter-Agency Collaboration: Cluster E collaboration during the project design and review.

As a consequence of the restrictions placed on the movement of UN staff in Iraq, UNDP Iraq sought other ways to overcome the situation on the ground in order to reach the target populations of its interventions. Hence, a strong partnership was developed with line ministries and station management. This arrangement allowed UNDP to assess the local institutions capacities for project implementation as well as to support its counterparts in identifying their major priorities.

These de-facto partnership with beneficiaries and contractors are a flexible and efficient operational modality in Iraq’s difficult conflict environment.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

- Created employment opportunities: 48,690 workdays

- Direct Beneficiaries: 1,646 labourers

Moreover, project implementation will indirectly result in:

- Creating and sustaining employment opportunities for the appointed National Consultant

- Creating and sustaining employment opportunities for National Contractors

- Creating and sustaining employment opportunities for relevant TC’s

- Capacity building of the BWA staff will result in Improving the Employment Terms, Conditions and Future Opportunities

- Future Work Plan

  - Summarize the projected activities up to the end of June 2007.

Projected by 30 Dec 2007:

-Completing the installation, construction, etc., of all RO plant sites associated works including civil works, electrical supply, stand-by power generation, etc.

As a result:

- 2,400 and 1,200 cubic metres per day of raw water will be available for the inhabitants of Khor Zubair and Safwan respectively.

-  2,400 and 1,200 cubic metres per day of safe reverse osmosis (RO) desalinated potable water will be available for the inhabitants of Khor Zubair and Safwan respectively.

-  A management structure capable of delivering potable water developed.

-  Contribution to public health risks reduction achieved

-  Contribution to socio-economic development achieved