SIXTH Six-monthly progress report for project

“Rehabilitation of unit 1 of mussaib TPS – Stage 1”

# REPORT COVER PAGE

| Participating UN Organisation: |  | Cluster: |
| --- | --- | --- |
| United Nations Development Programme |  | E – Infrastructure Rehabilitation |

| Project No. and Project Title: |  | Project Location/Region/Province: |
| --- | --- | --- |
| Project No. E4-10 - 41699 Rehabilitation of Unit 1 of Mussaib TPS – Stage I |  | Mussaib District, Babylon Governorate, Iraq |

| Reporting Period: |  | Report no: |
| --- | --- | --- |
| 1 January 2007 to 30 June 2007. |  | 6 for this project 6 for IRFFI projects |

| Counterpart organisations / implementing partners: |  | Project cost: |
| --- | --- | --- |
| Client Counterparts: Ministry of Electricity (MoE), Baghdad; General Directorate for Electricity Production (GDEP) – Euphrates Region, Hilla; Mussaib Generating Station Implementing Partners: Hitachi Ltd. (Japan), Babckok-Hitachi KK (Japan), Hyundai Engineering & Construction Co. (Korea). |  | $15,510,982 |

| Abbreviations and acronyms: |  | Project Duration: |
| --- | --- | --- |
|  |  | 25 months (22 Nov. 2004 – Dec. 2006 |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Development Goal

Ensure the supply of reliable and safe electricity to Central Iraq to permit operation of essential humanitarian services.

Immediate Objectives:

1. The generating capacity, availability, reliability and efficiency of Musayab Thermal Power Station (Unit No.1) increased.

2. Parts, materials and components, dedicated to future maintenance and repairs, received or targeted for Stage II procurement.

3. Plant operations and maintenance management and staff able to conduct condition assessment of thermal power generating units, and to maintain MoE thermal units in accordance with international standards.

Output 1: Unit 1 of Musayab Thermal Power Station demonstrating increased generating capacity and reliability.

Output 2: Comprehensive set of selected and essential spare parts supplied to Musayab TPS, which will be available in stock for emergency repairs and routine maintenance – in order to maintain Unit 1 future generation reliability.

Output 3: Core Team of plant staff proficient in thermal unit condition assessments and able, in turn, to train other junior technical personnel (engineers and technicians) to enlarge MoE in-house capabilities to conduct unit condition assessment.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment,

- Iraqi National Development Strategy

The project is in line with the UNDP Needs Assessment Report of October 2003.

The project is within the list of 727 projects presented by Iraqi Authorities in Abu Dhabi.

Project Stages I & II approved by Iraq’s Ministry of Electricity on 22 Nov. ’04.

Improvement of the electricity situation in Central Iraq and increased reliability of Mussaib Station is part of the UN Strategy for Assistance to Iraq in 2004/05.

Project addresses the Millennium Development Goals.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

International: Hitachi Ltd, Japan (main contractor to UNDP and supplier of I&C equipment), Babcock-Hitachi KK, Japan (supplier of boiler equipment), Hyundai Egg. & Construction Co, Korea (procurement of equipment for Balance of Plant & Common Facilities).

National (Iraqi): MoE Unit 1 Assessment Team (preparation of boiler for inspection and assessment tasks addressing all of Unit 1 as well as overall plant equipment affecting Unit 1), Al-Rook Co. (boiler inspection and condition assessment). Both are contractors to Hitachi Ltd.

Satellite-based Telecom Systems Design/Supplier: Mitsa Co., Cyprus (supplier of telecom systems for videoconferencing and equipment examination via mobile camera to observe plant equipment from outside Iraq during its assessment / rehabilitation and to communicate with Mussaib Station).

Adaptation to Local Security Conditions in Iraq: Use of an Audio/Video/Telecom (AVT) satellite-linked system to communicate live with Mussaib Station staff and observe condition of equipment. The AVT system together with training of Iraqi specialists and periodic meetings in Amman & Cyprus is designed to eliminate the need of having international staff inside Iraq.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

See separate detailed financial report

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

N/A

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

See separate expenditure report

  - Indicate other funding sources, if applicable.

N/A

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

N/A

  - Project expenditures for the 1 July to 31 December 2007 period.

N/A

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

1 Project Officer (part-time)

  - International Staff: Provide details on the number and type (operation/programme)

1 Project Manager (part-time)

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

Due to the prevailing security situation and restrictions placed on the movement of UN staff over the majority of Iraq, local contractors, team of engineers and architects were chosen to implement the project.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Procurement is made through competitive process by the experienced UNDP -Iraq procurement office, which demonstrated performance over the last few years and is a major asset on which this project has already built and from which it benefited. In case too few competitors respond or are eligible for the task at hand, waiver may be sought to contract without competitive bidding.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

The implementation is ongoing and works are monitored regularly. This ensures that the sub-contractors for various technical works comply with the scope, work plan and Bill of Quantities as contracted.

In addition, UNDP’s technical team are fully engaged in advising and guiding the contractors throughout the implementation phase. The implementing agents are paid by UNDP in arrears based on predetermined milestones, which are independently verified by UNDP’s Consultant upon receipt of payment request invoices from the contractor. Payments are subject to the progress of works and the submission of all supporting documentation by the contractor and independent consultants including monthly progress reports, before, during and after with photographs of the works and on-site cameras, etc.

  - Report on any assessments, evaluations or studies undertaken.

-- Unit 1 overall assessment results were reviewed with MoE, Hitachi/Hyundai in Amman on 25-29 Sept. ‘05. The comprehensive technical data (gathered at the Station via data collection forms or observation sheets as brief field data/reports) plus equipment pictures obtained during the Cold Assessment -- all e-mailed to the contractor, were reviewed by Hitachi/Hyundai, MoE and UNDP specialists. An Interim Assessment Report was generated on this basis.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

Project Outcomes: The project milestones set for 2005 (training of Iraqi specialists, fielding of communications system, assessment of Unit 1, first delivery of plant equipment to Mussaib Station) were met.

Plant equipment delivery milestones for 2006/07 (4 shipments in excess of 82 tons) were met.

Thorough assessment of Unit 1 during a maintenance shutdown and while in operation to identify equipment requiring rehabilitation or replacement (to be implemented in Stage II of the project) completed.

Capacity development: High impact (21 Iraqi specialists were trained in thermal unit assessment in Japan & Korea; 3 Iraqi staff were trained on AVT system assembly and operation)

Inventory control is yet another area in which the Iraq engineers / persons working in Stores and operation are being exposed to latest techniques of inventory control by practicing the area as guided by UNDP for the material so far arrived.

Policy dialog: High-impact continuous dialogue on project issues with senior management at MoE, GDEP and Mussaib Station during Stage I project planning and unit assessment was achieved.

Employment creation: Temporary impact during unit assessment activities (3 from Al-Rook and 50 -200 personnel from Mussaib Station over a period of 2-4 weeks).

Basic service delivery: Improved electricity delivery expected at the completion of the rehabilitation works and in particular during the 2008 peak electricity demand season (Summer) in Iraq.

-- A contract between UNDP and Hitachi was executed on 11 May ’05 for the provision of goods and services under Stage I. The contract encompasses the supply of equipment (in particular long-lead pressure parts components for the boiler and delivery of equipment to the site. The services component of the contract includes training of MoE staff, monitoring of the Unit 1 assessment work by Hitachi/Hyundai specialists temporarily based in Amman, plus non destructive examination of plant components and other site services.

-- A group of 21 staff from MoE received 3-week training in Japan and Korea on unit condition assessment, improved maintenance practices and enhanced thermal unit operation. The training was conducted at Hitachi Kure Works (topics related to mechanical systems of steam units), Hitachi Omika Works (topics related electronic components of Instrumentation & Controls of steam units), Korea Power Learning Institute (Simulator training on boiler start-up, turbine engagement, synchronizing to grid, etc). In addition, they visited the Pyungtaek TPS (Korean Station similar to Mussaib) and received training on water treatment, T/G maintenance and Non-destructive evaluation testing.

-- A team of three staff from MoE attended training in Amman on the satellite-linked audio/video/teleconferencing system (AVT system) deployed at the Station for monitoring the assessment and rehabilitation works. The training was provided by MITSA International, the supplier of the AVT system.

-- Project kick-off and team organizational meetings were held in Amman with participation by Mussaib Power Station, GDEP/Euphrates, MoE/Baghdad, Hitachi, Hyundai, Al-Rook and UNDP. The project Stage I schedule, tasks and plans for deployment or resources were reviewed in detail. Initial plans for the project Stage II were also discussed.

-- Cold assessment of Unit 1 (examination of equipment with unit on outage) started on 15 August ‘05 as a result of Unit 1 unexpected outage (due to turbine malfunction) and lasted two weeks. MoE stated that some 200 MoE staff and Iraqi contractors were involved in work at assessment peak time. Hot assessment of Unit 1 (calibration of operational data while unit is operating) was conducted on 14 September ‘05. The outstanding cold assessment tasks (remaining from the cold assessment period) were completed with the unit back in operation. The comprehensive Cold and Hot Assessment tasks amount to the first detailed assessment of Unit 1 condition since its construction in 1987.

-- Unit 1 overall assessment results were reviewed with MoE, Hitachi/Hyundai in Amman on 25-29 Sept. ‘05. The comprehensive technical data (gathered at the Station via data collection forms or observation sheets as brief field data/reports) plus equipment pictures obtained during the Cold Assessment -- all e-mailed to the contractor, were reviewed by Hitachi/Hyundai, MoE and UNDP specialists. An Interim Assessment Report was generated on this basis.

-- The Unit 1 assessment data obtained in August ’05 and reviewed at the September ’05 meeting  included a large amount of data and constitutes a unique technical database for Unit 1: Boiler (over 130 field inspection data sheets & 366 pictures) , Instrumentation & Controls (9 field data sheets),  Balance of Plant ( 92 reports on major equipment & 71 pictures), Electrical System (14 field data sheets & 18 pictures), and Common Facilities (195 reports on equipment/systems & 71 pictures).

-- A Japanese agent (OMIC PMD JP) was contracted on 20 October ‘05 to conduct Pre-Shipment Inspection of power plant equipment being shipped by Hitachi to MoE under the UNDP project. Pre-Shipment Inspection of equipment being sent by Hitachi as Lots # 1 and 3 took place at Kure and Omika Works and Kobe Port (Japan) on October/November ’05 and January ’06. Shipment #1 comprising some 7 containers plus 3 boxes arrived at Mussaib Station 28 Dec ’05.

-- The combined shipment #2 & #3 reached Al-Mussaib Station on 15 March. The convoy had suffered an attack shortly after the Iraqi border. Although one vehicle was damaged and had to be replaced, there was no damage to the shipment. Payment on receipt of shipping documents was released as per contract.

-- Meetings were held in Amman in February ’06 with MoE management to review the Unit 1 assessment results in light of current Mussaib Station and Unit 1 priorities plus MoE plans to independently procure funds for a comprehensive rehabilitation of the remaining units at Mussaib Station. This review permitted coordination between MoE and UNDP of all activities related to Unit 1 and the rest of the Station, as well as to confirm the priorities for Stage II of the subject Mussaib Unit 1 Emergency Rehabilitation Project.

-- Four MoE engineers underwent training in Nicosia, Cyprus on how to utilize VSAT and Video conferencing equipment and in Computer network security.

-- Detailed inspection of the equipment of lot 1, 2 and 3 is in progress at Mussaib as per guide lines provided by UNDP.

-- Testing of new VSAT equipment was completed.

-- VSAT equipment was transported to Mussaib and Hilla.

-- Investigation of some damaged temperature gauges received at Mussaib is in process.

- Equipment included in lot 4 arrived at Kuwait and was transported from Kuwait to Iraq by road. The equipment was escorted by private security guards.

- Payment has been released for lot 4 equipment as per contract.

- Payment was released to OMIC, having completed the inspection of equipment in Japan,.

- Station staff completed the inventory as per format provided by UNDP.

UNDP consented to use the spare parts to the station staff and sent the consumption report at regular intervals.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

The final financial obligations are being liquidated with the view of project closure, attaining all outcomes.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

During the reporting period, the inventory has been completed as per required format of UNDP and the station manager started using the available spare parts for routine and breakdown maintenance. He has further been updating inventory as per laid down procedure regularly after using spare parts.

All substantial activities have been completed, and the final financial obligations are being liquidated with the view of project closure. The final report is being compiled.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

Constraints:

(1) Difficulties in getting access to the unit for cold assessment (i.e. condition assessment while the unit is not operating). This was due to the shifting of target dates for access to the unit because of the need to operate the unit whenever possible. Mussaib Unit 1 (currently operating at 200-220 MW) represents roughly 4.5 % of the estimated available capacity in Iraq of 4500 MW). This resulted in having to adopt a more flexible approach in our planning and implementation of the project.

(2) Difficulties in implementing inspection of Shipment # 1 at the Station for MoE issuance of an Acceptance Report. This resulted in the UNDP plan to use the AVT mobile camera for future inspection (jointly with MoE staff) of shipments that have arrived at the Station.

(3) Difficulties in entering shipments into Iraq because of security conditions.

Lessons Learned:

Improve availability of spare parts to be used during equipment assessment.

Explore other routes of transport which could be more safe, keeping in mind the past experience.

Although the equipment of lot 4 has to be stored in Kuwait for about one month, as security clearance on route to Mussaib was not accorded by the survey team of the forwarder, the equipment finally arrived at the destination safely.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

As a consequence of the restrictions placed on the movement of UN staff in Iraq, UNDP Iraq sought other ways to overcome the situation on the ground in order to reach the target populations of its interventions. Hence, a strong partnership was developed with local authorities, religious and community leaders. This arrangement allowed UNDP to assess the local institutions’ capacities for project implementation as well as to support its counterparts in identifying their major priorities.

These de-facto partnership with beneficiaries and contractors are flexible and efficient operational modalities in Iraq’s difficult conflict environment.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Temporary Employment creation: impact during unit assessment activities (3 from Al-Rook and 50 -200 personnel from Mussaib Station over a period of 2-4 weeks).

Employment creation will result from the increase in electricity supply to users in Iraq.

(Mussaib Unit 1 currently represents about 4.5% of the available electricity generating capacity in Iraq. Rehabilitation of the unit will add about 60 to 80 MW of generating capacity at the station.)

- Future Work Plan

  - Summarize the projected activities up to the end of December 2007.

- Station will continue to use the spare parts for routine and breakdown maintenance. The consumption is monitored and communicated to UNDP.

- Utilize the unit assessment information obtained in Stage I for decisions on equipment priorities for Unit 1 within the price negotiations with the main contractor (Hitachi) for Stage II of the project (including the supply of equipment with long-lead and short-lead delivery periods as well as for services for the installation of the equipment).

- Final reporting and financial closure.