Sixth Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNESCO |  | Cluster B: Education and Culture |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| B1-08 “Literacy and Life Skills Development Project" |  | No. 6 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 (with an update until September 2007) |  | US$ 2,230,400 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| Ministry of Education Directorates and Governorates of Education UN partner: UNOPS, UNICEF NGOs: Movimondo, Armadilla, AMAR International Charitable Foundation and Norwegian Church Aid |  | MOE Iraq (a) Baghdad; (b) Dyala; and (c) Samawah (Al-Muthanna). |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| - NFE = Non-Formal Education. - EFA = Education for All. - CLCs: = Community Learning Centres. - NLRC = National Literacy Resource Centre. - MOE = Ministry of Education. - MDGs = Millennium Development Goals. - NGOs = Non-Governmental Organizations. |  | One Year (August 2004 – August 2005). Project extended until 30 June 2007 and another request has been recently submitted for project extension until 31 December 2007. |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Objectives of the Programme/Project:

The overall objective of the project is to provide the basis for strengthening personnel and institutional capacities at national, governorate and local levels in policy design, implementation, monitoring and evaluation of literacy and NFE. Specific objectives are:

- To provide and revitalise, in a short period of time, the knowledge-base required for designing and implementing large-scale, effective NFE programmes based on community mobilization in collaboration with the government drawing on the United Nations Literacy Decade; EFA Dakar (2000) goals and the Millennium Development goals;

- To establish a National Literacy and NFE Resource Centre (NLRC) and setting up five pilot Community Learning Centres (Baghdad 3, one each in Erbil and Samawah);

- To support innovative projects and programmes with a view to reducing the alarming illiteracy rate in general and that of women in particular and promote “learning to live together”;

- To build and strengthen the capacity of the Non-Formal Education sub-sector of the MOE;

- To provide literacy and NFE vocational training for empowering adult women;

Outcomes of the Programme/Project:

- A National Literacy and NFE Resource Centre (NLRC) established along with a set of programmes of non-formal education to ensure the sustainability of the five pilot Community Learning Centres (CLCs);

- Development of literacy and livelihood skills, enhancing local capacity, generation of gainful employment and an entrepreneurial culture;

- Advocacy programmes and campaigns utilising national and local media to ensure socio-economic transformation and empowerment of adult women in addressing the right to education that seeks to generate partnership towards democratic change.

Outputs of the Programme/Project:

In close collaboration with the government and NFE/literacy stakeholders:

- A National Literacy and NFE Resource Centre (NLRC) will be established along with a set of programmes of non-formal education to ensure the sustainability of the five pilot Community Learning Centres;

- Development of literacy and livelihood skills, enhancing local capacity, generation of gainful employment  and an entrepreneurial culture;

- Multi-media literacy training materials developed especially by involving media and developing existing projects;

- National/sub-national networks strengthened;

- Holistic information on literacy and NFE experiences and development opportunities; locally specific development needs of the poor assessed;

- Local and national facilitators of community-based literacy and NFE programmes trained and re-trained;

- Consolidation of on-going literacy and NFE programmes and initiation of innovative pilot projects; and

- Advocacy programmes and campaigns utilising national and local media to assure socio-economic transformation and empowerment of adult women in addressing the right to education that seeks to generate partnership towards democratic change and for raising and seeking technical and financial commitments.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq

- UN Millennium Development Goals

- Joint Needs Assessment

- Iraq National Development Strategy

In order to meet the pressing demand for literacy and NFE and to contribute to the achievement of national EFA and MDGs, the proposed project establishes a National Literacy Resource Centre (NLRC) within the authority of the MOE. The major thrust of the project is to provide a basis for building indigenous NFE and literacy networks, thus strengthening the capacity of MOE and providing technical input for other NGOs and government organizations involved in literacy and NFE activities. If the task of providing educational opportunities is not addressed immediately, illiteracy will continue to multiply leading to compounding numbers of unemployed youth and adults.

As such, this project fits well within the framework of the UN strategy for assistance to Iraq as well as within the Millennium Development Goals. The project addresses directly the MDG goal related to the participation of children (Goal 2: “ensuring that all boys and girls complete a full course of primary education”). Further, the project contributes to the achievement of gender equity and equality in girls’ participation, retention and provision of relevant and quality education (Goal 3: “eliminating gender disparity in primary and secondary education”). Also, this project intends to generate employment opportunities in Iraq by offering opportunities for the participants to acquire specific training skills that could be applied in other contexts.

The Joint Needs Assessment and the National Development Strategy (NDS) analysed the status of education in Iraq in 2003. It was noted in both documents that enrolment rate decreased alarmingly and that students were dropping out from schools, mainly for economic reasons. The documents also list recommendations that aim at restoring the Iraqi education system to the level of the early 1980s, where the literacy rate was 96% of the total population. The Literacy and Life Skills Development project was designed in the year 2004 to respond to the immediate educational needs of women and girls who dropped out from schools or who had never had the opportunity to enrol in the Iraqi formal system, in order to avoid further deterioration in their educational status and to overcome the gender gap which was highest in the northern region, especially that the literacy rate back then was 20% lower for women than men.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency.

Ministry of Education and Directorates and Governorates of Education:

MoE and DoEs cooperate with UNESCO in several aspects, mainly:

- Identification of sites for setting-up the NLRC and CLCs in the three targeted governorates.

- Nomination of directors for these centres.

- Nomination of officials and community members for participation to capacity building programmes within the project.

- Receipt and verification of goods and supplies procured by UNESCO contractors.

UN Partners:

  - UNOPS: Assisted UNESCO in the procurement of the third batch of equipment for income-generation skills.

  - UNICEF: was not an implementing partner, however, being the Cluster B Coordinator, it played an important role in following-up on the project and ensuring that no overlap with other agencies occur during implementation. It also recommended several NGOs that could be helpful to the implementation of the project.

  - UNIDO, ILO and UNHABITAT: Although not an implementing partner, cooperation is ensured within the cluster activities.

NGOs:

- Movimondo undertook the Needs Assessmment Survey on Non-Formal Educationa and Literacy status in Iraq, due to its network inside Iraq. The assessment was conducted during 2005.

- Armadilla undertook a needs assessment on out-of-school children in Iraq. This survey was conducted in 2006 and the final report is available with UNESCO.

- AMAR International Charitable Foundation is co-implementing with UNESCO a sub-project on Literacy and Peace Education in the Southern Marshlands, targeting adult illiterates and semi-literates.

- Norwegian Church Aid: is implementing a project in Basra that aims at establishing a Youth Centre for children aged 7 – 14 years in order to provide them with the opportunity to undertake literacy classes and learn some vocational skills.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed.

Total funds allocated for the project: US$ 2,230,400.

Total funds committed until 30 June 2007: US$ 2,038,266 (91.39% of the total allocated budget).

Total funds disbursed until 30 June 2007: US$ 1,939,932 (86.98% of the total allocated budget).

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

The project has been ongoing for the last three years due to delays in implementation stages. These delays and variations are due to the following factors:

- The prevailing security situation in Iraq restricts MOE and UNESCO staff movement.

- The continuous delay in the decision-making process as well as regular turn-over at the MOE. This factor excluded the possibility of field visits to the sites of the NLRC and CLCs during the first year of the project. As a result, there were substantial delays in the identification of the sites and their need for minor repairs.

- Some logistical problems have been encountered with regard to the bidding process for rehabilitation of the centres.

- A problem with the MOE central warehouses whereby the warehouses had been overloaded with equipment. Accordingly, UNESCO has been requested to delay the delivery of the last batch of equipment, which affected negatively the timely implementation of the project and its implementation rate.

- Several delays in the distribution of all equipment and furniture to the five targeted centres in the project. The distribution was agreed to be under the full responsibility of the MOE. However, the delay in this activity pushed back the whole project's timeframe. UNESCO continues to monitor the progress of this activity closely. The MOE recently informed UNESCO that most of the equipment and furniture have been distributed and that this activity is anticipated to be completed by September 2007.

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

The explanation of the use of funds (as of 30 June 2007) is as follows:

- Staff Travel = 97% (of allocated budget for this item)

- Consultants = 100% (of allocated budget for this item)

- Salaries = 100% (of allocated budget for this item)

- Contracts = 88% (of allocated budget for this item)

- Training = 82% (of allocated budget for this item)

- Equipment = 100% (of allocated budget for this item)

- Miscellaneous = 100% (of allocated budget for this item)

- Security = 31% (of allocated budget for this item)

- Agency Management Support = 88% (of allocated budget for this item)

  - Indicate other funding sources, if applicable.

UNESCO core funds: US$20,000 to cover the fee of the Ministry of Education for undertaking the Needs Assessment Survey on NFE/literacy in Iraq for the period 1st July 2005 - 31st October 2005.

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable.

The project was extended four times and the budget was revised two times. In the first revision, US$ 75,000 was transferred from the budget line allocated for equipment to the budget line allocated to training, whereby in the second revision, US$145,000 was transferred from several budget lines to the budget line allocated for contracts.

These budget revisions were needed due to the shortage incurred in the budget allocated for training and capacity building. This shortage was due to the change in daily subsistence allowance rates from time to time, as well as to the change in procedures regarding hosting Iraqi nationals in certain countries of the region. Such changes obliged UNESCO Iraq to change the venue of several workshops to more expensive countries, which also led to the increase in the total values of certain contracts that were formalized in this regard.

  - Project expenditures for the 1 July to 31 December 2007 period.

  - Finalization of the Final Report for the two needs assessment surveys conducted throughout Iraq on the status of Literacy and NFE in order to identify and respond to the learning needs of the different population groups. It is to be noted that the Needs Assessment was conducted by both MoE (in collaboration with MoP) and Movimondo (International NGO).

  - Re-production of literacy and NFE advocacy materials for awareness-raising purposes inside Iraq.

  - Completion of the distribution of all equipment and furniture from the MoE Central Warehouses to the NLRC and CLCs, in order to enable the centres to start operating as soon as possible.

  - Continuation of the Literacy and Peace Education Programme, jointly implemented with AMAR International Charitable Foundation, in order to provide learning opportunities to illiterate and semi-literate people in the Southern Marshlands. About 1,000 persons have been benefiting from literacy (reading, writing and numeracy) and peace education classes through this two-year programme. During the coming two months, these persons will continue their fourth and final semester in order to pass the official examination and obtain their certificates from the Ministry of Education.

  - Establishment of the Youth Centre in Basra for illiterate and semi-literate children aged 7 – 14 years. The centre is being established in partnership with the Norwegian Church Aid and in close collaboration with the Ministry of Youth and Sports. The center will encompass small-scale activities in the first year and the activities will be divided into two major activities: educational (computer and internet courses) and skills development (carpentry and sewing). The center will be linked with a similar center in Jordan using computer technology. This Initiative will help Iraqi children to promote their communication across borders, widen their cultural perspectives, and promote cultural exchange.

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

The National staffs working on this project includes 6 National Officers and 6 Project Assistants (all are partially co-funded with other projects).

  - International Staff: Provide details on the number and type (operation/programme)

The project is managed by 2 International staff members (partially co-funded with other projects).

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

UNESCO has been implementing the project inside Iraq with limited human resources on the ground. The project was designed to respond to literacy and NFE needs even if security issues prevented international staff from working in Iraq. Making use of innovative collaborative approaches with partners, the UN team worked with hundreds of institutions inside and outside Iraq to provide supplies, services, policy advice and capacity building. The implementation depends on national experts, local contractors, and NGOs thereby building capacity and providing income-generation opportunities.

UNESCO’s team of monitoring contractors inside Iraq have been playing a crucial role in the follow-up on activities that relate to the rehabilitation of the centres' buildings, receipt of equipment and furniture, as well as liaising with the MoE to obtain necessary information in a timely manner.

UNESCO continues to follow-up closely on the project implementation through its monitors based in Baghdad and Erbil. Monitors perform regular visits to the project sites and provide comments and reports on the progress of certain activities handled by the MoE. As for refurbishment of the centres, UNESCO hired a consulting firm to monitor the progress of the rehabilitation works and provide monthly reports.

Although there were several delays in the distribution of all equipment and furniture to the five targeted centres in the project, it is expected that most of the equipment and furniture will be distributed by September 2007. The purchase of furniture was done locally in Iraq. As for the equipment, all procurement was subject to international competitive bidding processes. Due to time constraints, and the need to procure some tools locally in Iraq, the procurement of the third batch of equipment was handed over to UNOPS.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

The purchase of furniture was done locally in Iraq. As for the equipment, all procurement was subject to UNESCO’s standard rules and procedures of international competitive bidding processes. For contracts amounting to more than US$100,000, the offers/proposals are examined by the Contracts Committee established at UNESCO Headquarters. Upon obtaining the approval, UNESCO Iraq Office moves to the contracting stage. As for the third batch of equipment, as it involved the procurement of large amounts of small tools available on the local market, UNESCO decided to hand over the procurement to UNOPS due to time limitations given UNOPS stronger presence in the field and wider networks of distribution.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

UNESCO continues to follow-up closely on the project implementation through its monitoring partners in Baghdad and Erbil. Those monitoring contractors provide updates on a regular basis and when requested. They visit the sites targeted in the project and provide comments and reports on the progress of certain activities handled by the MoE. As for refurbishment of the centres, UNESCO hired a consulting firm to monitor the progress of the rehabilitation works and provide monthly reports. In some cases, UNESCO would request NGOs to monitor certain activities being implemented in some districts that are considered highly-tensioned and where UNESCO monitors are not capable of accessing due to security considerations.

  - Report on any assessments, evaluations or studies undertaken.

Once the final report of the needs assessment survey is finalized, UNESCO could provide concrete assessments and results. The on-going Needs Assessment Survey was designed to collect basic quantitative data and qualitative information as a means for developing a national policy document as well as for planning the future activities in other governorates. Specifically, a needs assessment survey on Literacy and NFE status in Iraq will identify and respond to the educational needs of illiterate and semi-literate population groups (aged 18+). UNESCO has completed the needs assessment survey on NFE/literacy status in Iraq, using diverse samples from households in the north, centre and south of Iraq with a particular emphasis on urban, semi-urban, rural and remote rural areas. A full project evaluation is planned and is scheduled to be effected once the NLRC and CLCs become operational and the project is declared operationally completed. UNESCO is undertaking regular monitoring and evaluation on the project’s activities, which permit following alternative implementation modalities whenever time deviations are noticed.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

Output 1:

National Literacy and NFE Resource Centre (NLRC) established along with a set of non-formal education programmes and five pilot Community Learning Centres;

Activities undertaken include:

- Refurbishment of the NLRC and CLCs sites. This included fixing the electrical points, white-washing, fixing sewage systems and water supplies.

- Procurement of necessary furniture and equipment to the centres. Final distribution from central warehouses to the centres is pending and is anticipated to be completed during September 2007. The equipment was identified by the MoE in accordance with the income-generation skills, which were determined for each CLC. This included computer laboratories, sewing, food production, beauty parlours, painting and English Language.

Output 2:

Development of literacy and livelihood skills, enhancing local capacity, generation of gainful employment and an entrepreneurial culture;

Activities undertaken include:

Once all equipment and furniture are installed, the centres will start operating to enhance the skills of the semi-literate and literate population groups. The centres will be opened in cooperation with and ownership of communities. Adults, particularly women in the economically active age-group, will be the target beneficiaries of the literacy, livelihood skills, income generation and poverty reduction projects.

Additionly, UNESCO and AMAR International Charitable Foundation have been providing basic literacy (reading, writing, numeracy) and Peace Education (human rights, child rights, living together) learning opportunities to semi-literates and illiterates in the Southern Mashlands through the Literacy and Peace Education Programme (as explained earlier in II 2.6). The total number of students benefiting from this programme amounts to 1,800 persons.

UNESCO has also been preparing for the establishment of the Youth Centre in Basra in partnership with the Norwegian Church Aid (NGO) to provide educational and skills-developing opportunities for semi-literate and illiterate children in Basra (Aged 7-14). (Please refer to II 2.6). With the skills-developing opportunities, the centre is providing an opportunity to these youth students to acquire skills that generate gainful employment and livelihood skills.

Output 3:

Multi-media literacy training materials developed.

Activities Undertaken include:

Organization of a training workshop on the development of literacy primers and advocacy materials in Cairo during March 2006. The workshop benefited 25 participants including the Directors of the CLCs and the Director of the NLRC.

Output 4:

National/sub-national networks strengthened

Activities Undertaken include:

This is ensured throughout the activities of the project's implementation. The Community Learning Centres will be opened in cooperation with and ownership of communities. The project seeks to build strong networks of literacy and NFE programmes with NGOs, government organizations, international agencies and public institutions (such as libraries). The National Literacy Resource Centre will restore linkages with its sister organizations in Baghdad, Samawah and Erbil and eventually in other governorates to share and improve experience in literacy activities. Additionally, this project will increase people’s ability to access learning materials, thus strengthening networks through empowering people to share views, discuss common problems and find solutions.

Output 5:

Holistic information on literacy and NFE experiences and development opportunities; locally specific development needs of the poor assessed

Activities Undertaken include:

Conducting the needs assessment survey on Literacy and NFE status in Iraq in order to identify and respond to the educational needs of illiterate and semi-literate population groups (aged 18+). The assessment was conducted during 1st July 2005 - 31st October 2005. The report of the survey was drafted in December 2006. However, a final analysis report will be issued by end August 2007.

Output 6:

Local and national facilitators of community-based literacy and NFE programmes trained and re-trained;

Activities Undertaken include:

Organization of a training workshop in Cairo during July 2006 in order to train NFE facilitators, animators and volunteers on managing NFE programmes in Iraq. About 17 Iraqi persons participated to this workshop, including the directors of the CLCs and the director of the NLRC.

Output 7:

Consolidation of on-going literacy and NFE programmes and initiation of innovative pilot projects;

Activities Undertaken include:

This output will be realized once the centres become operational. Up until August 2007, the supplies have been partially delivered to the end destination with a percentage that amounts to about 95%. Accordingly, it is guaranteed that the centres start operating upon the delivery of the remaining items.

Output 8:

Advocacy programmes and campaigns utilising national and local media to raise awareness about literacy and to support empowerment of adult women in addressing the right to education.

Activities Undertaken include:

Advocacy materials prepared with consideration given to the Iraqi context. These materials comprised wallpapers, posters, leaflets, T-shirts and caps. As for the re-production of these materials, it is still pending and anticipated to be completed during September – October 2007. These materials are to be used for launching a National Literacy Campaign throughout Iraq for awareness-raising on the importance of education, especially under the current security situation.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

The project was successful in achieving almost all short-term outputs, comprising all hardware and software components of the programme. As outlined above in 4.1, short-term outputs achieved include the procurment of equipment for centres, a training workshop on the development for literacy primers, a needs assessment survey, a training of NFE facilitators, and the preparation of advocacy materials.

However, the NFE programmes that should be incorporated within the targeted centres, and which constitute the main thrust of this project, haven’t been officially started yet. It is anticipated that once the centres operate and the programmes start running, a clearer assessment of the actual status will be developed. Accordingly, the medium-term outcomes cannot be measured at this moment.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Please refer to the following:

  - IV Results – Question 4.1 - Outputs 1,2, 3, and 8.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

Please refer to II 2.2 above.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The key partnerships and collaborations in this programme are with a number of NGOs and contractors of the private sector, which provided great and efficient support in monitoring and implementing activities on the ground (where UNESCO monitors could not reach). The two helped in pushing forward the implementation process through their skills, presence, and experiences in the field as well as through their knowledge of the history and background of certain areas.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The project aims at empowering girls and women and equipping them with income-generation and life skills that will lead to job creation and self-confidence. Unfortunately, no figures are available regarding long-term and short-term jobs created the learning centres are not yet operational. However, the holistic approach of the project seeks to encourage women's participation in the community in order to demolish the gender gap.

Through this project and through the component on Peace Education and Literacy, the semi-literate and illiterate people in the Southern Marshlands are given lessons in human rights, freedom of expression, peace and democracy, etc. This project has been trying to tackle most of the cross-cutting issues and matters that need to be treated in the Iraqi context. Environment issues are tackled within the life skills programme to enhance the community’s awareness of preserving the environment and environmental responsibility.

- Future Work Plan

  - Summarize the projected activities up to the end of June 2007.

During the last six months, UNESCO has been undertaking the following:

- Following-up with the MoE on the procurement, receipt and distribution of all furniture and equipment intended in the project.

- Implementing the Literacy and Peace Education sub-project with AMAR International Charitable Foundation in the Southern Marshlands. The project opened 80 literacy and peace education classes and about 1,000 persons benefited from this two-year programme up-to-date. Continuation of the programme for another two months is very crucial, as the beneficiaries shall complete the courses, sit down for the final examinations and obtain the certificate from the Ministry of Education for completion of Primary Education.

- Implementing the Youth Centre project in Basra in partnership with the Norwegian Church Aid (NCA). The project is ongoing and the following has been achieved: (a) Assessment and evaluation of the building provided by Ministry of Youth and Sports (MoYS), (b) Renovation and rehabilitation of the existing building to provide a healthy environment suitable for learning and socializing, and (c) Furnishing the center with needed equipments and supplies including:

General Items:

    - Furniture for Management

    - Furniture for Kitchen

    - Generator and Air-conditions

Activities’ Items:

    - Furniture for the classes

    - Carpentry tools

    - Sewing machines and tools

    - IT Hardware & Internet lines

The centre was successfully inaugurated in the beginning of this month in the presence of officials of the Ministry of Youth and Sports and community members in Basrah.

- UNESCO has been preparing advocacy materials for re-production in order to raise awareness on the importance of literacy and NFE programmes throughout Iraq.

# Text boxes

Report Formatting Instructions: We kindly ask that you review the instructions below and follow them in the preparation of your report:

- Do not put the narrative text into boxes as was done in the previous report and do not incorporate boxes, graphs, etc into the narrative report.

- Add additional information including charts, graphs, etc as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative

- Number all sections and paragraphs as indicated below

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.