SECOND six Monthly progress report

Strengthening primary and intermediate level education

# Summary

| Participating UN Organisation: |  | Cluster: |
| --- | --- | --- |
| UNICEF |  | Cluster B: Education & Culture |

| Project No. and Project Title: |  | Project Location/Region/Province: |
| --- | --- | --- |
| B1- 24: Essential materials for improved learning for all primary level students in Iraq |  | All 21 Directorates of Education in Iraq |

| Reporting Period: |  | Report no: |
| --- | --- | --- |
| 1st January – 13 June 2007 |  | 02 |

| Counterpart organisations / implementing partners: |  | Project cost: |
| --- | --- | --- |
| MOE, DoEs, UN agencies, and NGOs |  | US$ 18,172,619 |

| Abbreviations and Acronyms: |  | Project Duration: |
| --- | --- | --- |
| MOE Ministry Of Education DOE Directorate of Education UNICEF United Nations Children’s Fund WFP World Food Program UNESCO United Nations Education Scientific and Cultural Organisation MOLSA Ministry of Labour and Social Affairs MOHE Ministry of Higher Education MOH Ministry of Health UNHCR United Nations High Commission for Refugees CWC Child Welfare Commission |  | 02 October – 02 April 2006 |

# I. Purpose

Main objectives and outcomes expected as per approved Project/Programme/project document:

Main objectives The overall objective of this project is to enhance the access to and quality of primary level education by providing essential learning materials to about 4.7 million students with the goal to alleviate the effects of economic hardship on Iraqi families and thus promote the enrolment of age 6 children to primary schools while ensuring participation of children age 7-12 in primary schools. SPECIFIC OBJECTIVES OUTCOMES EXPECTED A total of 4.7 million Iraqi children aged 6 – 12 (grades 1-6) are provided with the necessary learning materials during the start of the 2006/2007 scholastic year. All 4.7 students are receiving 8 exercise books, 10 pencils, 2 sharpeners, 2 erasers, colouring pencils and 1 ruler. 3,937,849 students in grades 1 – 6 are receiving one drawing book each while 1.1 million newly enrolled grade one students are receiving school bags

Reference to how the programme/project relates to the UN Assistance Strategy to Iraq and how it aims to support international and national development goals (National Development Strategy) including the Millennium Development Goals and other goals as pertinent:

The project is fully in line with the 2005-07 UN Strategy for Assistance to Iraq and conforms closely to the priorities expressed by the Iraqi Authorities during meetings with the ministry of education in end of July 2006. The Ministry of Education has discussed the magnitude of the current, dire economic hardship and its impact of the ability of the families to provide the necessary school items for their children. The main purpose of the projects is to strengthen the overall quality of education and service delivery at primary and intermediate levels and improvement of the overall learning environment. The objectives are set against the background of the Iraqi National Development Strategy (NDS), the Millennium Development Goals (MDGs), particularly Goals 2 and 3 and the Education for All (EFA) Framework for Action. The activities will be closely aligned with specific gender, environment, employment, and security rights, and address as closely as possible concerns for reconstruction, rehabilitation and employment creation.

Main international and national implementing partners involved their specific roles and responsibilities in project implementation and their interaction with the agency:

UNICEF and UNESCO provide leadership for ensuring sector-wide perspective to the programme. UNICEF is primarily responsible for the development and implementation of the basic education strand, including Early Childhood and Primary & Intermediate levels of education, as well as for inclusion of learning opportunities for 12-18 year old out-of-school children. UNESCO prime focus is on the Secondary, Tertiary and Vocational / technical levels as well as tertiary education. UNICEF implements all activities in close collaboration with the Ministry of Education and its Directorates of Education, the Ministry of Higher Education, local authorities, international / national NGOs, private sector and donors. The main implementing line ministry is the MOE which collaborate with MOHE to provide direction and ensure Iraqi ownership of the programmes/projects. MOE manages all projects through the Directorates of Education (DOEs) in the governorates. Collaboration with NGOs is mainly in the area of rehabilitation of schools with renewed focus on the soft component of hygiene and sanitation in schools, including mobilization and capacity building of local stakeholders (PTAs and communities) in project implementation. As Cluster Coordinator, UNICEF actively endeavours to ensure synergy of interventions by fostering joint programming and implementation with agencies, based on their respective technical expertise, area of specialization and comparative advantage.

# II. Resources

Total approved budget and summary of resources available to the programme/project from the UNDG Iraq Trust Fund and non-Trust Fund resources where applicable:

As of June 2006, UNICEF’s total Education Programme budget for 2004-2006 was US$ 10,058,950. By the fourth quarter of the year UNDG ITF approved budget totalled US$ US$ 18,172,619 to cover cost of essential learning supplies for 4.7 million primary level students under this project. UNDG ITF also approved a second joint UNICEF and HABITAT project amounting US $ 9, 029,119 to cover the transformation of 90 schools into child-Friendly standards

# III. Results

An assessment of the extent to which the programme/project component / programme /project is progressing in relation to the outcomes and outputs expected for the year:

The Trust Fund significantly contributed to the procurement and distribution of essential learning materials to approximately 4.7 million students. Above 90% of the supplies reached Directorates of Education (DOEs) warehouses and delivery of the remaining items is expected to be finalised in a months time

Main activities undertaken and achievements/ impacts:

EDUCATION SUPPLIES 100% of the essential learning materials were delivered to all Directorates Of Education (DOEs) warehouses. A total of 4.7 million Iraqi children aged 6 – 12 are being provided with essential learning materials in this scholastic year. Each child is receiving 8 exercise books of 194 pages each, a box of 10 pencils, 2 pencil sharpeners, 2 erasers, 1 ruler, one drawing book and one box of colour pencil. In addition to that, 1.1 million newly enrolled grade 1 students are receiving one school bag each, in addition to the above mentioned materials. This most welcome development is made possible by a timely support from the European Union following an urgent request from the Ministry of Education. Late September, the Minister of Education approached UNICEF and the UNDG ITF to help cater for this critical need because funds were not available at Ministry. This initiative contributed to the improvement of teaching and learning practices in the classroom. It will also alleviate some of the cost burdens of education especially for the poor parents who will be encouraged to send their children, particularly girls to school, many of whom would have otherwise dropped out of school. UNICEF-supported Back-To-School Campaigns in 2004 and 2005 have been a success. Large quantities of essential learning and teaching materials were procured and distributed to over 6 million primary and intermediate level (grades 1 – 9) students in 17,000 schools in Iraq.

Implementation constraints, lessons learned from addressing these and knowledge gained from assessments, evaluations and studies that have taken place during the reporting period:

The lack of improvement regarding the security situation and the turnover at MOE and DOE levels has continued to hinder the effective implementation of the project. However, UNICEF succeeded to establish close working ties with the Minister of Education and his office; this helped reduce red tape and bottlenecks for implementation. Nevertheless, for various reasons, continuous replacement of key officials/directors remained an issue for holding regular meetings of the Sector Working Group on Education. Lack of proper coordination between MOE and DOEs continues to hamper implementation. The issue has been discussed with MOE officials at the Annual review meeting and will be tabled at Sector Working Group to enable MOE and other supporting donors and agencies to explore remedies together. DOEs don’t have recurrent budget to enable them efficiently distribute the materials to schools. Implementation and Monitoring In Iraq: UNICEF has three well qualified education staff between the Baghdad, Erbil and Basra offices assisted by 10 qualified engineers and 15 monitors hired under an institutional contract. In addition, UNICEF has full fledged operations, supply / logistics & finance support units in Baghdad and Erbil offices which support education as well as other sectoral programmes. UNICEF’s contracting and supply delivery procedures also had to be revised substantially to ensure minimum exposure of national staff, while safeguarding the transparency and integrity of processes. After considerable consultations with the Regional Office and the Headquarters, “remote-controlled” procedures for working in Iraq were put into place. For example, under normal circumstances, UNICEF would channel the supplies first through UNICEF warehouse in Baghdad and then redistribute them to counterpart’s warehouses through a secondary transporter. However, to minimise additional security risks involved, UNICEF sends all shipments directly to partners in the governorates. To improve the ability to verify safe delivery of the supplies to the Governorates, Consignee Signatory Panels were established within counterpart agencies to provide Proof of Delivery (POD) at the governorate/ directorate level. UNICEF-contracted monitors also play a crucial role in ensuring that the supplies are received by the right consignees and distributed to end-users without undue delay. To enable the bidding process to continue despite the restricted movement of staff inside the country and between Iraq and Jordan, UNICEF introduced a new modality of bidding and issuance of institutional contracts inside Iraq through the use of courier services. This new procedure allows UNICEF to revive and sustain the contracting process for infrastructure reconstruction activities, which had been suspended for a length of time during the year. These measures helped lay the foundation for UNICEF’s ability to continue providing support, even if the security situation does not improve in the future. Given the security situation and the consequent restricted movement of staff and government officials, monitoring of the activities is undertaken by a team of monitors and engineers, hired by UNICEF through an external contractor. The monitors and engineers (some of them are ex UNICEF/ UN staff) provide a critical monitoring/ supervisory input to the implementation of the project. They track the arrival of supplies/ equipment; supervise the civil works and installation of equipment in various governorates, while reporting to the UNICEF staff in Baghdad/Amman for technical guidance and adherence to implementation schedule. This allows UNICEF to minimize the exposure of its national staff to risks involved in travelling to project sites, while still being able to monitor programme implementation process and results. All ongoing programme implementation work has been monitored, to a greater or lesser degree, despite the extremely difficult programme environment. Certification of work completed, e.g. in reconstruction/rehabilitation of water/sewage plants, has enabled prompt payments and timely completion. Ideally this should be done on a sample basis by UNICEF staff. Whilst this is still not possible in Iraq, UNICEF is considering options to hire local audit companies to do this. Similarly, security and communications support to the monitors is being refined, to ease their work and lessen their risks. During and after completion of activities, reports including achievements, lessons learned and obstacles are prepared including photos of different activities are taken before and after completion of works, checked by Education staff on ground and sent to Amman to the International staff that analyse these reports and provide guidance on improvement and or ways to overcome obstacles. Outside Iraq: With the evacuation of international staff of UNICEF to Amman, the senior international education officer (head of section), and 3 project officers education are now located in Amman temporarily. As in the case of Iraq, the senior and highly experienced international operations, supply/ logistics and finance officers and staff are now temporarily located in Amman and support the programme implementation there from. There is a Supply unit especially established for Iraq within the UNICEF Supply Division in Copenhagen to facilitate international procurement of supplies and equipment. UNICEF also conducted several training workshops outside Iraq for MOE/ DOEs staff in Amman, Egypt and Far East countries, as part of the capacity building of the counterpart and exposure to several other countries experience in ECD and Formal Education. Outsourcing of Services and partner agreements with MOE and NGOs: Given the realities on the ground, UNICEF has contracted a number of agencies, which are providing the services of 10 monitors and 10 civil engineers on an ongoing basis. UNICEF is increasingly entering into agreements with NGOs to expand outreach of its programmes. Most importantly, UNICEF has entered into specific project agreements with MOE at the National and Directorate levels for implementation and management of key activities in the education sector (such as distribution of education kits, printing textbooks, conducting school surveys, and initiating teacher training activities). Capacity building efforts include organizing several workshops for MOE supply staff with the view of improving on the specification and quality of school kits. MOE also participated in the preparation and finalization of specifications/ designs of the child friendly school furniture, which is being procured and distributed under the Trust Fund project. It is worth mentioning that UNICEF has frequently encouraged the participation of MOE engineers in the school rehabilitation activities, including the selection of schools, supervision of rehabilitation works and the handover processes after completion of the works.

Key partnerships and inter-agency collaboration, impact on results:

UNICEF is coordinating the Education and Culture Cluster within the UN Strategic Plan and chairs the Education Coordination Forum in Amman. It is also an active member of the Sector Working Group on Education and provides technical support to MOE jointly with USAID, UNESCO and the World Bank. This has helped ensure good prioritization of education projects funded through the UNDG Iraq Trust Fund and avoided duplication by teaming up with other agencies on joint programming.

Highlights and cross cutting issues pertinent to the results being reported on, e.g. Gender disaggregation, policy engagement and participation of the public:

The programme has a strong gender dimension: 1,920,401 girls and 2,424,208 boys benefit under the education project phase-I. To offset this imbalance (0.13 gender gap), and based on findings of the 2003-2004 school survey, positive discriminatory measures are built in the UNICEF 2006 education programme, including an assessment to unveil the constraints to girls’ enrolment and attendance in formal primary schools and how to address them. Based on findings from the survey, MOE-UNICEF drafted a strategy for accelerating the education of girls in southern Iraq to be shared with donors and supporting partners that is currently shared with donors, as part of UNICEF Fund raising drive in 2006. Under UNICEF-supported Accelerated Learning Project for out-of-school children, as well as under the Teacher Training programme, policy dialogue with MOE has resulted in a more proactive engagement of their staff and their training needs have been identified in the areas of proposal writing and donor coordination.

# IV. Future Work Plan

Priority actions planned for the subsequent reporting period to overcome constraints, build on achievements and partnerships, and use the lessons learned during the previous period:

Monitoring and evaluation of the impact of essential learning supplies on enrolment and retentions will be carried out.

Indication of major adjustments in the strategies, targets or key outcomes and outputs:

Estimated Budget required (including any major funding shortfalls):