Sierra Leone MDTF

Fund Signature Page

(Note:  this page is attached to the programme document)

| Participating UN Organisation(s): UNICEF |  | Priority Area: JV: Equitable and Affordable Health Services AFC: Chapter seven – Human Development |
| --- | --- | --- |
| Programme Manager, Participating UN Organization: UNICEF Name: Dr Lianne Kuppens Address: Govt. Medical Stores Compound Jomo Kenyatta Road PO Box 221 New England Freetown - Sierra Leone Mobile: +232 76 291 023 E-mail: lkuppens@unicef.org |  | Implementing Partner(s): National Health System Name: N/A (Direct Execution) Address: N/A Telephone: N/A E-mail: N/A |
| Project Number: Joint Vision Programme Twenty. (ID 75591) |  | Programme Duration: Six Months Estimated Start-Up Date: July 2010 |
| Project Title: National Health System : Strengthen the Procurement and Supply Chain Management (PSM) for medical supplies of the MOHS |  | Programme Location: Country wide encompassing all 13 districts. |
| Project Description: National health systems: Strengthening the PSM of medical commodities and other health related of the MOHS at all level. UNICEF will ensure systems are strengthened and monitoring systems in place to ensure essential medical supplies and commodities reach the target population. |  | Total Project Cost: US$ 547,668 SL- MDTF: US$ 547,668 Government Input: 0 Other: 0 GRAND TOTAL: U$ 547,668 |
| Development Goal and Key Outcomes: Outcome : Harmonized procurement and distribution system that ensures uninterrupted equitable access to medicines and medical supplies |
| Deliverables: Efficient procurement and supply chain management system which incorporates development of training materials designed and put in place including integration of HIV screening and diagnostic facilities by the end of 2011. Training on data collection, analysis and use conducted for health personnel involved in the generation of data from the district health information system by 2011. Community based health and nutritional information system put in place by end of 2012. Annual planning process of comprehensive district planning in all 13 districts finalized each year from 2010 to 2012. A monitoring system for the free health care programme for pregnant women and children under five developed and implemented by 2010. |

|  | Signature |  | Date |  | Name/Title |
| --- | --- | --- | --- | --- | --- |
| UNICEF |  |  |  |  | Mr. Mahimbo Mdoe Country Representative |
| DEPAC Co-Chair |  |  |  |  | Honorable Dr. Samura Kamara Minister of Finance and Economic Development |
| DEPAC Co-Chair |  |  |  |  | Mr. Engilbert Gudmundsson Country Manager World Bank |
| DEPAC Co-Chair |  |  |  |  | Mr. Michael von der Schulenburg Executive Representative of the Secretary General of the United Nations |

Project Document

Executive Summary:

The Sierra Leone health system faces several challenges that affect its ability to provide the desired quality health care at all levels. These include a fragmented and inefficient healthcare delivery to adequately fulfil its sector leadership mandate; ineffective utilisation of existing skills and resources; inadequate national capability to test and respond to emerging and re-emerging diseases and disasters; lack of comprehensive health standards to guide the required minimum investment for quality health care delivery; amongst others. The sector is privileged to have several non-state health providers and development partners whose efforts however, in many cases due to poor coordination, experience duplication of health interventions and inefficiencies. Although the sector has developed a strategic plan to guide prioritisation of health interventions in response to the current burden of disease, its effective implementation will heavily rely on regular planning by all sector actors collectively and review of their performance, a function which is currently very weak. Health hereto, has been supply driven assuming that health providers fully understand their client/patient service needs, a situation that the strategic plan seeks to reverse to make health care delivery customer driven and responsive. Similar to other countries in the region, Sierra Leone is constantly faced with the risk of outbreaks of emerging and re-emerging diseases as well as natural disasters that require rapid evidence-based responses. These responses however, are currently compromised by weak laboratory services at all levels, a situation that is further worsened by inadequate research and quality control capability.

Situation analysis:

Sierra Leone continues to have very high child and mortality maternal mortality. The Government is thereby working with development partners to reverse the trend and achieve the Millennium Development Goals (MDG) four and five.

An intermediate goal before the MDGs target year was set by the country was to reduce by 30% the infant, child and maternal mortality by the year 2010. In order to achieve this, maternal and child health interventions need to be scaled up to reach universal coverage.

Availability of essential drugs at all levels of the health system is one of the important pillars to provide quality health care to the population and reduce significantly the mortality due to common diseases.

Assessment of the PSM System

A number of assessments of the Procurement and Supply Chain Management in Sierra Leone have been undertaken with varying levels of rigour and scope. An initial assessment was undertaken with funding from the European Development Fund for the Health Sector Support Project.  A mission to assess the context in which the request by MOHS to UNICEF  provide technical assistance and capacity building related to all aspects of the Procurement and Supply Chain Management within the MOHS system and  Service support related to the Reproductive and Child Health (RCH) programme while the system is set up ,  were taking place, analyze the risks and to support the formulation of recommendations for the way forward.  The Ministry of Health and Sanitation in collaboration with UNICEF also under took country wide assessments to quantify essential medicines and Medical consumables.

These assessments showed that the procurement and supply chain management of health commodities for Sierra Leone is facing serious challenges following the near collapse of the country’s health systems as a result of over a decade of conflict, economic recession and brain drain, which have inflicted a negative impact on its economic growth, with the worst effects being caused by under investments in health and therefore where the  root causes of the PSM system failures are linked to the incentive structures and lack of accountability in the present governance systems.

Challenges as a Result of Decentralization

The recent devolution of financial authority and procurement functions to the Districts Councils has highlighted problems in that area, including the encouragement of repetitive procurements in small quantities thereby denying the advantages of buying economics. There is also the risk of proliferation of substandard and counterfeit drugs and frequent stock-outs.

Coordination of Inputs

There are gaps that need to be addressed such as an uncoordinated PSM structure and system, insufficient budgetary allocation, human resource constraints, lack of public accountability, limited technical capacity of the human resource, incentive structures etc.

These gaps if addressed coupled with strong national leadership and political commitment at the highest level, a clear national framework, coherent budget allocation, and the presence of transparent and accountable decision making bodies will contribute to the effective implementation of the various health programs.

The RCH Program is generally recognized as positive platform and model for further health system development and is a major government strategic project in partnership with UNICEF and other major health partners including UN agencies and bilateral cooperation that addresses the extremely high infant, child and maternal mortality in Sierra Leone.

Actions by GOSL

The Government of Sierra Leone is aware of the gaps as well as what needs to be done, thus

The Honourable Minister of Health, Ministry of Health and Sanitation (MOHS) officially requested UNICEF to share their expertise by providing technical assistance and capacity building related to all aspects of the Procurement and Supply Chain Management within the MOHS system, and Support procurement services related to the Reproductive and Child Health (RCH) Program while the system is set up.

Response to the Request to UNICEF

As a first step in developing the basic principles that will guide the process of developing the PSM, as well as to assess the type of expertise needed, a team from the UNICEF Supply Division, Copenhagen, UNICEF Regional Office and the country team met with a range of stakeholders during 21-24 April 2009. The team assessed the level of risk for UNICEF, the willingness of partners to participate in the program, the feasibility and capacity of both government and partners including UNICEF. The team also assesses the policy and the governance issues around the program. The team and the Country Office agreed on a two track approach to the PSM development. The first phase covers the in-depth assessment of the current PSM systems in place. This first phase is in its final stage. This month, June 2010, the future model as a result of in-depth assessment will be shared with all stakeholders involved in PSM and decided upon. In July we will start the second phase covering the implementation of model chosen towards a national sustainable PSM system.

Results framework

Joint Vision framework and benchmark

As part of the Joint Vision programme 6 on HIV/AIDS and malaria, this project contributes to the UN Joint Vision’s broader effort to improve the national health services and in particular,  the development of national procure and supply management system for SL.

Outcomes

The intended outcomes of UNICEF contribution to programme 20 is to put in place a harmonized procurement and distribution system that ensures uninterrupted equitable access to medicines and medical supplies to all target population .

By 2012 the public supply chain management system will be in line with acceptable international standards is operational at all levels by 2012.

The aforementioned funds will target deliverables 20.1.6, 20.1.7, 20.1.8, 20.1.9 and 20.1.10 as highlighted below:

Deliverables

    - Efficient procurement and supply chain management system which incorporates development of training materials designed and put in place including integration of HIV screening and diagnostic facilities by the end of 2011.

    - Training on data collection, analysis and use conducted for health personnel involved in the generation of data from the district health information system by 2011.

    - Community based health and nutritional information system put in place by end of 2012.

    - Annual planning process of comprehensive district planning in all 13 districts finalized each year from 2010 to 2012.

    - A monitoring system for the free health care programme for pregnant women and children under five developed and implemented by 2010.

Core activities:

- Hire an international institution to support the process of establishing an efficient PSM

- Train health personnel on Health Information system (data collection, analysis and use)

- Support district annual planning process

- Support implementation monitoring activities of the Free Health Care.

Management and coordination arrangements

An International Consulting Firm with expertise in Pharmaceutical Procurement and Supply Chain Management will be contracted by UNICEF to work with and transfer skills to the Government to strengthen the entire PSM system at the central and district levels of health

care delivery in Sierra Leone.

It is envisaged that the consulting firm will have staff having diverse expertise in procurement, tendering, forecasting, contracting, logistics, freight, pharmacy, health product technology, quality control, inspection, warehousing & distribution, finance, human resources and information and communication technologies.

The design and implementation is planned to be very inclusive taking into account all existing systems and facilities in place and will be executed in three phases.

The expected output of the comprehensive technical assistance will be:

- Situation analysis leading to development of strategic plan and budget for PSM restructuring process.

- An integrated, transparent and sustainable Procurement and Supply-Chain management systems which is governed by well defined checks and balances and supported by a well trained Supply Chain team.

- Comprehensive PSM monitoring and quality assurance system.

- Setting up of a Donor/ Development Partners supply pooled fund system

- Establishing a local quality drugs procurement facility for districts and Faith Based Organizations.

Fund management arrangements

UNICEF will manage the funds according to internal funds management. An agreed reporting system will be established between UNICEF and MDTF.

UNICEF will sign the necessary MoU with the AA at the MDTFO to be a recipient of funds channelled through the SL-MDTF.

Monitoring, evaluation and reporting

Project monitoring and reporting will be done as per the UN Vision monitoring mechanisms and the UNICEF integrated monitoring and evaluation plans for 2010.

The impact of this project will be assessed as part of the Joint Vision programme 20 at least one calendar year after in the end of the project. However, a report on the project’s delivery will be issued in March 2010 as part of the MDTF reporting requirements

Elements of the logical framework

| Results chain | Performance indicators |
| --- | --- |
| Joint Vision Priority Area: Equitable and Affordable Health Service |  |
| JOINT VISION BENCHMARK |  |
| National health systems: Strengthening the PSM of medical commodities and other health related supplies of the MOHS at all level. UNICEF will ensure systems are strengthened and monitoring systems in place to ensure essential medical supplies and commodities reach the target population. |  |
| OUTCOME |  |
| Put in place a harmonized procurement and distribution system that ensures uninterrupted equitable access to medicines and medical supplies to all target population. | 1. An integrated public supply chain management system in place at central, district and PHU levels . 2. A Functional integrated Logistics Management Information System in place at central, district and PHU levels countrywide. |
| Public supply chain management system will be in line with acceptable international standards and is operational at all levels by 2012 | Transparent procurement process at National level. Proportion of good storage facilities at National District and PHU levels. Proportion of Efficient delivery and distribution systems at all levels Proportion of efficient inventory control system in place at all levels. Proportion of efficient monitoring and supervision mechanisms in place countrywide. |
| DELIVERABLE |  |
| Efficient procurement and supply chain management system which incorporates development of training materials designed and put in place including integration of HIV screening and diagnostic facilities by the end of 2011. Training on data collection, analysis and use conducted for health personnel involved in the generation of data from the district health information system by 2011. 3. Community based health and nutritional information system put in place by end of 2012. 4. Annual planning process of comprehensive district planning in all 13 districts finalized each year from 2010 to 2012. 5. A monitoring system for the free health care programme for pregnant women and children under five developed and implemented by 2010. | Availability of Logistics Management Information Systems (LMIS) forms – inventory control cards, stock card, reports, requisitions and issue voucher ( RRIV),Daily Health Commodities Dispensing register, Reporting form for claims /returns, Gate pass Availability of Standard Operating Procedure Manual (SOP) on the integrated logistics system. Number of people trained on the logistics system design . Proportion of districts with Community Based Health and Nutrition information system . Number of Comprehensive district Health Plans finalized Availability of protocols and guidelines for monitoring Free Health Care at National, District and community levels. |

Legal Context or Basis of Relationship

Signatory to the Joint Vision as the UN’s contribution to the GoSL Agenda for Change.

Workplan and budget

Workplan

| EXPECTED outcome and indicators of performance | PLANNED ACTIVITIES | J | A | S | O | N | D | RESPONSIBLE PARTY | SOURCE OF FUNDS | PLANNED BUDGET in US$ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Harmonized procurement and distribution system that ensures uninterrupted equitable access to medicines and medical supplies to all target population . Performance indicators: The public supply chain management system in place and in line with acceptable international standards is operational at all levels. | Hire an international institution to support the process | x | x |  |  |  |  | UNICEF | MDTF/UNICEF | 350,000 |
|  | Train counterparts, policy workshops, support district annual planning process |  |  | x | x |  |  | UNICEF/ HERA | MDTF | 100,000 |
|  | Monitoring the project | x | x | x | x | x | x | UNICEF, WHO, MOHS | MDTF | 47,668 |

UNDG standard Budget

| Line # | Line description | Amount |
| --- | --- | --- |
| 1 | Supplies, commodities, equipment and transport | 0 |
| 2 | Personnel (staff, consultants, travel and training) | 0 |
| 3 | Training of counterparts | 100,000 |
| 4 | Contracts | 350,000 |
| 5 | Other Direct costs (project monitoring) | 47,668 |
| 6 | Indirect Costs (10%) | 50,000 |
| 7 | Total Received Funds (this project) | 547,668 |
| 8 | Agency Earned Interest Income |  |

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.

Health Sector Support Project (HSSP) PE3 Final Report July to December 2006

Analysis and recommendations for Procurement and Supply Management (PSM) strengthening in Sierra Leone. Mission Report. April 20-24, 2009

Technical Report on the assessments of the Supply Chain and the Forecasting and quantification of Essential Medicines and Medical Consumables for the RCH/MOHS, Sierra Leone, May 2009

UNICEF is one of the world’s leading organizations supporting national policies, strategies and systems, procuring medicines and vaccines for children and women globally

MOHS Letter dated 25th February 2009