sECOND Six-month progress report for project

# SCHOOL REHABILITATION AND CAPACITY BUILDING FOR SCHOOL MAINTENANCE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UN-HABITAT and UNICEF |  | B: Education and Culture |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| B1-22 (a &b) School Rehabilitation and Capacity Building for School Maintenance |  | 2 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January - 30 June 2007 |  | UNDG ITF: $15,660,938 UNICEF: $ 9,029,120 UN HABITAT: $ 6,631,818 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| UNICEF & UN-HABITAT Ministry of Education/ Directorates of Education and Local Contractors |  | Basrah, Thiqar, and Missan Governorates |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| DoEs : Directorates of Education PTA: Parents and Teacher Association BoQ:Bill of Quantities MoE : Ministry of Education PM: Programme Manager PMO: Programme Management Officer HQ : Head Quarter |  | 18 months (October 2006 – March 2008) Report on budget revisions and extensions and provide the new dates. Indicate if the project has been operationally closed during the reporting period. |

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

The main objective of the programme is to increase access to primary, intermediate and secondary education for school age children (grades 1 to 12) with emphasis on rural areas and girls’ education. Secondly, to enhance the capacity of DoEs on school maintenance and school sanitation and hygiene promotion.

Immediate Objectives:

- Improvement of the physical environment of 70 schools in 3 Southern governorates, including water and sanitation facilities.

- Enhance the capacity of DoEs to undertake the maintenance of schools and promote hygiene practices.

- Reduce the number of shifts and reduce the number of students in crowded  classrooms by adding new classrooms

- Building capacity of local contractors under several categories and using local materials, which will contribute to improving the economical conditions of the local communities

- Contribute to the reduction of the number of unemployed people in local remote communities

Outputs:

Output (1)

70 schools rehabilitated in 3 Southern governorates benefiting about 35,000 school age children.

Output (2)

20 DoEs technical staff, 70 head teachers  and 140 PTA representatives of the rehabilitated schools trained on best practices in the school maintenance programme (including the use of public-private partnerships) and on the promotion of improved sanitation and hygiene practices.

Output (3)

Manual on management of school buildings and maintenance and guidelines on school sanitation and hygiene practices produced.

Outcomes:

The main outcomes as per the approved project document are as follows:

- Improved teaching learning environment for approximately 35,000 students in 70 schools;

- Strengthened capacities of DoEs technical staff in maintenance of school buildings, water and sanitation facilities and in hygiene promotion;

- Improved capacities of local contractors and young engineering professionals involved in the rehabilitation activities;

- Enhanced employment opportunities within the local communities.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq;

The project is part of the reconstruction and development programmes presented in the Joint UN-Iraq Assistance Strategy 2005 – 2007 and implemented by the UN agencies through national partners and counterparts and via the Cluster B approach.

- UN Millennium Development Goals;

Reference to the project main objective and immediate objectives (see above), the project plans to achieve Universal Primary Education indicated in goals 2 and 3 in the Millennium Development Goals, which aim, by 2015, to have all children in primary schools, and provide girls with the same educational opportunities as boys.

- Joint Needs Assessment;

Following the 2003 Needs Assessment and the 2004 Living Conditions Survey, the Unmet Basic Needs (UBN) study which was jointly launched by the Ministry of Planning and Development Cooperation and UNDP shows that a high percentage of people in Iraq live under various levels of poverty and human deprivation despite the huge economic and natural resources of the country. This study with the Rapid Needs Assessment (RNA) of recently Internally Displaced Persons in Kurdistan Region has highlighted the priority needs as the following:

  - Shelter

  - Access to public food and rations

  - Healthcare

  - Provision of Water and Sanitation facilities

  - Provision of Electricity and Fuel

- Iraqi National Development Strategy;

NDS for 2005-2007 emphasized on improving quality of life by developing required policies based on current and future needs. Achieving definite aims till 2015 requires hard efforts and developed policies in all life aspects such as economic, social, environmental and educational. The project is in line with the NDS goal 2 as illustrated hereunder,

Goal (2): Achieve primary education for all

Everyone will have the opportunity for education and necessary skills to be able to enter world economy and have citizen rights and obligations. Educational levels are measured based on rates in the primary level and postgraduate level. According to living standards surveys, illiteracy is wide spread in Iraq; 39% in rural areas, 22% of adults didn’t join schools and 9% in secondary schools which is the highest educational level for them.

(Target) (4)

Dialogue continues with the Ministry of Education (MoE) regarding a rapid assessment of the impact of insecurity on school attendance after , UNICEF reported that the number of children not attending school continues to be of concern. The education sub-cluster has been making an essential contribution to the long term goal through its programmes to undertake the physical rehabilitation of schools as well as to provide essential education and recreation materials.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

The project is being implemented largely through:

- The project is implemented by UN-HABITAT and UNICEF. The two agencies are regularly sharing information on prices of materials and labour, both agencies are able to better monitor cost effectiveness of project interventions. The agencies are also planning joint capacity building initiatives related to school building maintenance management and hygiene promotion.

- Local contractors in order to maximize the employment impact of the project

- Local consultants/engineers who are engaged to undertake the technical assessments and scope of work, prepare bidding process documents, undertake the tenders opening process, and supervise, follow up and control the rehabilitation works according to tender based requirements including: quality of work and compliance with technical specifications, quantities according to the approved BOQ, and the work time schedule.

- Representatives of the Directorates of Education (DoE), who are conducting field visits in collaboration with UN-HABITAT and UNICEF consultant engineers in each governorate. The MoE and the local Education Directorates continue to be involved in all procedures relating to identification of project locations, bid opening and supervision of the works.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

Total budget of the funded project is US$ 9,029,119 of which US $7103187.8 is committed and US $3,809,206.7 disbursed.

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

The project is being implemented according to plan, and as such, there are no variations from the planned budget.

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

US $7,103,187.8 is committed in 10 budget categories, of which US $3,809,206.7 has already been disbursed.

| CATEGORY | UNDG ITF approved budget (US$) | Actual COST | Percentage of Approved |
| --- | --- | --- | --- |
| 1. Personnel including staff and consultants | 1,182,304 | 567,988.1 | 48% |
| 2. Contracts including companies, professional services, grants | 12,652,000 | 7,220,156.5 | 57% |
| 3. Training | 300,000 | 92,158.8 | 31% |
| 4. Transport |  |  |  |
| 5. Supplies and commodities | 15,000 | 0 |  |
| 6. Equipment | 5,000 | 0 |  |
| 7. Travel | 570,427 | 564,403.2 | 99% |
| 8. Security |  |  |  |
| 9. Miscellaneous |  |  |  |
| 10. Agency Management Support | 1,029,179.2 | 1,029,179.2 | 100% |
| Total Expenditure | 15,660,937 | 9,473,885.8 | 60% |

NOTE: The actual expenditure figures in the table show the joint expenditures of both   agencies (UNICEF/UNHABITAT)

  - Indicate other funding sources, if applicable.

N/A

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

No budget revisions have been requested for this project.

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

For UN-HABITAT, the total number of national operations staff is 17, distributed according to the operations' needs as follows:

- Two senior engineers and one database expert (in Amman office).

- Four consultant engineers (in Basrah Communication Base)

- Four consultant engineers (in Nassiriyah Communication Base)

- Five consultant engineers (in Missan Communication Base)

While for UNICEF, a total of 27 persons are currently working on the project in the field, as follows:

- Eight engineers inside Iraq

- Thirteen facilitators inside Iraq

- Four national staff inside Iraq

- Two national Officers in Amman

  - International Staff: Provide details on the number and type (operation/programme)

The total number of international operations staff is as follows:

- Programme Manager (UN HABITAT)

- Rehabilitation Expert (UN HABIBAT)

- Programme Management Officer (UN HABITAT)

- Rehabilitation Specialist (UNICEF)

- Education Specialist (UNICEF)

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

- National consultants of the two agencies (UNICEF and UN-HABITAT), with the active participation of DoEs, carry out a detailed assessment of the facility to be rehabilitated. An assessment report is prepared and forms the basis for discussion among all stakeholders to agree on the priority needs. As soon as consensus is reached on the broad scope of the rehabilitation works, Bills of Quantities are prepared by the consultants who set out in precise detail, the scope of work and specifications.

- The Bills of Quantities and the technical specifications are sent to UN-HABITAT and UNICEF Offices for review by Rehabilitation Divisions. Once approved, the agencies authorize the preparation of the tender documents.

- The two agencies maintain a register of - now over 700 - Iraqi Contractors with different specialties and grades in the three targeted governorates. A comprehensive contractors database was prepared based on a selection criteria, which is used as a decision support tool to select the bidders. Normally, between 10 and 20 Iraqi contractors are invited to tender for each rehabilitation contract depending on the estimated amount of each contract.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

- The tender evaluation process incorporates a system of checks and balances with a clear segregation of functions. Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate Tender Evaluation Committee. A separate technical team based in Erbil prepares the agency estimated cost for each contract, using a specifically designed database system, which generates priced BOQs using monthly updated market prices. The process occasionally based on comparison with market survey done by other UN Agencies.

- For contracts, which exceed $150,000 the tender evaluation report is subject to review and approval by the Local Contracts Committee in the Headquarters / Nairobi and the UN Office in Nairobi (UNON)/ Procurement, Travel and Shipping Section .Contracts less than $150,000 are reviewed and approved by the Programme Manager under the terms of a delegation of authority.

- As for UNICEF, bidding evaluation is submitted to a Contract Review Committee (CRC) who after vetting and evaluation submits recommendations to the Special representative of UNICEF for authorisation.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

- The rehabilitation works are supervised and monitored by Iraqi national consultants and facilitators. The progress of works monitored and approved through time-series photographs, daily briefings from the consultants, videos and telecommunication and laboratory test reports for quality control of construction materials. In addition, an initial handing over certificate is issued upon completion and receipt of the rehabilitated facility by the MoE Directorates.

- Interim payments are only released to the contractor upon accepting the work progress and quality by the Senior Engineer and the Rehabilitation Expert in Amman Office, certified by PMO and then approved by PM as a final stage before being sent to HQ for processing.

- Liquidated damages apply for any unjustified work delay and violation of the contract period.

- During the maintenance period, constant surveillance of the implemented work is carried out by the consultants and facilitators to guarantee implementation sustainability and defects repair. This is normally enhanced by interviews with local authority staff and beneficiaries for addressing their remarks on the work and responding to any justified request before the final handing over takes place in order to ensure the public good reputation and impressions of the agency achievements. All contracts incorporate a defects liability clause so that any defects, which emerge after completion are repaired by the contractor.

- Before the rehabilitated school facility is finally accepted, a final inspection is undertaken by an Acceptance Committee, which comprises representatives of the local authority, the beneficiaries, the relevant department of the Government and UN-HABITAT and UNICEF staff and consultants. The final payment is not released until the Acceptance Committee certifies that all work has been satisfactorily completed.

  - Report on any assessments, evaluations or studies undertaken.

UN-HABITAT –Iraq programme has conducted a review of the procurement processes and the operations modality through a qualified procurement expert from UNICEF NYHQ between in June 2007, where a thorough review was done and recommendations were put forward to strengthen and enhance the procurement processes. UNICEF from its part has been reviewing its processes to incorporate lessons learned and tune them to the reality on the ground.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

- During the reporting period, comprehensive rehabilitation/extension of 55 schools (28 by UNHABITAT and 27 by UNICEF) were completed  in Wasit, Salaheldin, Muthanna, Kirkuk, Ninewa, Baghdad, Diala and Dohuk governorates, benefiting 34,349 students, while 76 schools (31 by UN-HABITAT and 45 by UNICEF) are still at various stages of rehabilitation. In addition, rehabilitation of 26 schools is in the bidding and evaluation process.

- UN-HABITAT and UNICEF in close coordination with MOE have arranged a two day workshop on Asset Management and Maintenance of School Buildings in Iraq in April 2007 in Amman. The participants included 18 Engineers from Central and Southern governorates led by the Director General of School Buildings, 6 engineers from the Kurdistan Region led by the Director General of Planning of the MoE and 9 participants from UN-HABITAT and UNICEF.

- The booklet/manual for hygiene promotion in schools was prepared and printed.

  - Report on progress made towards the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period;

The project is contributing to the increase in enrolment for girls and boys while also contributing to the reduction of crowding in schools by adding a number of classrooms in crowded schools; in addition, the rehabilitation of water and sanitation facilities has encouraged families to send their girls to school.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

55 schools were comprehensively rehabilitated benefiting 34,349 students; (UNHABITAT 16,500 students and UNICEF 17,849 students).

55 schools with Water and Sanitation facilities rehabilitated

136 (UNICEF) schools annexed with an additional one classroom each

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

The project is being implemented in a smooth manner with no recognized delays .However, potential delay causes could be outlined as follows:

    - Local curfews due to insecurity

    - Employment difficulties due to unstable situation and interior conflicts.

    - US Dollar retrogression against local currency

    - Interim payments possible delay.

Lessons learned: Improving learning teaching environment is one of the most important factors affecting enrolment rates, dropouts and learning achievements.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

This work is done in collaboration with the engineers from the Directorates of Education in each governorate. MoE and the local Education Directorates continue to be involved in all procedures relating to identification of project locations, bid opening and supervision of the works. This has helped to ensure transparency and greater sense of responsibility and commitment as well as sustainability of the project after its completion.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

- Although security has not yet improved, the work progress is generally acceptable and most of the stoppages if any have not violated the implementation period planned for the project and delays could be compensated via shifting the planned completion dates to several days ahead.

- The schools were selected on gender equality basis with special focus on Girls’ schools to mitigate the dropout rates for girls.

- The project in general was planned to achieve human rights through fulfilling the Millennium Development Goals 2 & 3, stated that by 2015 :

- all children will be in primary schools

- girls will have the same educational opportunities as boys

- The project has so far achieved the concept of increasing the capacity of local small contractors via awarding the works to 49 contractors during the reporting period and still three contracts are waiting to be awarded soon. The project has so far attained an employment generation of 39,574 persons-days.

- Through the expected hygiene promotion in schools, the project will contribute to improve the environment since part of the hygiene guidelines were designed to increase environmental awareness as well.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2007.

- The rehabilitation works for the remaining 82 out of the 160 schools, where rehabilitation processes will be completed in the coming few months to achieve 95% of the project progress, including the rehabilitation and upgrading of water and sanitation facilities.

- Guidelines booklet on the adaptation of hygiene practices in schools has been produced by UNICEF and will be distributed to all the targeted schools, while training of teachers on school sanitation and hygiene practices is planned in the coming six months in coordination between UNICEF and UN-HABITAT focusing on the schools rehabilitated by the two agencies as a pilot project, and expanding to other schools based on the evaluation of the results of the pilot project.

- The booklet/manual on "School Maintenance Guidelines" will be prepared during the coming six months. In close cooperation with the technical committees formed by MOE in Baghdad and Kurdistan Region, while the two agencies will compile information and prepare the first draft on school maintenance in coordination with the DG of school building.