Sixth Six-month progress report for project

Governance in Support of Employment Creation (GEC)

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNOPS ESCWA |  | C – Governance and Human Development |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| C10-06 Governance in Support of Employment Creation (GEC) |  | 2 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 |  | US$ 4,126,284 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| Participating UN Organizations Other International Organizations National (government, private, NGOs & others) ESCWA Ministry of Labour and Social Affairs (MoLSA) Ministry of Municipalities and Public Works (MoMPW) Municipalities of Shat Al Arab, Al Khaseeb, Al Faw Basra Provincial Council |  | Specify in which governorate, region and/or national coverage/scope of the project Basra, Districts: Al Faw, Shat Al Arab, Al Khaseeb |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| List the main abbreviations and acronyms that are used in the report. Ministry of Labour and Social Affairs - MoLSA Ministry of Municipalities and Public Works - MoMPW Provincial Council – PC Governorate Steering Committee – GSC Municipal Steering Committee – MSC Vocational Training – VT Mobile Vocational Training Units - MVTU UNOPS Iraq Operations Center – IQOC Governance in Support of Employment Creation –GEC Bills of Quantities – BOQ Memorandum of Agreement – MoA International Training Centre of International Labour Organisation - ICT-ILO Terms of Reference – TOR Request for Proposal – RFP Multipurpose Technology Community Centres - MTCC |  | Provide the programme/project duration. Report on budget revisions and extensions and provide the new dates. Indicate if the project has been operationally closed during the reporting period. 18 months The budget revision was approved on the 30th May 2007. |

# NARRATIVE REPORT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

The overall objective of the project is to contribute to poverty reduction and sustainable livelihoods through optimal employment generation in all sectors at the local level, in particular:

Objective 1 - Promote broad participation, including for example the optimal participation of women, in decision-making processes for public works, rehabilitation and short term employment at the Municipal level

This component of the project aims at building capacity of the 3 selected municipalities in Basra governorate to effectively plan and manage rehabilitation and development activities with a special focus on employment generation and social protection. This component will provide intensive training and study tours to the municipalities and employees of Labour Offices, MoLSA and PC.

In addition, it will introduce the concept of community participation mechanism at the municipal level and establish Municipal Steering Committees consist of representatives of the communities and local authorities. Technical Advisers will be appointed to the municipalities and communities to assist in preparation of the municipal development plans which will be further priorities and partially funded by the project.

Objective 2 - Optimise employment opportunities through the rehabilitation and reconstruction of social and economic infrastructure, using an employment-intensive approach

This component will contribute to the short term employment creation through quick impact public works schemes and infrastructure rehabilitation. In the first phase the project will fund quick impact public works and create around 16 000 labour days in each of the selected municipalities. In the second phase, based on the municipal development plans, the project will fund infrastructure rehabilitation works identified and prioritized by the Municipal Steering Committees.

Objective 3 - Support decentralized policies for a social safety net through a pilot phase in the Governorate of Basra

In close collaboration with MoLSA, UNOPS project will support the existing Safety Nets Programme and include its beneficiaries into small business development activities and provide short term employment support.

Objective 4 - Contribute to long term employment creation through support to income-generation activities

This component covers income generation activities, including vocational training and support to small business development in order to enhance long term employment opportunities. Vocational Training Mobile Units and tool kits will be purchased and 6 different types of vocational training provided. The project will provide micro grants, tool kits and training for small business, in particular the most vulnerable groups.

Project outputs:

Output

1.1 Six Municipal Steering Committees established in three Districts of Basra Governorate

1.2 One Governorate Steering Committee established in Basra Governorate within the existing Provincial Council Reconstruction and Development Committee

1.3 Seven Technical Units set up in 3 Districts and Basra Governorate to support the Municipal and Governorate Steering Committees

1.4 Municipal and Governorate staff as well as Steering Committee staff trained in territorial and conflict management techniques

1.5 Established and operative Temporary Income Assistance Fund

1.6 Indicator to measure the participation of women in the municipal planning boards and steering committees

2.1 Establishment of four Multipurpose Technology Community Centres (implemented by ESCWA);

2.2 Drafted and implemented rehabilitation and development plans

2.3 Refurbished municipal public infrastructure

2.4 Establishment of Local Development Fund to support community infrastructure projects

2.5 Temporary Income for Labourers through the provision of up to US$ 250,000

3.1 Established safety nets through implementation of the Safety Net Fund

3.2 Income generating activities made available and provided to the most vulnerable groups

4.1 Establishment of Rural Recovery Fund specifically designed and set-up to provide support for farming activities.

4.2 Small Business Support Fund developed to support income generation activities.

4.3 400 small farmers provided with support and to benefit from the rural recovery fund and tool kits

4.4 100 small businesses who will have been assisted through a grants scheme

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The project has been developed within the framework of UN Cluster C (Governance and Human Development) and contributes to the Programme goal 1 to “SUPPORT ECONOMIC AND HUMAN DEVELOPMENT AND SUSTAINABLE MANAGEMENT OF NATURAL RESOURCES” under the outcome “ENABLING ENVIRONMENT FOR SUSTAINABLE EMPLOYMENT OPPORTUNITIES AND SOCIAL PROTECTION FOR ALL.”

The proposal is consistent with the Basra Provincial Development Strategy, in particular the Objectives: 1) Seeking to achieve the comprehensive economic development and 2) Completing and developing the infrastructure

As the main objective of the project is to reduce the levels of vulnerability through employment creation, it will contribute to the aims of MDG 1, which aims at eradicating extreme poverty and hunger.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

Implementation level involves:

1)      Municipalities – who are a part of Local Government structure under Provincial Council

2)      Labor Offices - who are under the Ministry of Labor and Social Affairs

3)      UNOPS / ESCWA staff

4)      UNOPS / ESCWA contractors

Roles and Responsibilities of each partner:

1.	UNOPS, as the executing agency will have the overall responsibility for the implementation of the project and supervision of the implementing partners and contractors. In particular, UNOPS will:

- Set up and participate in decision-making committees envisioned by the project;

- Approve operational sub-plans like, but not limited to, procurement plans, employment creation plans, payment schedules;

- Recruit staff and consultants to work with local partners;

- Organize all training activities and technical assistance to local partners, as required;

- Do procurement;

- Carry out internal monitoring of project’s achievements

- Organize external independent reporting of project’s achievements;

- Be responsible for financial management of the grants;

- Be responsible for substantive narrative and financial reporting to the donor.

2.	ESCWA will be an associated agency and will be responsible for implementation of one of the components of the project – establishment of Multipurpose Technology Community Centres. This involves:

- Preparing a final model for MTCCs (ToRs, staffing, management) in up to 4 locations, depending on results of the project Inception Workshop.

- Set up MTCCs, to be under the managerial responsibility of MoLSA, as agreed with local partners in identified locations, by providing basic equipment and selecting staff.

- Train trainers on skills needed to provide range of services envisioned by project partners to be made available to small entrepreneurs through the MTCCs

- Train MTCCs staff by trainers previously trained.

- Make available all training curricula developed for the project to other project partners.

- Ensure that MTCCs provide the range of services agreed upon with project partners during Inception Workshop, including, but not limited to: screening of applicants for micro-capital assistance, business referral system, business development proposal support;

- Be responsible for financial management of the MTCC component, except where agreed otherwise with UNOPS (see Inter-Agency Agreement);

- Providing regular reports to UNOPS on achievements of MTCC component outputs, as per donor reporting schedule;

3.	The main national counterparts are the Ministry of Labor and Social Affairs, Ministry of Municipalities and Public Works and Basra Provincial Council. They have the oversight of the project and undertake verification and monitoring function. Representatives of both ministries are members of the Basra Steering Committee and are thus involved in exercising monitoring and verificating roles in its implementation. In details, their roles is as follows:

a) MoLSA

- Assign staff as members of planned decision-making bodies (Steering Committees);

- Contribute office space – local Labor Offices;

- Provide facilities and staff for the set-up of MTCCs as per ToRs agreed during Inception Workshop

- Contribute staff as vocational trainers to conduct vocational trining activities;

- Approve technical specifications for Vocational Training Units and Tool Kits

- Provide quality assurance spot checks and monitoring to the project

b)	MoMPW

- Assign staff as members of planned decision-making bodies (Steering Committees);

- Approve technical specifications for tools and public works schemes;

- Provide quality assurance spot checks and monitoring of the related activities;

c)	Basra Provincial Council

- Assign staff as members of planned decision-making bodies (Steering Committees);

- Provide support to the municipalities in strategic planning and implementation of municipal plans;

- Provide quality assurance spot checks and monitoring of the related activities;

d)	Municipalities: Al Khaseeb district, Al Faw district, Shat Al Arab district

- Conducting needs assessments

- Establishing Municipal Planning groups

- Developing municipalities priority lists / development plans

- Preparing implementation plans for various components (public works, infrastructure projects, vocational trainings) as identified in the plans

- Preparing technical documentation for the selected infrastructure projects

- Preparing public works schemes

- Supervision of contractors for public works and infrastructure projects

- Identification of beneficiaries in accordance with the generic criteria

- Assigning  municipality staff  to work full time for the project

- Identification training needs and beneficiaries for the capacity building activities

- Reporting on progress to UNOPS and Steering Committee (under MoAs)

4.	In addition UNOPS outsourced an International Monitoring Agent who will provide monitoring and due diligence services to the project. Its duty is to conduct independent monitoring of the following activities of the project:

- Public works

- Infrastructure rehabilitation

- Beneficiaris pre-selection

- Vocational training

- Distribution of microgrants

- Repayment of microgrants

- Provide scheduled monitoring reports to UNOPS as per agreed timeline

- Provide adhoc monitoring reports to UNOPS on a need basis

Coordination Mechanisms:

The following temporary bodies are being established to implement the project:

1)	Governorate Steering Committee (GSC)

- It will composed of representatives from UNOPS, MoLSA, MoMPW, Basra PC, Al Khaseeb district, Al Faw district, Shat Al Arab district. MoLSA will Chair the GSC.

- The main functions of the GSC will be:

  - general oversight of the project and take strategic decisions, e.g. approval of the selection criteria, approval of substantive revisions of the project;

  - monitor progress of the project and approve quarterly reports, training plans, etc.;

  - meet on quarterly basis.

  - quality assurance and spot checks of project activities.

2)	Municipal Steering Committees (MSC)

- It will composed:

  - 10 community representatives in each sub-district will be selected

  - Each sub-district community steering group will assign 2 representatives (preferably 1 woman and 1 man) to work with the Municipality in the Municipal Steering Committee

  - Sub-district groups will consist of: 2 farmers, 1 religious man, 1 doctor/teacher, 1 engineer, 2 IDPs/returnees, 2 owners of small business, 1 disable person

- The main functions of the MSC will be:

  - propose and pre-select lists of beneficiaries

  - participate in the process of needs assessment

  - prepare municipal development plans

  - identify priority projects

  - monitor projects execution by the municipalities

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

Total budget:	USD 4,126,284

Commitment:	USD 1,219,971

Disbursement:	USD 657,652

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

By the end of April 2007 UNOPS has completed 3 major tenders. In all 3 cases the offers received from the bidders exceed the budget available significantly:

| tender | Budget available as per ITF budget | Lowest financial offers |
| --- | --- | --- |
| monitoring services, | 48,735 | 121,800 |
| training for municipalities; on the job training study visits | 50,000 126,000 | 383,255 |
| technical assistance for municipalities district consultants | 72,000 | 184,355 |

It was clear that with the current increase in prices of services and goods in Iraq it would not be possible to deliver all outputs within the approved budget. Since the above mentioned contracts were crucial to start the activities on the ground in Basra, UNOPS would not be able to carry on the activities unless the funds were made available through a budget revision.

GEC project was developed in 2004 and subsequently the budget was prepared and submitted for Cluster review in November 2004. The project then was in the pipeline until the final approval by the Steering Committee in July 2006. The cost estimation used for the budget has never been revised and updated therefore it does not reflect prices fluctuations and the current situation on the market.

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

The amounts provided below constitute the expenditures of IQOC and do not include the expenditure of UNOPS HQ.

| Budget Category | budget | Commitment | Disbursement |
| --- | --- | --- | --- |
| Personnel | 849,480 | 354,712.00 | 258,073 |
| Contracts | 2,493,322 | 428,991.00 | 180,068 |
| Training | 276,000 | 245,261.00 | 55,657 |
| Equipment | 32,000 | - | - |
| Supplies and Commodities | 0 | 7,000.00 |  |
| Transport | 0 | - |  |
| Travel | 107,972 | 62,015 | 43,353 |
| Miscellaneous | 107,500 | 60,102 | 43,531 |
| Security | 17,288 | - | - |
| Management Fee | 242,723 | 3,983 | 3,941 |

  - Indicate other funding sources, if applicable.

N/a

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

A budget revision was prepared and subsequently approved on the 30th of May 2007.

The following amendments have been introduced to the budget:

1) It was decided that output and the budget line “refurbishment of vocational training centre in Abu Al Khaseeb” (budget US$154,251) will be cancelled. Refurbishment of this vocational training centre was in plans of MNC-I C9 Economic Development as a part of the country wide programme of support to vocational centers.

A meeting was held between MoLSA, MNC-I Economic Division, Vocational Training Team and UNOPS Project Manager in Baghdad on the 12th of April 2007 in order to discuss and agree on the coordination. MNC-I was now starting a rehabilitation of VTCs country wide and they had confirmed that within the next 6 months they would rehabilitate both centres in Basra.

It was agreed during the meeting that UNOPS would focus on the mobile training and MNC-I would do the rehabilitation of Abu Al Khaseeb Centre. Thus the budget and project revision, which will now exclude rehabilitation of the Centre from the UNOPS project, has been agreed and approved by all 3 parties: MNC-1, MoLSA and UNOPS.

The amount of US$ 154,251 has been redistributed between:

- Training - US$ 100,000)

- Mobile Vocational Training Units – US$ 21,186

- Equipment – US$ 32,000

- Monitoring and Evaluation - US$ 1,065

- Training. Study tours have been cancelled. There has been only training provided for the municipalities, local authorities and representatives of communities. The amount of US$ 100,000 out of US$154,251 (previously allocated for the Abu Al Khaseeb Centre), has been added to Training.

- Monitoring and Evaluation budget line has been increased by US$ 73,065 out of which US$ 72,000 comes from the reduction in the budget line “Provision of tool kits” and the remaining US$ 1,065 from the cancelled budget line “rehabilitation of the Abu Al Khaseeb Centre”

- Provision of tool kits has been decreased by US$ 72,000 moved to Monitoring and Evaluation.

- Mobile Vocational Training Units budget line has been now increased by 21,186. This is based on the cost estimated after the first round of tendering that had to be cancelled and the market price survey.

- Equipment budget line has been introduced for a total of US$ 32,000 which is now allocated to buy extra equipment (generators and IT equipment) for the 3 municipalities so that they can run secretariats for the Municipal Steering Committees and work on the planning and development of municipal development plans.  At the moment there is no infrastructure in their offices that could allow working on the project and therefore provision of basic equipment is absolutely essential to allow them to work on the project.

7)	Supplies and commodities have been moved under contracts.

  - Project expenditures for the 1 July to 31 December 2007 period.

It is expected that with all procurement finalized by mid 2007 the commitment in the second half of the year will amount to approximately USD 1,000,000 in contracts only.

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

Project Associate, Basra (operations)

Project Associate, Amman (operations)

Socio-economic Specialist, Erbil (programme)

  - International Staff: Provide details on the number and type (operation/programme)

Project Manager, Amman (programme/operations)

Admin & Finance Manager, Amman (operations)

In addition the project’s contribution to the operational / core staff is 3% of the total budget over the duration of the project (18 months)

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

With the increasing number of incidents and deterioration in the security situation in the South UNOPS had to adopt its implementation modalities to the reality on the ground. The most important thing is to involve the local authorities into implementation and have support of both Provincial and Ministerial authorities. The number of UNOPS staff has been reduced to the minimum and most of Technical Advisors working for the project have been hired through a private company. The current implementation modality involves:

- UNOPS staff (limited to the minimum for security reason)

- Mayors Offices

- Ministry of Labour

- Private contractors

- Monitoring by an independent monitoring agent

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Standard UNOPS procurement procedures have been applied, competitive bidding process has been applied in case of all contracts awarded. Waivers have been approved it the case of the agreements with the pre-selected municipalities.

UNOPS procures goods and services in close collaboration with the Clients, Iraqi authorities, and the Beneficiaries. While the individual arrangements vary depending on the Client and the specific project requirements, the general modalities are:

- Requirements

  - Upon request of Client, and together with the Iraqi counterparts, identify the goods and services for UNOPS to provide or contract.

  - Preparation of detailed specifications of equipment and services and work plan, by UNOPS, based on input and with the support from the Client, the Iraqi authorities and the beneficiaries.

- Short-listing

- UNOPS has developed and maintains a database of known suppliers and service providers in Iraq (incl. performance assessment, capacity, registration in Iraq, etc.) and a roster of registered experts.

- Qualified and potentially interested vendors in the area can also be drawn from the local authority’s relevant company registration offices.

- Alternatively, interested companies can requested to submit their profiles in response to an Expression of Interest ad published in the Iraqi and/or international media (incl. internet).

- Where necessary and relevant, information on companies/vendors can also be drawn from other UN agencies and entities operating in Iraq.

- The short-list of companies selected to be included in the procurement exercise requires approval by the Regional Director, confirming that all relevant sources of information have been utilized for compiling the list.

- Tendering Process

  - UNOPS issues an Invitation to Bid/Request for Proposal to all short-listed companies, requesting them to submit an Offer/Proposal in line with the specific requirements. The document also stipulates the exact process of submission, receipt, opening, and evaluation of bids and it informs on the nature of the contract/purchase order the selected bid could result in.

  - Requests for clarification received from potential bidders are responded to by UNOPS, if necessary upon consultation with the Client, relevant Iraqi authorities, and/or Beneficiaries.

  - After expiration of the submission deadline, all Bids received are opened by a UNOPS Bid Opening Committee. The opening ceremony is open to observers from the Client, relevant Iraqi authorities, the Beneficiaries, as well as for companies participating in the tender.

  - The evaluation follows UNOPS standard procedure, varying on procurement type and value, and should result in a recommendation for award of contract to the lowest, compliant bid. This recommendation requires approval by the relevant authority within UNOPS.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Monitoring is done at 3 levels:

- UNOPS staff on the ground

- Involvement of MoLSA and Provincial Councils personnel through spot checks and quality assurance activities

- UNOPS has contracted and independent monitoring company. The selected institution has been workign on the ground since May 2007 and developed monitoring tools and plan specific to this project.

The Independent Monitoring Agent Team Structure

UNOPS have prepared a proposed Project Structure, identifying the task and responsibilities for each project personnel taken in to consideration the Work Load with regard to total number of working days and field trips over the project period.

Detailed scope of work

Working closely with UNOPS and the municipal authorities in the Basra governorate, the selected institution provides monitoring services to the project as follows:

Public Works

Technical Officer Infrastructure and Public Works / National

- Quality assurance checks for the procurement of tools used for public works

- Verification of the process of identifying workers done by Municipalities in cooperation with Labour Office.

- Monitor workers registration process by the municipalities

- Monitor and quality assurance spot checks during the public works on project sites

- Monitor attendance of workers in accordance with the approved list of beneficiaries and check on the attendance list maintained by the municipalities

- Verification of payment list in accordance with the approved list of beneficiaries

- Monitor of payments sites administered by the municipalities and agreed payment procedures based on the agreed payment schedule

- Monthly monitoring reports (work progress, quality assurance, payments, attendance)

Infrastructure Rehabilitation

Technical Officer Infrastructure and Public Works / National

- Based on the procurement plan prepare and discuss with the project partners a monitoring plan

- Conduct regular checks and apply quality assurance measures during the work of the contractors on the infrastructure project sites

- Monitor time management of the infrastructure projects as compared to the work plan and project scheduling agreed with the contractors

- Monitor infrastructure project cost management

- Monitor infrastructure project quality assurance procedures applied by the contractors and report back to UNOPS on the quality of the works

- Establish infrastructure project risk management plan and the system of early warning system on possible mismanagement by contractors

- Monitor involvement of the municipalities in the procurement at the stages when their inputs are required (BOQ, technical designs and specifications, etc.)

- Certify completion of works in conformity with initial specifications

- Report to UNOPS on safety on the workplace provided by contractors on the infrastructure projects sites.

Support to income generation activities, including vocational training

M & E Coordinator / Grants Scheme / Capacity Building

Technical Officer Vocational Training / National

- Verification of the identification process of the beneficiaries pre-selected by Municipal Steering Committees for small grants support in accordance with the agreed criteria

- Prepare and submit to UNOPS a verification report on the beneficiaries’ selection process

- Monitor the process of beneficiaries’ enrolment for the training provided by Multipurpose Technology Centres and the training activities

- Monitor the process of the business plans and application evaluation and the final selection of the beneficiaries of the small grants assistance

- Prepare and submit to UNOPS monitoring report on the selection process

- Monitor vocational training activities and report on quality of services provided by the contractors and Labour Office trainers

- Prepare and submit to UNOPS a monitoring report on vocational training

- Monitor delivery of the mobile vocational training units and tool kits procured by UNOPS and certify on the handover and quality of goods delivered

- Monitor distribution of small grants and tool kits to the beneficiaries

- Monitor the small business projects during their implementation and report to UNOPS on the status of implementation

- Monitor and verify repayment of the grants by the beneficiaries in accordance with the terms and conditions of repayment agreed and approved by the Steering Committee

Reporting Schedule

M & E Assistant / National

Apart from the reports mentioned in the above activities, the contractor will submit the following additional reports:

- Monthly monitoring reports covering the three monitored components as per details instructions above.

- Six-monthly evaluation reports analyzing rate of project implementation and initial impact of project activities.

- Final evaluation report (to be delivered latest 2 months after completion of project) reviewing overall project achievements against planned outputs as well as impact on beneficiaries (institutions, individuals).

- Detailed ToRs for the mid-term and final evaluation exercises will be discussed with the Consultant at the beginning of contract execution so that needed preparatory work and data collection can be organized at the outset of the project.

  - Report on any assessments, evaluations or studies undertaken.

Financial and Procurement Screening of the Mayors Offices

Prior to signing the agreements with the municipalities, UNOPS, through the monitoring agent, conducted the basic screening of Mayor’s Offices examining their capacity for procurement and contracting. The results of the screening show that Mayors Offices basically have a very limited capacity as the implementation is usually done by Basra Provincial Council and Directorates (DGs) of the respective ministries. Following the screening UNOPS has decided to provide and extensive 4 weeks training for the Mayors Office on procurement, contracting and financial management and reporting prior to the commencement of the public works. The training will be provided by the Technical Assistance Company under the supervision of UNOPS staff. In addition a book keeping system needs to be put in place in all 3 municipalities.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

| Output | Result |
| --- | --- |
| 1.1 Six Municipal Steering Committees established in three Districts of Basra Governorate | Achieved |
| 1.2 One Governorate Steering Committee established in Basra Governorate within the existing Provincial Council Reconstruction and Development Committee | Achieved |
| 1.3 Seven Technical Units set up in 3 Districts and Basra Governorate to support the Municipal and Governorate Steering Committees | Under preparation |
| 1.4 Municipal and Governorate staff as well as Steering Committee staff trained in territorial and conflict management techniques | Achieved |
| 1.5 Established and operative Temporary Income Assistance Fund | Achieved |
| 1.6 Indicator to measure the participation of women in the municipal planning boards and steering committees | Achieved |
| 2.1 Establishment of four Multipurpose Technology Community Centres (implemented by ESCWA); | Under preparation |
| 2.2 Drafted and implemented rehabilitation and development plans | Under preparation |
| 2.3 Refurbished municipal public infrastructure | Not started. awaiting completion of Municipal development plans by the beneficiaries |
| 2.4 Establishment of Local Development Fund to support community infrastructure projects | Achieved |
| 2.5 Temporary Income for Labourers through the provision of up to US$ 250,000 | Prepared, starting September |
| 3.1 Established safety nets through implementation of the Safety Net Fund | Achieved |
| 3.2 Income generating activities made available and provided to the most vulnerable groups | Prepared, awaiting completion of Municipal development plans by the beneficiaries |
| 4.1 Establishment of Rural Recovery Fund specifically designed and set-up to provide support for farming activities. | Prepared, awaiting completion of Municipal development plans by the beneficiaries |
| 4.2 Small Business Support Fund developed to support income generation activities. | Under preparation |
| 4.3 400 small farmers provided with support and to benefit from the rural recovery fund and tool kits | Under preparation |
| 4.4 100 small businesses who will have been assisted through a grants scheme | Under preparation |

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

N/a

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Objective 1 - Promote broad participation, including for example the optimal participation of women, in decision-making processes for public works, rehabilitation and short term employment at the Municipal level

Fully achieved (100%)

Municipal Steering Committees have been established and carried on their work in all 3 districts. Each MSC consist of 10 people out of which 2 are women. 8 people from each MSC have received a two weeks long training on municipal planning and management. They have started work on the development of municipal economic development plans. A very good coordination mechanism has been established with the Provincial Council and the DGs of MoLSA and MoMPW through the Governorate Steering Committee.

Training on municipal planning and management for 32 participants from Shat Al Arab, Al Fao and Al Khaseeb districts conducted by International Training Centre of ILO on 25 June - 7 July 2007 in Turino, Italy. The participants were representatives of the Municipal Steering Committees and Governorate Steering Committee.

UNOPS recruited International Training Centre of International Labour Organization to provide comprehensive training program on municipal planning and management.

Objectives of the training program:

- Building the capacity of the local government and the local community in developing municipal development strategy and local economic plans ensuring the complete usage of the available local resources within the municipalities.

- Building the capacity of the municipalities in conducting need assessment studies, gathering information on the activities and programs available for vulnerable groups and individuals depending on the available local resources within the local community.

- Creating guidance and referral systems in the municipalities to support the local authorities/districts local stockholders in the design of district-wide survey instruments for the purpose of socio-economic mapping.

- Providing technical assistance in the planning and decision-making of public forums.

- Facilitating a better understanding for conflict transformation and post conflict reconstruction.

- Promoting the concept of community participation and participatory approach at the governance level.

- Enhancing the method of volunteering and building the sense of volunteer work in both levels and among the project’s stockholders.

The training modules covered:

  - Conflict transformation

  - Post-conflict local economic recovery

  - Territorial diagnosis and institutional mapping

  - Stakeholders’ and needs’ analysis

  - Stakeholder dialogue and consensus-building

  - Project Cycle Management

  - Local Employment Policies

  - Local Development Initiatives

  - Project Management Logical framework

  - Community mobilization

  - Strategic of vocational training in Iraq

  - Reality of unemployment and the strategic of employment

  - Local development strategy for 2007-2010 in Iraq

The training program was supported by various field visits to municipalities in Turin. The next step is preparation of the Municipal Development Plans to take 5 – 6 weeks and is estimated to be completed by September.

Objective 2 - Optimise employment opportunities through the rehabilitation and reconstruction of social and economic infrastructure, using an employment-intensive approach

Partially achieved (50%).

The initial plan agreed during the Inception Workshop in Erbil last year to implement garbage collection activities under the GEC project public works component had to be revisited as it had been reported to UNOPS that MoMPW would be implementing garbage collection programmes in the area.

UNOPS requested the Municipalities to prepare new plans for public works which caused a delay in the implementation and the change in the number of working days to be created but was necessary not to overlap with the activities of MoMPW.

The Municipalities have decided on the type and scope of the new public works projects. In all 3 locations public parks will be rehabilitated. The BOQs and the budgets have been prepared, reviewed and approved by UNOPS. Subsequently UNOPS has prepared the draft MoAs and workplans for public works. The basic training on public works implementation was provided to the MSCs by ICT-ILO.

Objective 3 - Support decentralized policies for a social safety net through a pilot phase in the Governorate of Basra

Partially achieved (50%)

Safety Nets Programme has already been implemented by MoLSA. Therefore, it has been agreed with MoLSA and the local authorities that US$ 200,000, previously planned for the support to the most vulnerable, will be re-allocated to the small business support fund and distributed to the beneficiaries of the Safety Nets not as social support but grants for economic activities.

Objective 4 - Contribute to long term employment creation through support to income-generation activities

Partially achieved (50%)

Vocational Training:

The MoA between UNOPS and MoLSA has been agreed upon and signed. It includes a detailed TOR for MoLSA to coordinate Mobile Vocational Training, participate in preparation of development plans, linking the project with the Social Safety Nets programme and monitoring.

The Scope of Works and specifications for equipment and tool kits for the Mobile Vocational Training Units have been discussed and agreed with MoLSA. The procurement of tool kits and the equipment have been nearly finalized and the contracts are to be issued shortly. The agreed final concept of Mobile Vocational Training Units consists of 3 mobile, fully equipped camps that will be moved around by one truck. Each camp will be equipped with the tool kits for 3 different types of training thus 9 training courses can be provided simultaneously in 3 different locations at the same time. Each camp will consist of: 1 container with tool kits and workshops, 1 air conditioned tent where the courses will take place, 1 accommodation container for trainers, 1 generator.

The training courses will commence as soon as the MSCs finalize their plans and provide the lists of beneficiaries.

Business Training:

ESCWA has completed the preparations of the project components to support business development services in the target areas in the Basrah governorate. The Ministry of Labour and Social Affairs has officially seconded 15 staff of the some of its staff for the project, who will participate in the first training on business planning and business counselling that will take place in Torino (Italy) in collaboration with the International Training Center of the ILO. The relevant logistics preparations are being finalized. The training will be the corner stone of the project, as it will improve the capacity of the MoLSA staff to screen, review, and potentially advise on improving applications for funding submitted by SME's in the targeted area for financing by the GEC project. Beyond the project, the trained MoLSA staff will become the core team of the MoLSA in the target areas for business development initiatives that are planned by the MoLSA.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

The major delays occurred due to problems with procurement and recruitment of people in Iraq.

As already described in detail in section 2.2 the delays in procurement process were caused by the budget limitations versus the increase of prices in Iraq. This affected nearly all procurement processes and forced UNOPS to revise the budget, RFPs and TORs. In the case of Mobile Training Units the whole concept had to be changed and UNOPS had to develop a new, low budget strategy for provision of mobile vocational training which, including re-negotiations with MoLSA, took some additional 3 months.

The second reason of delay was problems with recruitment. Due to the security reasons 4 Technical Advisors hired in Basra gradually resigned and at the beginning of July UNOPS had to change the strategy and go for contracting a TA company.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The key partnerships are described in sections 1.3 and 3.1.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Out of 30 members of Municipal Steering Committees, 20% are women. Out of 6 women actively working with MSCs, 4 travelled to Italy and received the training. It should be pointed out this is rather a success story as it is usually not accepted to have women travelling abroad on their own.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2007.

- Municipal Planning

Currently all 3 Municipal Steering Committees have established working groups and put together the work plans for the preparation of the municipal development strategies and local economic plans which should be drafted within 2 months after the completion of the training. Working closely with the representatives of Basra Provincial Council they are now in the process of conducting needs assessments.

- Short term employment creation – public works

In parallel UNOPS will shortly sign agreements with the Mayor’s Offices and the public works will start in September with the budget of USD 120,000 per district. This activity will be conducted in the close consultation with MoLSA Labor Offices for selection of the unemployed and the most vulnerable people from social safety nets. The implementation will be done by the Mayor’s Offices as a part of building capacity to implement labour intensive project in their respective municipalities. Training on procurement and contracting, technical assistance and on-going monitoring will be provided in order to assure the quality of the execution. The rehabilitation of public parks will be completed by December.

- Income generation activities - Mobile Vocational Training Units

A concept of mobile vocational training has been put together by UNOPS and MoLSA UNOPS has procured equipment and tool kits for the mobile units which will be delivered to Basra (Al Khaseeb Vocational Training Center). The training schedule and locations will be drawn out based on the result of the needs assessment thus the training is expected to commence by the end of October and completed before the end of the year.

4)	Income generation activities - training on business planning and business counselling

ESCWA will conduct the training on business planning and business counselling for the MoLSA staff.

Multipurpose Technology Community Centres will have been established by the end of the year and the trainign shoul dcommence, depending on the beneficiaries readniness and submission of the lists of trainees selected by the Steering Committees for the business development support.

Microgrants schemes should be identified and service provider contracted. The microgrants will not be distributed by the end of the year though as this is the last step in the process:

1. Needs Assessment and finalization of Municipal Developemtn Plans (August – September)

2. Selection of beneficiaries by MSCs and MoLSA (September)

3. Vocational Trianing (October – November)

4. Business Training / Evaluation of business plans (November – December)

5. Approval by Steering Committee and the final lists of beneficiaries (December)

6. Procurement of toll kits (December – January 2008)

7. Distribution of tool kits and microgrants (2008)

5)	Infrastructure rehabilitation

Infrastructure rehabilitation project will have been identified in the Municipal Development Plans and selected by MSC for implementation by September. BOQs, technical drawings should be prepared and procurement process to select contractors should be done by November. Unfortunately the works can not start during the winter time and there will be a need to extend the project beyond the planned duration. It is now estimated that due to the above and the previous delays in procurement the project will have to be extended by additional 4 – 5 months.