Sixth Six-month progress report for project

Provision of Logistics and GEO Support to IECI

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNAMI/UNEAD UNOPS |  | Cluster G - Electoral Support |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| G11-09 Provision of Logistics and GEO Support to IECI (Phase II of G11-08) |  | 5 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 Jan. 2007 to 30 June 2007 |  | G11-09 Total Project US $61,309,996 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| UNEAD IECI |  | 18 Governorates of Iraq |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| IECI – Independent Electoral Commission for Iraq EAD – Electoral Assistance Division GEO – Governorate Electoral Office |  | Start dates GEO Support – 24 August 2005 Logistic Support 1 September 2005 Warehouse Security 27 September 2005 Last revised end date 31st May 2007 |

# NARRATIVE REPORT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

1.1 The key immediate objectives of the programme/project  are to:

      - Establish basic office facilities and install project team in order to be able to initiate the project immediately

      - Identify appropriate contractor to provide GEO Support to the IECI for the Referendum and General Elections

      - Identify appropriate Ensure forwarders of electoral goods and ensure they are able to collect goods from the suppliers to an agreed schedule and provide on time onward transport through a regional hub to the Governorate hubs in Iraq

Logistics Phase II Extended Objectives

- Contracting of an international company to provide security to the 19 GEO W/H and a contractor W/H, which will house contingency stock

- Retrieval of Tally Sheets from the GEO level to the IECI HQ in Baghdad

The expected outcomes of the programme project  are:

The international logistics operations for both the October Referendum and December General Elections have been identified and highlighted as an area of importance and one in which support should be provided to the IECI by Cluster G. Furthermore, in a letter dated 12th of April to UNAMI, the IECI specifically highlighted the area of logistics as one in which they would be in need of assistance for future electoral purposes.

Lessons learned from the January Elections also showed that there were weaknesses in the implementation of this electoral process and that there were most pronounced at the Governorate level on. It is as a result of these evaluations that Cluster G through UNEAD, supported by its implementing partner UNOPS, have worked to develop a project to provide a GEO Support unit to help overall electoral operations at this level. This support Unit will also assist in attempting to recover unused electoral items, which was a problem identified also in relation to the January Elections

The expected outputs of the programme/project within this reporting period are:

Whilst all specific IECI support activities were completed during the previous reporting period, UNOPS will still be responsible for the safekeeping (inventory, storage, and maintenance) of the considerable assets belonging to this project and eventually their disposal in line with the client request (sale to other UN projects within Iraq and the sub-region, possible hand-over of some assets to Iraqi counterparts, etc.). UNOPS has to maintain a guarded warehouse for the safekeeping of all items.

As the project still has funds uncommitted, it is recommended by UNEAD and in line with UNCT Iraq Cluster G “Electoral Support” strategy to further extend the project duration to ensure that the UN’s core capacity to provide logistics support to the IECI can be maintained and funds will be available to cover expenditure for additional support requirements (e.g. for a Needs Assessment Mission, which is planned to take place after the electoral law has passed and a new Board of Commissioners has been appointed).

  - 1.2 Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq

The project falls under the guidelines for UN involvement in Iraq. As stated in the UN strategy document:

“Recognising the presently evolving and anticipated future circumstances leading eventually to peace and stability in Iraq, the UN system is committed to supporting the effective and efficient organisation and delivery of its humanitarian, rehabilitation, and development assistance and technical cooperation as opportunities and security conditions permit. UN assistance and technical cooperation seek to encourage, strengthen and support Iraqi authorities at all levels to exercise their leadership, managerial, co-ordination and accountability roles effectively and transparently, to empower civil society in the development of participatory processes and social capital, and to promote sound economic growth including the role of the private sector.”

The support provided by this project will relate particularly to Paragraph 7a (ii) of UN Resolution 1546 on Iraq (8 June 2004), describing the UNAMI mandate, namely: “Advise and support the Independent Electoral Commission of Iraq, as well as the Interim Government of Iraq and the Transitional National Assembly, on the process for holding elections.”

- UN Millennium Development Goals

As per the original project document, this project contributes tangentially to the achievement of MDG8 concerning the development of a global partnership for development by y providing access for the IECI to the top international quality international logistics and GEO assistance services. These project support functions assist in the creation of a stable political system in Iraq, which is essential in enabling Iraq develop in an acceptable and positive manner for all its citizens. Through such a development process, Iraq is better able to cater for its citizens, by achieving a higher standard of living and increased employment opportunities

- Joint Needs Assessment

This project is in its final phase of operational closure. While the project was originally planned to cover a needs assessment mission to BGD with the objective of identifying operational needs for a next round of elections (jointly with the IECI), political developments have delayed such process. New elections are now not expected to take place before the end of 2007 or beginning of 2008 and a joint needs assessment would be carried out as soon as details for the next electoral event emerge (e.g. what kind of elections, modalities, role of the IECI and role of the UN, etc.) and would be covered under a different project which has been developed, approved/funded and started during the reporting period Jan – Jun 2007.

- Iraqi National Development Strategy

  - 1.3 Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

UNOPS is an implementing partner for UNAMI/EAD. UNOPS had one full time Programme Officer acting as focal point and liaison, and one Operations Officer based in Baghdad, with a back-up team in Amman to deal with procurement and coordination.

IECI: IECI is an independent body having the full responsibility and authority to run elections in Iraq. Policies for efficient implementation of the elections are determined by a Board of commissioners. The IECI is additionally tasked with overseeing the actual electoral process

- Resources

Financial Resources:

  - 2.1 Provide total funds provided, disbursed and committed

A total amount of USD 61,309,996 was approved for project G11-09- Provision of Logistic and GEO Support to IECI.

The project is funded in its entirety by the UNDG ITF.

Total amount disbursed as of end of June: US 55,331,363*

Total amount committed as of end of June: US $55,863,848.45*

Total Amount available still available as of End June 2007: US $5,978,633 *

* Please note that these figures are tentative while the financial certification process is still ongoing. For certified data, please refer to the Financial Report which is due on 15 September 2007 (as per standard reporting timeline).

  - 2.2 Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

The actual spending during the reporting period is indirectly related to the project scope. The expenditures are mainly related to the provision of security services to IECI head quarter for the duration of 01 March to 31 May 2007.

  - 2.3 Explain programme/project expenditures within the 10 budget categories, including security expenditures.

See certified mid-year financial report

  - 2.4 Indicate other funding sources, if applicable.

N/A

  - 2.5 Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

A budget revision for extending the duration of the project was requested and approved several times by the funding source, the budget extensions were basically to permit remaining funds to be used for additional and related activities as requested by IECI.

The latest budget/project extension requested during the reporting period was on March 4th 2007 for a new end date for commitment 31 May 2007.

  - 2.6 Project expenditures for the 1 July to 31 December 2007 period.

The project is operationally closed as of 31 May 2007 and now in the phase of financial closure. Financial closure includes the disposal of project assets (e.g. armoured vehicles, communication and security equipment, all currently stored at a project warehouse in Erbil/Iraq). While warehouse, safekeeping and possible transfer costs for some of the items to the IHEC in BGD are expected to incur some additional expenditure for the estimated period Jul – Aug 2007, there will also be project income from the sale of other project assets to other UN programmes.

Human Resources:

  - 2.7 National Staff: Provide details on the number and type (operation/programme)

Project Associate (partially) (operation)

Warehouse Manager (for Erbil warehouse) (partially) (operation)

Driver/Security (for Erbil warehouse) (partially) (operation)

  - 2.8 International Staff: Provide details on the number and type (operation/programme)

Project manager (partially) (operation/programme)

During the first half of 2007, project staffing was reduced to core personnel in charge of following up on ongoing activities and logistics arrangements, audit preparations and project closure as well as management and disposal of project assets in Erbil.

- Methods of Operating

  - 3.1 Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

UNOPS received a request from the funding source through cluster G to provide one additional service (provision of security services to the IECI head quarters based on a pre selected vendor scenario).

  - 3.2 Provide details on the procurement procedures utilized and explain variances in standard procedures.

A waiver was approved by the UNOPS HQCPC

The provision of the security services was intended as a continuation of the same services provided by the security company (Edinburgh Risk and Security Management) which was coming to end on 28 Feb. 2007. The request for the continuation of this service was received by UNOPS on 27 February. Any delay could have resulted in demobilization/remobilization of security personnel and equipment on site and exposure of a very vulnerable Iraq partner to the UN to significant security threats. Therefore the urgency of this contract was justified through this waiver.

  - 3.3 Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

UNOPS required a written confirmation from the IHEC for the satisfactory services of the contractor. Based on such a confirmation, the contractors invoices were processed.

  - 3.4 Report on any assessments, evaluations or studies undertaken.

  - N/A

- Results

  - 4.1 Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

The original outputs of the project were achieved in the last reporting period.

The following outputs were achieved in this reporting period:

1. Provision of security services to the IECI Building for 3 months.

Activity achieved 100%.

2. Project assets are managed and disposed according to the UNOPS rules on Assets disposal. Activity achieved 50%

  - 4.2 Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

N/A

  - 4.3 Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

- The IECI building was secured by (Edinburgh Risk and Security Management) from 01 March -  31 May 2007.

- Project Assets Disposal

Sale of some of the project capital assets to UNCT Iraq members and other UN organisations working in the region.

- Four armoured vehicles were sold to UNDP/Iraq at a depreciated value of US$259,120

- Two armoured vehicles were sold to UNHCR/Iraq at a depreciated value of US$122,318

- One armoured vehicle was sold to UNDP/Programme of Assistance to the Palestinian People (PAPP) at a depreciated value of US$57,849

Some other armoured vehicles are reserved by other UN organizations, the sale process was not finalized during the reporting period.

The remaining project assets are intended to be donated to the IECI as they were originally purchased for the security provision during the electoral events of 2005.

The Lease contract of Erbil warehouse has been extended during the reporting period to accommodate the project assets.

  - 4.4 Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

N/A

  - 4.5 List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The project was open at all times to suggestions or requests on the part of the IECI and suggestions were always them into account.

  - 4.6 Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Security: The provision on security to IECI building was continued through UNOPS contract with (Edinburgh Risk and Security Management) for three months as requested by EAD and the funding source.

- Future Work Plan

  - 5.1 Summarize the projected activities up to the end of December 2007

- Sale of reserved project assets.

- Donation of remaining Project assets to IECI

- Shipment of project assets to IECI HQ in Baghdad IZ.

- Project will be operationally and financially closed during the coming reporting period. Remaining funds will be returned to the funding source.

# Footnotes

A UN Strategy for Iraq, IRFFI Meeting in Abu Dhabi, 28 February 2004, p. 14