Sixth Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| WHO |  | Cluster B :Education and Culture |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| B1-25: Strengthening school health services at Primary School level through implementation of the Health Promoting Schools |  | one |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 |  | US$ 1,757,280 received April 2007 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| - Ministry of Health, - Ministry of Education |  | All governorates |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| . COSIT Central Organization Of Information and Statistical Technology HPSI Health Promoting schools Initiative IBSP Integrated Basic services Project MDG Millennium Development Goals MOH: Ministry of Health MoE Ministry of Education MoEn Ministry of Environment PTA Parent Teacher Association UNICEF: United Nations Children Fund |  | 12 months |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

The aim of the project is to assist MoH/Iraq and MoE to strengthen the school health services at primary level through updating the health education concepts into school curriculum (in all governorates)

Main objectives of the project were to:

- Implement health promoting schools programme (life skills education and psychological first aid) implemented in 44 schools in 18 governorates (2 schools in each governorate except for Baghdad governorate 10 schools in (Karch and Rasafa).

- Increase capacity of MoH officials to take over the health promoting school initiative and continue the activity of school health screening for primary school children as part of the Strengthening Primary Heaalth Care system.

- Raise awareness among community on Health Promoting Schools initiative and the role of parent teachers association (PTA) meetings

- Hearing aids and eyeglasses provided for needy students and those with musclar skeletal abnormalities referred to specialists.

- Effective partnerships between all stakeholders including the community  to build public awareness and strengthen demand for the school health services

The expected outcomes of the program within this reporting period were:

- (100) teachers and school staff trained on health promoting school initiative in 44 schools in all governorates and MoH officials informed about health promoting school Initiative.

- School health including psychological first aid services strengthened and maintained at all levels through successful coordination approaches between schools and primary health care centers.

- screening for visual, hearing problems and Muscular-skeletal abnormalities of all students in the 150 schools at 9 governorates completed and (300) teachers trained on detection of visual ,hearing defects and Musclo- skeletal abnormalities

- Provision of eyeglasses and hearing aids to school children with visual and hearing difficulties and those with muscular skeletal abnormalities referred to specialists completed.

- Community committees established to build public awareness in demanding for school health services.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

Working in close collaboration with government counterparts at both the central and regional levels, the UNCT has committed to reinforce its support to institutional capacity-building and the provision of key basic services in addressing urgent Iraqi needs and priorities.  This realignment of UNCT Cluster activities shall remain flexible in responding to the evolving operational context within the overall strategic framework.

The implementation of the health promoting schools approach in Iraq will assist MoH and MoE in developing new school policies and guidelines, and provide teachers with the necessary support to enable them to promote health. It is expected that this will lead to an improvement in the standard of the health services and health status of school children and community through increasing their awareness about main health problems and its preventive measures. Also it will lead to increased self –esteem of children and decrease of risk taking behaviour in later life.

As a result, the program will contribute to the following UN Millennium Development Goals (MDG):

- Achieve universal primary education (MDG2)

- Promote gender equity and empower women (MDG3)

- Reducing child mortality (MDG-4)

- poverty reduction (MDG-1)

- Improve maternal health (MDG5)

The project addresses the health of students, school personnel, families and community members. Currently, the health status of school children is deteriorated due to lack of proper and periodic health care, lack of awareness on main health problems and psychosocial well being.

The project proposal is fully in line with the 2005-2007 UN Strategy for Assistance to Iraq and  conforms closely to the priorities expressed by the Iraqi Authorities during the July 2005 Donors’ conference -– embracing  education, water & sanitation and health needs and demonstrating good impact, contributing to the overall targets of reducing morbidity and mortality.

Specifically the project addresses the following clusters and  some of the relevant matrix outcomes(underlined) from the Joint UN-Iraq Assistance strategy:

| Cluster | Matrix outcomes |
| --- | --- |
| Cluster-B (Education and Culture) | To enhance access to all levels of education with special reference to disparity reduction (gender, geographic, ethnic, socio-cultural, economic and other disparities); To improve rates of retention, completion and participation at all levels of education; To improve learning outcomes at all levels of education. |
| Cluster-D (Health& Nutrition) | 50% reduction in under five and infant mortality; 15% reduction in maternal mortality; Increase access to quality health care services especially for vulnerable group and un-reached; Enhance disease prevention and control including HIV/Aids. |

Moreover this program is also in line with the Dead Sea strategic meeting held in July 2006, since this program ensures the provision of basic services and education

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

WHO continues to enjoy very close collaboration with the Ministries of Education, Health, Public Works and Municipalities, in all the Directorates of the Governorates where the project will be implemented, including the Mayoralty of Baghdad. WHO works very closely with these line Ministries, from the assessment of needy areas to the joint preparation of Bills of Quantities, handing over of site to the Contractor, supervision of the ongoing works, to final taking over of the project after successful completion of the project. It is worth noting that partners in the line Ministries are very conversant with the WHO modus operandi and have benefited from multiple capacity building opportunities in the integration of water, education and health sector programming.

WHO worked in close coordination with Ministry of health/School Health unit and Ministry of education through the national staff at WHO office in Baghdad to implement the school health screening component within the UNICEF Integrated Basic services Project B1-19 for 2005-2006. Purchasing order and the bidding process for the equipments needed for the health screening was initiated in Amman. Delivery of the equipments was done inside Iraq in coordination with the logistic staff at WHO office in Baghdad.

For successful achievement of the health and education goals, it is imperative to draw on formal and informal agreements with public and private sectors as well as the civil societies. Moreover, community participation is crucial for a successful education system in Iraq.  This entails the change of community behavior and awareness for education and school health services provided at PHC level especially after the deterioration in this service over the past few years. WHO through introducing of the health promoting schools initiatives (HPSI) in 20 schools in Baghdad and has been working with the communities in the selected areas and strengthening the parents teachers association and encouraging them in identifying their children‘s needs and priorities.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

The total project approved budget US$ 1,757,280 and this amount was received in WHO account on end of April 2007. As for the date 30 June 2007,out of  this  amount ,commitment amounted to US$ 103,370.

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

The project is in the early implementation phase

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

The total project budget approved by UNDG Trust Fund Steering Committee was US$ US$ 1,757,280

Funds were received by WHO on the 30 April 2007.This budget was allocated to cover the costs of the following component activities:

- Procurement of Supplies and commodities:	US$ 220.000

- Training and capacity building                              US$ 450.000

- Contracts:			                          US$ 787,000

- Personnel:			                          US$ 114,000

- Miscellaneous and security cost			US$ 78,000

  - Indicate other funding sources, if applicable.

- There are no other funding sources. However, additional resources were provided to support the early implementation phase  of the project, which are not included in the above mentioned budget which include logistics and administrative facilities of WHO, at this stage such as tele and videoconferencing tools which have been key to coordination and interaction with the MOH and other partners involved in the project;

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

The project is in the early implementation phase

  - Project expenditures for the 1 January to 30 June 2007 period.

- During the period between 1 January and 30 June 2007, funds committed amount at US$ 103,370.

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

- One national staff is providing technical support for the implementation of the project

  - International Staff: Provide details on the number and type (operation/programme)

- One international support at WHO/Iraq office will provide good management and coordination of the project throughout the entire implementation period

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

- The implementation of this project started after the transfer of funds to WHO in early May when schools were closing for long summer holiday. The process of implementation of interventions according to the project workplan is on going. The main interventions at this stage before the starting date of implementation of the project in early October (beginning of the new school term 2007-2008)  is the preparatory phase including, selection of schools ,formation of the questionnaire forms, orientation meeting, training and capacity building, provision of supplies and equipment which are needed for the implementation of health education and school health screening components of the project building on the previous experience of school health screening within the Integrated Basic services(IBSP) Project B1-19 with UNICEF.

WHO/Iraq continues to maintain a low profile, for obvious security reasons, to avoid any possible negative repercussions to premises and staff, in particular. In line with this policy, international staff remains based in Amman and provide guidance and support to national staff and monitors operations within Iraq. Possible short missions, security situation permitting to the lower south and North will be undertaken.

- WHO/Iraq provides also technical support to the national staff in MoH and MoE and monitors the implementation of the activities through the continuous communication with the project's focal points through video/ teleconferences.

- The Ministry of health will be the key stakeholder at the national level to ensure that the integration of school health in PHC System which will work in close co-ordination and partnership with the other line ministries such as the Ministry of Education and Ministry of Environment to endorse the schools/ communities selected for needed interventions and provide policy guidance in school health. Ministry of environment usually is informed about the environmental aspect at schools as reported by the MOEv monitoring team during their visits. The information will be circulated to all line ministries and requested for action to be taken.

- At the Governorate level, the respective Directorate will be jointly involved in the assessment, implementation and the subsequent monitoring & evaluation processes. At the central level, the establishment of steering committee which consist of members of related stake holders including the community local leaders/representative of PTAs with the responsibility to oversee the implementation of the activities, follow-up on the interventions and therefore ensure the convergence of basic services.

- The role of Ministry of Health is to integrate the work between partners and identify the role of each partner involved in the process including contractors and the organization for contract tendered for cars and goods.

Quality control at the project sites will be ensured through regular supervision by local national staff and project focal points at peripheral level that will make random visits to a statistically significant number of project sites. The Local Authority staff will be involved in every step/process and monitoring during implementation.

At the onset of the project, WHO through its monitors will have established a base line data related to the project outputs. Post completion of the project, the monitors would once again assess the outputs against the established base line data to determine the outcome of the project.

Moreover WHO has been working closely with cluster members in different thematic areas e.g. UNICEF on immunization campaigns and maternal and child health; FAO and UNIDO in food safety; and World Bank in health care financing and national health accounts. There is constant dialogue with other UN health cluster members such as WFP and UNFPA to ensure integration in the areas of malnutrition and emergency obstetric care.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Procurement of supplies and equipments such as , Audiometers, ophthalmoscopes and snell’s charts for the health screening component of the project (In process)

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

The program will be managed by the district directors supported by the UN Health Cluster (technical and logistical support). From its base in Amman, WHO national staff network in the Governorates (Erbil, Mosul, Basrah and Baghdad) will work closely with the MOH/district director through teleconferencing and direct meeting in Amman. Information flow will be streamlined for sharing with partners, planning, decision making and for advocacy purposes.

Four focal points will be appointed and each will be responsible for 4 governorates except for Baghdad focal point who will be supervising and monitoring 6 governorates. These Focal Points should work closely with the DoH on ensuring proper implementation. They have to oversee the implementation at the governorate level and should report to WHO on all activities implemented.

These focal points will report to WHO offices in the governorates mentioned above , which in turn is transmitted to Amman, the base for consolidation and for action if necessary

  - Report on any assessments, evaluations or studies undertaken.

The project is still in early implementation phase

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

(The project is still in early implementation phase)

During the specific reporting period, the focus of implementation continued to be upon the following four key outputs.

  - School health including psychological first aid services strengthened and maintained at all levels through successful coordination approaches between schools and primary health care centers.

  - MoH officials informed about health promoting school Initiative.

  - MoH health professionals trained on school health screening activities.

  - Community leaders trained on health promoting schools initiative.

The following key outputs regarding the actual field school health screening will be met after starting of implementation of the project as mentioned earlier (early October2007).

- Health screening of all students in the 150 schools at 9 governorates completed.(screening for visual, hearing problems and Muscular-skeletal abnormalities).

- Teachers trained on detection of visual ,hearing defects and Musclo- skeletal abnormalities  in 150 schools in 9 governorates involved in Health screening

- Provision of eyeglasses and hearing aids to school children with visual and hearing difficulties and those with muscular skeletal abnormalities referred to specialists completed.

- Community committees established to build public awareness in demanding for school health services.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

The project is in the early implementation phase and the process of implementation of

interventions according to the project workplan is on going.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Main activities undertaken and achievements during the period May –June 2007:

1-Technical Meeting for Members of Steering Committee from MoH, MOE and MOP on     Health Promoting Schools Project in Amman,1- 5 May 2007.

2- Procurement of supplies and equipments such as, Audiometers, ophthalmoscopes and

snell’s charts for the health screening component of the project (In process)

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

No implementation constraints were shown till now as the implementation of the actual project’s components will be starting early October. From our previous experience in implementing the school health screening component as part of the IBSP with UNICEF we faced delay in Implementation due the following contaminants which might be faced during the implementation of the current project mainly due to security situation, difficult access to some remote districts, changes in Mid term holidays and school  vacations

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

WHO is working closely with line ministries such as MOH, MoE. MoP and MOEv, international organizations such as USAID, EC and donors countries such as Japan. In addition, WHO is also working closely with other UN health cluster this includes Health and Nutrition, governance, environment, and infrastructure. This collaboration ensures coordination and avoids duplication. This is ensured during bi-weekly cluster planning meetings where there are several agencies working in the area of Education such as UNICEF, UNISCO and others. During these meeting the cluster members streamline their efforts, prioritize the country needs and ensure that all ongoing programmes are aligned with the country needs and harmonized with the government national development strategy

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

During the coming implementation phase more information will be highlighted on cross cutting issues related to the project which will be reflected from the regular school visits, the facilitators who will assess the relative levels of activities /involvement of the Parent Teacher Association (PTA) in each school, social mobilization and community participation. Assessment reports will be obtained by the facilitators which will provide WHO with valuable insight on the behaviours of the children at primary schools implementing the health promoting school Initiative and their families living in the area of project implementation.

- Future Work Plan

  - Summarize the projected activities up to the end of June 2007.

- Training of trainer workshop for MoH and MoE focal points, members of the steering   committee and central supervisors on Health promoting schools and school health screening workplan .

- Support MoH and MoE  in the implementation of the health promoting school initiative through conducting of 5 orientation workshops for head masters for the health promoting schools

- Training of health professionals, teachers and health worker on health promoting

Schools.

- Training of ( 200) teachers and health personnel working at primary health care centers on providing first aid psychological and basic mental health care for children with psychosocial problems.

-Training of 50 MoH health professionals on school health screening.

-  Advocacy among community and religious leaders through training and distribution of    educational materials and strengthening the Parent Teachers Association (PTA) meetings

# Text boxes

Report Formatting Instructions: We kindly ask that you review the instructions below and follow them in the preparation of your report:

- Do not put the narrative text into boxes as was done in the previous report and do not incorporate boxes, graphs, etc into the narrative report.

- Add additional information including charts, graphs, etc as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative

- Number all sections and paragraphs as indicated below

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.