FOURTH Six monthly progress report for project:

EMERGENCY MEDICAL OXYGEN PRODUCTION AND SUPPLY FOR IRAQ, NOW REPROGRAMED FOR EMERGENCY HUMANITARIAN RESPONSE SINCE

10 APRIL 2008

| Participating UN Organization: |  | Sector Outcome Team: |
| --- | --- | --- |
| The World Health Organization |  | Health and Nutrition |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| D2-11 Emergency Medical Oxygen production and Supply in Iraq |  | Report no: 4 |

| Reporting Period: |  | Project Budget |
| --- | --- | --- |
| 10 April – 30 June 2008 |  | US$ 2,824,760 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| Ministry of Health Iraq - Technical Affairs Directorate (TAD), - National Blood Transfusion Center (NBTC) - First Aid and Ambulance Services Center -National Center for Drug Control and Research (NCDR) |  | Initially, the project was meant to (1) supply oxygen to hospitals in Baghdad, Mosul and Kirkuk and (2) install 3 oxygen production plants in Basrah, Diwaniyah and Baghdad governorates. Since 10 April 2008, the scope of the project has been changed into emergency humanitarian response (funds reprogrammed to be used by 31 Dec 2008) |

| Abbreviations and acronyms: |  | Project Duration/closed project: |
| --- | --- | --- |
| MDG: Millennium Development Goals MOH: Ministry of Health MOI: Ministry of Industry NCDR: National Center for Drug Control and Research PSA: Pressure Swing Adsorption QC: Quality Control SOPs: Standard Operating Procedures WHO: World Health Organization |  | - Approved on 29 August 2005, the last project extension was up to 30 Nov. 2006. After this date, due to a series of difficulties encountered during the implementation, it was decided to suspend the project and return the remaining funds. - However, in April 2008, as a result of emergency needs, the MOH requested to use the funds for emergency response. The new closing date is 31 Dec. 2008. |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

The first objective of the original project (a quick impact project) was to provide medical oxygen to all hospitals in Baghdad, Mosul and Kirkuk governorates to meet their six month oxygen needs. This activity was meant to be implemented as a temporary measure, until such time the MOH finds suitable solution for long term oxygen supply system.

The second objective was to provide a reliable, sustainable and long term arrangements for an uninterrupted oxygen supply in Iraq through installation of 3 medium size oxygen production plants/units (1 in Baghdad, 1 in Basra and 1 in Diwaniyah) as a pilot project to be expanded to the entire country with government owned resources.

However, following several obstacles and constraints previously reported, with regard to the procurement and installation of the three oxygen plants, the implementation of the project was interrupted in November 2006; and WHO decided to return the remaining funds in March 2007.

Nevertheless, because of the urgent needs of essential basic emergency medicines in the country particularly in March- April 2008, the Ministry of Health strongly recommended to use the available funds for the procurement of medical supplies for emergency humanitarian response and capacity building of professionals working in emergency medical services. Based on the Ministry’s request, the Chairperson of the UNDG ITF Steering Committee approved on 10 April 2008 the revival and extension of the project implementation period with changes in project scope putting the strict condition on the project completion by 31 December 2008.

Details regarding the four main activities to be implemented under the revised project are described below.

The main development goal and immediate objectives of the reprogrammed project remain almost the same as in the initial project. These include two aspects:

- Increase access to quality health intensive care services especially for vulnerable groups and increase emergency preparedness and response capacity to deal with emergencies;

- Reduce disability and mortality, including maternal and children under 5 mortality rate caused by lack of basic emergency medicines and supplies, including oxygen and other anesthetics among patients requiring emergency attention and health care.

The new project outputs are:

- Timely response to emergencies in intensive care units through better access to needed emergency medicines and supplies;

- Improved outcomes of visits to hospital emergency units with reduced morbidity and mortality

Under the reprogrammed project there are four key activities planned as follow:

- Provision of a list of emergency medicines and supplies requested by the MOH.

- Replacement of some of the basic life support equipment/supplies in a number of ambulances

- Capacity building (training of trainers) of professionals involved in emergencies with focus on workers involved in first aid and ambulance management and blood transfusions

- Review and updating the report resulting from the nation wide survey on first aid and medical gases services which was conducted early 2006 but could not be finalized for dissemination.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The project fits well with the UN Assistance Strategy to Iraq as it would have contributed to:

- Increasing access to quality health care services especially for vulnerable groups and the un-reached

- Ensuring emergency preparedness and timely response.

- Achieving the contemplated 50% reduction in Under-5 and Infant Mortality

This project is also geared to contribute in addressing the following MDGs:

- Reduce child mortality (MDG4),

- Improve maternal health (MDG5)

- Develop global partnership for development (MDG8).

Furthermore, the project indirectly will contribute to eradicating extreme poverty (MDG1).

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

The main partner in this project is the MOH. The main departments involved are:

- The Technical Affairs Directorate (TAD) which is mainly involved in providing the list of urgent requirements for humanitarian response and in the review of the results of the survey on first aid and ambulance services which was conducted between Nov-December 2006.

- The First Aid and Ambulance Centers at central and governorate levels which are involved in the selection of candidates for training on Basic and Advanced Life Support Techniques

- The National Blood Transfusion Center which is involved in the training in emergency blood safety programme.

The National Center for Drug Control and Research will be involved for performing the quality control of the pharmaceutical products to be procured as well as Kimadia, the State Company for Medicines and Medical Appliances that will deal with their handling and distribution from Baghdad to other governorates respectively.

- Human Resources

  - National Staff: Provide details on the number and type (operation/programme)

Two national officers (one project manager and one logistician) are involved in supporting the operation and the implementation of the programme. The project manager is constantly liaising with different departments of the Ministry involved in the implementation of the project for needs identification and compilation, facilitation of the training programmes and he will also play an important role at the time of delivery of the goods.

The logistician is involved in supporting the international project manager in the review of the requests and in preparing the invitation to bid for local procurement and in facilitating the shipping of medicines delivered in Amman which have to be forwarded inside Iraq.

In addition to those two national officers, the project will be supported, time to time,  by other staff within WHO offices of Baghdad and Amman. For specific tasks, short term assignments with regards to capacity building will be awarded to individuals or to institutions to perform specific tasks, particularly in the areas of capacity building. These will be in the form of Agreements of Performance of Works (APWs) contracts.

  - International Staff: Provide details on the number and type (operation/programme)

A WHO international officer is coordinating the overall project implementation and is responsible for every day management of the project (Project manager). He is assisted by other international staff in the office on part time basis, particularly the officer responsible for follow up on Purchase orders and technical specifications of equipment and supplies.

It is important to mention that for the procurement of medicines and supplies, most of them are done through international bidding. In this context, the project is enjoying the support of international staff working in Section of Logistic Support to Countries at the Regional office in Cairo.

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

This project comprises mainly of two components: Procurement of medicines and medical supplies to respond to emergency humanitarian needs and capacity building of staff involved in emergency medical services, including staff managing ambulances and blood transfusion services.

The project is being implemented primarily by the Ministry of Health, with the technical support of WHO. Specifically the departments involved are the MOH Technical Affairs Directorate for the component related to the identification of medicines and medical supplies needs, the First Aid and Ambulance Centres and the National Blood Transfusion Centre for the component related to training and capacity building.

With regards to the procurement component, the project is being implemented in accordance with set procedures within WHO rules and regulations (see the process explained in section III.2 below) and these procedures are geared to be cost effective for the beneficiaries.

For the training, the selection of candidates is being done using set criteria to ensure the candidates with the right education background and experience are selected. In order to achieve the maximum benefit, the training on Basic and Advanced Life Support Techniques will be conducted in Arabic language and will be for a group of trainers (training of trainers) who once trained will in turn train their colleagues inside Iraq.  This is to ensure ownership and sustainability.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

WHO has well established procurement procedures. Goods are generally delivered to Baghdad under international insurance coverage. The procurement process is being carried out through the application of the international bidding process for most of the goods to be procured, based on rules and regulations which are geared to ensuring the quality, efficiency and cost effectiveness. In few cases, local procurement is applied and follows a set of clear and written procedures for bidding according to the amount involved and the delegation of authority conferred by the organisation to the WHO Representative for Iraq.

Organisation manuals providing strict guidance and procedures on invitation to bids, bids opening, bids analysis, bids review and contract award, including conditions abiding both parties (the successful bidder and the organisation) are available for international and local procurement. There are specific committees at each stage of the bidding process.  There are no variances in standard procedures.

To ensure that all goods/supplies that will be procured are of the desired quality, are properly delivered and installed as case may be and that appropriate training for application in the case of equipment usage and maintenance, the following steps are considered by WHO:

- A needs assessment is carried out to establish the requirements of the facility for which goods are to be procured.

- Extensive consultations between WHO and the concerned health facilities are held to agree on the technical specifications and to ensure they satisfy the users' needs.

- The vendors are requested to provide technical specification/data sheets for all equipment components and supplies, including description of all major features and performance specifications. These include: (1) Manufacturer and model name (2) Physical, environmental, and electrical utility requirements (i.e. steam, medical gas, vacuum requirements); and (3) Physical dimensions and weight of the unit.

- The vendors are requested to provide documentations and standards related to the Quality assurance and Quality control procedures for all supplies and equipment procured and all procured consignments are covered by insurance valid for 90 days from date of arrival to Iraq till duration of 1 year.

- For procurement of equipment the vendors are requested to provide lists for reagents, consumables, and disposables including pricing.

- Procured supplies should have a minimum 75% of maximum shelf life at date of shipment.

- WHO facilitates direct communication between vendors and end-users to ensure that manufacturer’s pre-installation requirements on the newly procured equipment are met.

- Receiving reports for consignments procured and delivered to end users in Iraq are issued, compiled, and reviewed by WHO Country Office and thereafter submitted to WHO Regional and HQ offices to acknowledge the safe receipt and satisfactory functioning of the equipment and supplies.

- One year warranty from date of arrival/installation is provided by the manufacturer for all items procured. During this period WHO field staff conduct site visits to assess the performance of the equipment provided, check any fault and malfunction, and report accordingly.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Approaches and methodologies used for monitoring the implementation of this project are similar to those used for other UNDG ITF projects.

There are focal points in the Ministry for each component of the project and the work plan of each component is discussed between WHO team and the focal points, mostly in Baghdad during the visits of the International manager. To this effect, at least three meetings were held in Baghdad involving the focal points on first aid and ambulances and the focal points from the national blood transfusion centre.

The implementation of the project is also being monitored by a team comprising of representatives from the MOH who are being supported by a WHO Team. It is also important to mention that this project as part of UNDG ITF funded projects is subject to the regular mandatory internal and external audits.

  - Report on any assessments, evaluations or studies undertaken.

The lists of medicines and medical needs for procurement were developed based on the results of an exercise of quantification of emergency medicines and medical supplies   sufficient to meet one year’s needs. Given the limited budget compared to the needs, the quantities to be procured have been prorated to the budget available

A study (survey) on first aid and medical gases services in Iraq was conducted between Nov 2005-Feb 2006 and the preliminary findings will be revisited and reviewed in the next few weeks.

Concerning the domains for training and capacity building (Basic and advanced Life Support), these have been defined on the basis of the results of the workshop on Emergency Medical Services which was held in Amman in March 2007.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

It has to be noted that the reporting period under review is for less than three months (from 10 April to 30 June 2008 where focus was put to compilation and analysis of the list of medicines and medicals supplies, its cost estimates and preparation of the documents for invitation to bid. In as much as no items had yet arrived in the country, with the exception of quadruple blood bags locally procured in May 2008 to address acute shortages, it would be premature to assess the progress on expected outcomes which were as follows:

- Timely response to emergencies in intensive care units through better access to needed emergency medicines and supplies; and

- Improved outcomes of visits to hospital emergency units with reduced morbidity and mortality

Similarly, it would also be premature to make any statement with regard to outputs although much progress was made in finalizing the preparation of the activities which will lead to these outputs as explained under section IV.3.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

Please see section IV. 1 above and Section V. 3 below

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

As earlier indicated, there are 4 activities retained in the re-programmed funds for emergency humanitarian response. These include:

- Provision of a list of emergency medicines and supplies requested by the MOH

- Replacement of some of the basic life support equipment and supplies in a number of ambulances

- Capacity building (training of trainers) on Basic and Advanced Life Support Techniques  and on identified topics in the areas of blood transfusion services

- Review and update the report on national survey on first aid and medical gases

Below is a summary of the status of implementation of each activity.

  - Provision of a list of Emergency medicines and supplies requested by MoH

The initial list of medicines and medical supplies requested by the MoH was received mid-April 2008. The ministry has prioritized anaesthetics, sutures and external fixators in that order.  The quantities to be ordered will be based on the availability of funds.

Following intensive review and close consultation between between WHO and the MOH the  specifications of each item were refined. Three separate lists of 9 anaesthetics, 42 sutures of different types and 10 types of external fixators were submitted to the regional office for international tendering. Invitations to bid (ITB) were addressed to several pre-qualified suppliers and the situation is as follow:

For the external fixators, only one supplier responded to the invitation to bid. Out of 10 items requested, only 6 were available for delivery within a period  2 to 4 months.  Moreover, due to increasing cost, of items  the quoted quantities amounted at Euro 2.7 million vs., the equivalent of Euro 1,2 million available funds for the procurement of all categories of items requested by the MOH under the re-programmed funding. As a result, the quantities were drastically reduced and the bidding process was re-launched. At the time this report is being finalised, new offers are being received.

For the procurement of sutures, the bidding process has been completed and a purchase order (PO) with a list of 42 items valued at $ 213,780 has been issued on 03 September 2008.

As to the list of anaesthetics, after intense consultations between WHO and potential suppliers to clarify the specifications and confirm the quantities requested, the bidding process has been completed and a total of 5 purchase orders valued at $ 471, 883.45 have been finalised on 18 September and the delivery period quoted by the suppliers vary from 3 to 4 months.

In addition to the above mentioned items which are being procured through international tendering, an emergency local procurement of about 11,000 quadruple blood bags valued at about $ 97,000 which are badly needed by the NBTC is being finalised. Out of the above quantity, 5,000 will be given back to the Ministry of Health in Jordan to reimburse the loan given to the Ministry of Health Iraq through WHO Iraq Office in Amman in May 2008.

- Capacity building (ToT) on professionals involved in emergencies mainly on ambulance management and blood transfusion.

Following the discussion with MoH in June 2008 in Baghdad, the ministry indicated that the training packages should focus on different categories of health professionals in ambulance management and blood transfusion services.

For the professionals managing ambulances, the focus will be put on basic and advanced Life support training which will be organised for 30 professionals (in two batches of 15 persons each) as a TOT. The training will be technically supported by Jordan General Directorate of Civil Defence and the period retained for the two back to back training sessions is from 5- 30 October, 2008.

For the professionals working at the MOH/Iraq National Blood Transfusion Center (NBTC) the suggested training package to be conducted in Amman for 15 workers (in two groups of 8 et 7 participants respectively) has been discussed between WHO team and the senior Management of the Jordan Directorate of National Center for Blood Bank which has been identified as a suitable center to carry out the training. The programme will be a training of trainers and the tentative period to conduct the said activity is November (for 8 participants) and December 2008 (for 7 participants). The programme which is being tailored to the specific needs expressed by the NBTC will include a wide range of topics covered in blood transfusion services.

- Replacement of some of the basic life support equipment/supplies in ambulances

WHO has provided technical documentations to assist the MOH/Ambulance Center in assessing the needs and in refining the technical specifications. Moreover, this activity has been further discussed with the focal points for this activity during the recent visits in Baghdad of the Project Manager in May and June 2008.

The MOH is re-assessing the requirements and it will submit a separate request in case the need still subsists.

- Review and update the report on national survey on first aid and medical gases

The process of the review of the report which was produced in April 2006 has been discussed. The report is under review for possible update before printing. However, the main challenge faced is that most of the professionals who have participated in the survey and were involved in the data collection, analysis of field data and report writing are either no longer in the same  department or are no longer working for the Ministry of Health. Some have even left the country.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

There were no major delays per se, in the programme implementation. However, it should be noted that the delays are due to the process of Invitation to Bid which can not be shortened without breaching the rules of fair competitiveness.

Lessons learnt:

The regular process of bidding for the procurement of items on international market is cumbersome and lengthy and therefore defeats and delays the timely response in emergency situations.  Pre-positioning of items for emergencies should be privileged. Furthermore, the medical supply management should be organised in a such way that there is always a buffer stock for about 2 to 3 months for use while the processes of re-ordering through the regular channel is underway.

With the globalised pharmaceutical market, it is difficult nowadays to find a supplier which has all items needed in stock at hand. In many cases, the manufacturer requires long period to be able to deliver the quantities requested.

In the future, the combination of prepositioning of items considered as emergency items, combined with the possibility of keeping sufficient buffer stock could be a measure that may mitigate the risk of shortages of medical supplies.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The main partner as earlier indicated is the Ministry of Health and its specialized departments. The MOH/Technical Affairs Directorate (TAD) which oversees the work of the First Aid and Ambulance Center as well as the work of the National Blood Transfusion Center will play an important role in ensuring the coordination of all the project activities inside Iraq at central and governorates levels.

The National Center for Drug Control and Research is another partner that will be needed to ascertain the quality of goods received before their distribution.

Coordination and collaboration with all these partners is critical for the smooth implementation of the capacity building activities.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The project is mainly focussing on procurement of emergency medical supplies and hence it does not have substantial implication and impact on most of the cross cutting issues.

However, for capacity building activities, gender balance is taken into consideration whenever possible.

In terms of employment generation, only few positions have been created through short term tasks and tuition fees allocated to the training centres in Jordan.

The prevailing security situation, if it further deteriorates, could become a threat and may possibly hinder the timely distribution of goods to the end-users in affected areas.

- Future Work Plan

Between July and December 2008, it is expected that the project implementation will be sped up with the delivery of the items procured and the launch of training activities.

The following will be the main activities during this period

- Follow up on the delivery of items ordered and follow up on bidding process of external fixators and their procurement.

- Preparation and follow up on training activities scheduled to take place between October and December 2008

- Follow up on the ongoing assessment of items that might be needed replacement in some ambulances

- Follow up on updating the report subsequent to the survey of first aid and medical gases services in Iraq

It is expected that all activities will be completed by December 2008.

# Text boxes

Report Formatting Instructions: We kindly ask that you review the instructions below and follow them in the preparation of your report:

- Do not put the narrative text into boxes as was done in the previous report and do not incorporate boxes, graphs, etc into the narrative report.

- Add additional information including charts, graphs, etc as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative

- Number all sections and paragraphs as indicated below

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.