Sixth Six-month progress report for project

D2-17: Re-establihing the Food Safety and food INDustry Capacity in Iraq

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| WHO, FAO and UNIDO |  | D: Health and Nutrition |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| D2-17: Re-establishing the Food Safety and Food Processing Industry Capacity in Iraq |  | 2 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 |  | US$6,506,112 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| WHO, FAO and UNIDO Ministry of Health, Ministry of Agriculture, Ministry of Industry, Local contractors and other Ministries involved in Food sector. |  | This is a project implemented in all governorates with a national coverage |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| MOH: Ministry of Health MOA: Ministry of Agriculture MOI: Ministry of Industry WHO: World Health Organization FAO: Food & Agriculture Organization UNIDO: United Nations Industrial Development Organization HACCP: Hazard Analysis Control Critical Point GMP: Good Manufacturing Practices GAP: Good Agriculture Practices NRI: Nutrition Research Institute DOH: Department of Health MDG: Millennium Development Goals PSC: Project Steering Committee |  | 18 months from 1 July 2006 project. The closing date is 31 January 2008. No budget revision has been requested yet. The project is still ongoing |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

The overall objective of the Food Safety Programmes, supported by three UN collaborating agencies (WHO, FAO and UNIDO) is to assist the MOH, MOA, MOI and other Ministries involved in Food safety to protect consumer’s health through addressing current weaknesses of the food safety system as well as the gaps in the food production sector. It aims at putting in place mechanisms for updating food laws and regulations, development of coordinated Food control mechanisms/services, improving the food production sector and the development of an integrated programme for prevention and control of Food borne diseases.

The main objectives are to:

- Create a coordination mechanism for a comprehensive national food safety system including the establishment and operation of a national codex committee.

- Strengthen the capacity of the national institutions and their staff in food control and improving enforcement at all levels.

- Improve the environment for the development of entrepreneurship in the food processing sector.

- Assure food safety improvement throughout food continuum.

The main expected outcomes are:

- National food safety profile (all national food control means and data) assessed.

- Laws and legislations on food safety reviewed and possibly adopted.

- National Codex Committee for Iraq (NCCI) setup and the contributions of Iraq to the work of Codex Alimentarius Commission and other food safety international forums increased.

- Food monitoring and food-borne disease surveillance enhanced and coordinated.

- Food control laboratories rehabilitated and emergency preparedness of food control system increased.

- Food Inspection and food control of imported food improved.

- Food consumed, distributed, marketed or produced are of the highest affordable standards of food safety and hygiene and food handlers committed to ensure hygiene conditions are maintained in the food processing facilities.

- HACCP principles in selected food industry facilities are in place and enforced and serve as models for the following three sectors as a pilot (dairy, fruits/vegetables and mills).

- Safe agriculture practised with less chemical contamination, including pesticides

- Consumers educated on the risks of unsafe food and its short and long term impact on health.

- Infant and maternal mortality due to food related diseases reduced

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

Strengthening food safety and Food processing industry capacities in Iraq is integral part of the UN Assistance Strategy for Iraq for 2006-2007 and is contributing to improving  basic services, poverty alleviation and economic development. The  food safety programme is part of the UN Health and Nutrition and Agriculture, Environment and Natural Resources Management Clusters’ priorities. It will contribute directly to the increased access to quality services especially for vulnerable groups and unreached. Programme outputs related to food safety which will contribute to achieving this programme outcome include provision of technical and logistical support to key laboratories and institutions at the National and regional levels. This will include the institutionalising of food safety measures covering health, agro sector and industry.

In relation to the UN Millennium development Goals (MDGs), this programme will indirectly contribute to the 15% reduction in maternal mortality and 50% reduction in under-5 and infant mortality expected outcomes, through enhancement of food borne diseases surveillance and prevention and through production of high quality and safe products in the food industries applying Good Manufacturing Practices (GMP) and HACCP principles. The project will contribute towards attainment of MDGs related to health targets through consumption of safer food and through development boosted by financial gains in food processing business. The MDGs involved include:

- Eradicate extreme poverty and hunger

- Reduce child mortality

- Improve maternal health

- Ensure environmental sustainability and

- Develop a global partnership for development

This programme is also in relation with the Iraqi National Strategy as it will contribute to improving quality of life and will promote small and medium size enterprises through creation of food industries complying with internationally accepted production and quality standards.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

The project comprises of three main components (health, agriculture and food processing industry). All these components are implemented in an integrated and coordinated manner through regular interaction between the respective UN collaborating agencies working together with the line Ministries as explained below:

- WHO is working closely with the Ministry of Health through the Nutrition Research Institute and the  Health Audit department responsible for Food Inspection related activities, the Governorate Departments of Health (DOH) in Basrah, Mosul and Erbil, local contractors selected to carry out the physical rehabilitation of the three food control laboratories. The above mentioned  partners are mainly involved in implementing the health component

- UNIDO works closely with the Ministry of Industry focussing on the rehabilitation of model food processing facilities and capacity building in the application of HACCP principles.

- FAO works closely with the Ministry of Agriculture and focusses on rehabilitating food control infrastructures at the border entry points as well as building the capacity in setting of food standards, participation in codex activities  jointly with WHO and carrying out good agriculture practices.

There is also a project Steering Committee which provides guidance during the implementation and is comprised of representatives of UN agencies and line Ministries. An international project coordinator based in WHO is also liaising on regular basis with all involved parties to ensure smooth implementation of the project.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

The total project approved budget is US$ 6,506,112. The breakdown of funds per agency is $3,015,117 (46.3 %) for WHO, $1,718,393 (26.4 %) for FAO and $ 1,772,602 (27. 3 %) for UNIDO. Funds were received by collaborating agencies in August 2006.

Out of the total budget allocated, cumulative commitments and disbursements as of 30 June 2007 amounted at US$ 1,034,452 (15.9 %) and US$ 574,158 (8.8%) respectfully.

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

So far, there is no major variation between the actual budget expenditures and the spending which were projected for the reported period.

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

The initial budget allocations breakdown within the 10 budget categories is summarized below:

- Personnel, including consultancy:			US$ 830,000

- Contracts:						US$ 2,030,000

- Training:						US$ 1,129,250

- Equipment:						US$ 1,365,000

- Supplies and commodities:				US$ 417,000

- Transport:						US$  0

- Travel:							US$ 15,000

- Miscellaneous:					US$ 174,4888

- Security:						US$ 116,325

- Agency Support Costs:				US$  399,050

Most of the expenditures incurred during the reporting period are related to training activities, procurement of equipment/supplies, contracts related to the preparation of the Bills of quantities and design drawings for the rehabilitation components as well as for personnel. It is worth mentioning that each collaborating agency has received a separate budget allocation which is managed according to each agency financial rules and regulations.

The total actual expenditures/disbursements during the reporting period amount at US$ 537,917. The breakdowns of these expenditures by category are available within each agency.

  - Indicate other funding sources, if applicable.

In addition to the resources provided through the projects funding, there are other inputs provided by the Ministries involved in the project.

For the health component, WHO Logistics and administrative facilities such as videoconferencing tools are often used to facilitate the interaction and coordination between the UN and the MOH staff including other partners involved in the project.

Also, technical support and backstopping are received from regional and headquarters offices of the three respective agencies outside the agency management support cost framework.

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

No budget revision has been requested so far.

  - Project expenditures for the 1 January 2007 up to 30 June 2007 period.

During the period between 1 January and 30 June 2007, funds committed amount at US$ 734,718 against US$ 537,917 of disbursement during the same period.

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

This project is implemented by three collaborating UN agencies. The information provided below is agency specific.

WHO employs four national technical officers. Those include:

- One national staff based in Iraq to follow up the implementation on the ground,

- One engineer who is overseeing the work related to the physical rehabilitation of the three food control laboratories of Basrah, Mosul and Erbil in coordination with the MOH engineering team,

- One biomedical engineer who is tasked to develop the specifications of lab equipment and will follow on the installation and commissioning of the procurement equipment

- One administrative and finance assistant who is assisting the International  project manager in financial and budget tracking.

WHO also regularly utilises the expertise of national consultants who were assigned to perform specific tasks under an Agreement for Performance of Works (APW) or under Special Service Agreement (SSA) contract for a very short period.

FAO employs one national technical officer based in Iraq  to follow up implementation in the field.

UNIDO is also when necessary utilising the expertise of national consultants who are assigned to perform defined tasks for a limited period.

  - International Staff: Provide details on the number and type (operation/programme)

One international technical officer based in WHO/Iraq Office in Amman is managing and coordinating on a permanent basis the overall project  implementation. He is being supported by one FAO international consultant acting as Chief Technical Advisor based in Amman at FAO/Iraq office and one UNIDO international consultant also acting as Chief Technical Adviser based in Amman at UNIDO/Iraq Office

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

The project is being primarily implemented by the line Ministries (Ministry of Health, Ministry of Agriculture and Ministry of Industry)  with the technical support of the respective UN agencies. This is to ensure ownership of the project and its continuity once the project closes. These Ministries are directly responsible for all food quality and safety issues and activities inside Iraq and are close counterparts of this project. The project is collaborating with the senior management of these institutions who form the national counterparts in implementing the project throughout Iraq. Other Ministries are also involved to a lesser extent such as the Ministry of Planning (COSQC) in particular with regard to the Codex Alimentarius Commission activities and the Ministry of Trade.

For implementing and delivering the technical and training component of the project, the UN agencies involved in this project have sought collaboration with international experts and institutions and centres of excellence specialised in capacity building related to Food safety issues. Institutions for which contacts are already established  in the region include the University of Damascus, the American University of Beirut, the Jordan Institute for Standardization and Metrology(JISM)) and the Plant Protection Laboratory of the Ministry of Agriculture-Jordan.

For the rehabilitation component within the Food Safety Project in particular the WHO supported rehabilitation of the three food control laboratories in Basra, Mosul and Erbil these projects are implemented based on the “Physical Rehabilitation Guidelines” agreed upon by the Ministry of Health, Ministry of Environment, and WHO earlier in 2004. These guidelines provide detailed information on how each stage with its micro-steps is dealt with for each WHO supported project with a physical rehabilitation component. There are sets of information and background data required by both MOH and WHO before reviewing any stage accomplishment of the rehabilitation project.

The rehabilitation process of the three food lab is being overseen by “MOH Engineering Supervisory Committee” and “WHO Engineering Team.” However, in order to ensure the accountability and monitoring system in each line ministry - which is mandatory for WHO supported projects - WHO has to follow up each stage of implementation from the central level to the project site through a network of regional and governmental engineering focal points.

Despite the fact that the security situation does not allow the high visibility profile, the UN collaborating agencies have taken all the necessary steps to ensure the smooth implementation of the Food safety through the following modalities and steps:

The project implementation work plan and its execution are planned through line ministries' focal points, UN national/international staff, and private contractors.

The Food Safety project implementation is guided by a Project Steering Committee (PSC). PSC Membership includes UN agencies and the Ministries senior manager’s staff with defined responsibilities and roles.

To ensure follow up on programs implementation, WHO has appointed “focal points” in all Governorates who are residents in these governorates. These focal points are equipped with appropriate means of logistic support including communication means to facilitate coordination and exchange of information.

For reconstruction and rehabilitation component, WHO also assigns focal points (engineers) to monitor the quality, verify the implementation progress, and report back to WHO-Iraq Office in Amman for review and approval of the financial statement. The reports should also be supported by photos and/or videos of site operations. Moreover, the information collected and submitted in such reports enabled WHO to fill some of the gaps faced by the lack of ground presence, and sustained the programme implementation capacity within the country.

The three UN collaborating agencies also use different innovative communication modus operandi such as tele-video conferencing and enhanced access to internet provided to individual national project managers and focal points to enable them to work from home when the security situation does not allow them to reach the work place.

As for funds disbursements, in most cases WHO does not release funds to the Ministries in advance but upon completion of work which has to be verified by WHO Finance and National technical staff as well as the Focal points of the subject program.

For the component administered by FAO  and implemented by the Ministry of Agriculture, FAO headquarters ensures technical and administrative assistance and supervision and the Chief Technical Advisor (CTA) is in continuous contact with MoA counterpart in Baghdad. Logistic services and secretarial help are provided by FAO Iraq office relocated to Amman.

UNIDO  and the Ministry of Industry follow procedures which are similar to those of FAO and MOA.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Each UN collaborating agency in the project has well established procurement procedures and goods are generally delivered to Baghdad under international insurance coverage.

The procurement process is being carried out through the application of the international bidding process for most of the goods to be procured, based on each collaborating agency rules and regulations which are geared to ensuring the quality, efficiency and cost effectiveness. In few cases, local procurement is applied and follows a set of clear and written down procedures.

Organisation manuals providing strict guidance and procedures on invitation to bids, bids opening, bids analysis, bids review and contract award, including conditions abiding both parties (the successful bidder and the organisation) are available for international and local procurement. There are specific committees at each stage of the bidding process.  There are no variances in standard procedures.

To ensure that all procurements and supplies are of the desired quality, properly delivered and installed, and that proper training for application, the proper usage, and maintenance are implemented, the following steps have been considered by WHO:

- A needs assessment is carried out to establish the requirements of the facility for which goods are to be procured.

- Extensive consultations between WHO and the concerned health facilities are held to agree on the technical specifications and to ensure they satisfy the users' needs.

- The vendors are requested to provide technical specification/data sheets for all equipment components and supplies, including description of all major features and performance specifications. These include: (1) Manufacturer and model name (2) Physical, environmental, and electrical utility requirements (i.e. steam, medical gas, vacuum requirements); and (3) Physical dimensions and weight of the unit.

- The vendors are requested to provide the Quality assurance and Quality control for all supplies and equipment procured and all procured consignments are covered by insurance valid for 90 days from date of arrival to Iraq till duration of 1 year.

- For procurement of laboratory equipment the vendors are requested to provide lists for reagents, consumables, and disposables including pricing.

- Procured supplies should have a minimum 75% of maximum shelf life at date of shipment.

- WHO facilitates direct communication between vendors and end-users to ensure that manufacturer’s pre-installation requirements on the newly procured equipment are met.

- Receiving reports for consignments procured and delivered to end users in Iraq are issued, compiled, and reviewed by WHO Country Office and thereafter submitted to WHO Regional and HQ offices to acknowledge the safe receipt and satisfactory functioning of the equipment and supplies.

- One year warranty from date of arrival/installation is provided by the manufacturer for all items procured. During this period WHO field staff conduct site visits to assess the performance of the equipment provided, check any fault and malfunction, and report accordingly.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

The approaches and methodologies used for monitoring the implementation of the Food Safety Project are similar to those used by each of  three UN collaborating agencies for other projects.

There is also a Project Steering Committee (PSC) comprised of senior officials from the relevant Ministries and UN agencies. The project holds its meetings every six months. During the meeting, the PSC reviews  the project implementation and provides policy guidance on the project as well as on adjustments needed to ensure that project implementation remains on track. The most recent PSC meeting was held in Amman from 1-2 May 2007 and has provided guidance for a further review and adjustment of the work plans which were developed in January 2007.

In addition to the above monitoring mechanisms, the project implementation is being monitored and assessed through the bi-weekly coordination meetings held between the international project manager and the two international consultants from FAO and UNIDO. During these meetings, activities accomplished are reviewed and plans of future activities are discussed, gaps identified and addressed.

In the case of the rehabilitation of the three food control laboratories in Erbil, Basra and Mosul, there are specific MOH and WHO Supervisory and monitoring Teams for each site project. These teams are requested to produce monthly  reports.

Also, like for any other WHO supported project involving the MOH, the review of the progress made in implementing the food safety project was made during the most recent Mid Term Joint Programme Review Mission (JPRM) which was held in December 2006. At the time of the preparation of the present report, the food safety project implementation was further reviewed during the most recent JPRM for the biennium 2007-2008 which was held from 19-23 August 2007.

It is also worth mentioned that the UNDG ITF funded projects are subject to the regular mandatory internal and external audits.

  - Report on any assessments, evaluations or studies undertaken.

During the reporting period, national and international short term consultants specialised in different topics related to Food safety have conducted various assessments. In this regard the following studies/assessments/evaluations have been completed.

FAO, in collaboration with the Ministries involved has completed the rehabilitation needs assessment for the food control facilities at the entry points. As a result of this assessment, 4 sites (Shallamcha in Basra governorate with Iran border, Rabeeah in Mosul with Syrian border , Safwan in Basrah with Kuwait and Zorbatia in Wasit with Iran border) have been selected for physical and functional rehabilitation as indicated in the section on results.

UNIDO, in collaboration with the MOI, has completed the needs assessment aimed at selecting model factories candidates for rehabilitation. For each of selected project sites an in-depth assessment for the required laboratory equipment as well as for the civil rehabilitation works, including costing for the Mosul Dairy factory are almost complete.

WHO in collaboration with the MOH governorate Departments of Health of Basra, Mosul and Erbil  have completed the assessment of rehabilitation needs of the food control laboratories in these DOHs. The assessment results were used the basis for developing the architectural design/drawings of the three food control laboratories.

Similarly, the WHO international legal consultant specialised in international Health has completed the assessment of the current status of the Public Health Law as it related to the food safety component. He has also reviewed all available food related regulations provided by the Ministry of Health. An assessment report contained recommendations on the next steps and ways forward has been produced and is under review to guide policy decision making on how the country wishes to proceed with regard to the process of reviewing the current food law and regulations.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

As overall, the implementation of the food safety project is progressing as planned and the main outcomes/outputs are being pursued with no variance in the outcomes to achieve compared to the planned outputs during the period from January to June 2007.

Most of the activities which will contribute to achieving the defined outcomes have started. These outcomes will contribute to developing a framework for updating food laws, and harmonizing Iraqi food standards with international requirements. Enforcement of the new food legislation will contribute to a better protection of Iraqi consumers. Some of the expected outcomes are interlinked and will be achieved gradually. The entire community will benefit from these outcomes. At this point, it is too early to talk about the impact of these outcomes. The situation with regard to major outcomes acted on during the reporting period is described under point 4.2 below.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

- Assessment of the National food safety profile and the review of food legislations is ongoing.

- The National Codex Committee for Iraq (NCCI) is being reactivated and Iraqis have started to participate to the work of Codex Alimentarius Commission through participation of Iraqi officials to the codex committees meetings.

- Efforts continue to be exerted in assisting the MOH to integrate and enhance the monitoring of animal and food-borne disease surveillance as part of the national Centre for Communicable Diseases (CDC) surveillance and reporting system.

- In collaboration with the relevant Ministries, food control laboratories continue to be supported and the rehabilitation and emergency preparedness with regard to food control system is ongoing, including support to food inspection services through provision of technical documentation and training.

- The work related to raising awareness of different actors in Food safety is ongoing on the issues of ensuring that food consumed, distributed, marketed or produced are of the highest affordable standards of food safety and hygiene as well as to ensure that food handlers are committed to ensure that hygienic conditions are maintained in the food processing facilities.

- Capacity building contributing to ensuring good agricultural practices aiming  to reduce the occurrence of food borne hazards as well as consumers’ education on the risks of unsafe food and its short and long term impact on health have started.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

During the reporting period, the following activities some of which are sectoral were implemented. Cross sector activities include the following:

- Review of Iraqi food legislation

Texts on Public Health Laws, were collected and reviewed. Amendments were proposed for the food related section. Also several national food standards were compiled and reviewed in preparation for the anticipated seminar on NCCI and Iraqi food legislation.

- Capacity building activities to reactivate the National Codex Committee for Iraq and enhance the participation of Iraq to the work of the Codex Alimentarius Commission

A training workshop on “Enhancing participation in Codex activities” was conducted in March 2007. Fifteen persons participated to the workshop and were from different Ministries (MOI, MOA and MOH) with 5 participants each. Also, the National Codex Committee of Iraq was finally located and its members were identified. TOR for “would be” participants in Codex meetings were drafted.

Three MOH officials have participated each to the meetings in China of the Codex Committee on Food Contaminants (CCFC) from 16-20 April, Codex Committee on Food Additives (CCFA) from 24-28 April and Codex Committee on Pesticides Residues (CCPR) from 7-12 May 2007.

- Development of IEC materials and national training activities in different areas related to food production and control

The development of Information, Education and Communication (IEC) materials which are part to the campaign to raise the awareness about food safety started. Themes and draft sketches for several posters were prepared. Those prepared by the Ministry of Health have been communicated to the three UN collaborating agencies and are under technical review. The posters developed by line Ministries with FAO support deal  mainly with topics related to GAP. Also a list of references needed to supplement library holdings at MoA in Baghdad was prepared.

- Training in specific topics related to food quality and safety

Training possibilities under the fellowship program supported by FAO are under  consideration for shorter periods instead of long periods. The advantage is that this will lead to a simultaneous increase in number of participants. This alternative is considered due to difficulties faced in finding a 9-month program that culminates in a graduate degree as originally indicated in the work plan. Two applications were filed for a 3-week course at FAO/IAEA unit in Austria. Other courses are being considered.

Fellowship programmes (training of trainers) supported by WHO on food borne disease surveillance (four candidates) and on bacteriological and chemistry laboratory investigations methods of Food borne diseases for two candidates have been initiated. The MOH/Iraq  has provided to WHO all the background documents enabling the organisation to review the candidates profiles and eventually proceed with the placement of the fellows in the appropriate training centres. Areas identified as priority needs are the methods for detection of hormones, pesticide residues, veterinary drug residues and additives in food preparations.

Regarding the international training courses already completed, a training course on the use of a wide range of Food control portable kits was conducted in Amman from 3-8 March 2007 and was attended by five engineers and technicians (2 from the Nutrition Research Institute, 2 from the MOH/Health Audit Department in charge of Food inspection activities and 1 from Kimadia). This was a training of trainers course and those five people are currently preparing a national training inside the country which will be conducted in two sessions in Basra and Erbil respectively. About 40 participants are expected to take part to the national training.

Similarly, a series of national training packages related to food safety supported by WHO were completed by the Ministry of Health during the reporting period. These included the following:

Three workshops on good hygiene practices (GHP), good manufacturing practices (GMP) and on Hazard Analysis Critical Control Point (HACCP) conducted in Baghdad from 15-19 April 2007 and in Basra from 22-26 April 2007 and in Erbil from 29 April to2 May 2007 respectively. A total of 88 laboratory technicians (75 male and 13 female)  participated to these three courses and the  new acquired skills are assisting them in performing their routine work. Five governorates were represented as follow: Baghdad (28), Erbil (28), Basra (20), Missan (5) and Thi-Qar (5).

Similarly, a series of three workshops for food inspectors have been completed in Baghdad (13-17 May), Basra (20-24 May) and Erbil (27-31 May).  The main focus was development of guidelines and procedures for food sampling and inspection.  A total of 87 food inspectors (68 male and 18 female) participated to the workshops. These food inspectors are from a wide spectrum of expertise, including agriculture engineers, food technologists, medical doctors and food lab technicians. A total of 10 governorates were represented. These include Baghdad (25), Erbil (19), Basra (18), Kirkuk (6) Mosul (5) Thi-Qar (5), Missan (5), Diwaniyah (2), Babylon (1) and Kerbala (1).

Another series of three workshops for food inspectors working at entry points organised by the MOH and supported by the UN took place in Baghdad (17-21 June), Basra (24-28 June) and Dohuk (1-5 July). These were attended by a total number of 87 (79 male and 8 female).    Those included participants from the governorates for Baghdad (35), Basra (20), Dohuk (14), Mosul (7) Missan (5), Suleiymaniyah (4) and Erbil (2).

- Rehabilitation of food control facilities in the regional food laboratories and food control facilities at entry check points.

The design and bill of quantities for food import entry points were prepared. Also computers and connectivity equipment were procured and delivered to Baghdad. Laboratory supplies have been defined and the procurement process is ongoing.

With regards to the three regional food control laboratories, the final architectural design/drawings, including Bills of Quantities developed by WHO Architecture and Engineering Team in consultation with the DOH engineering teams in Basrah, Mosul and Erbil were completed and submitted to the MOH for review and endorsement.

Invitation to bids for the selection of local contractors has been completed and at the time of preparing this report, the committees in charge of opening, analysing and reviewing the offers are working on offers from potential contractors for contract award.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

In general, the implementation of the project is on schedule, except for some components related to the rehabilitation components as explained below

Delays and constraints

There have been delays in identifying the sites for the border checkpoints causing subsequent delays in preparing the designs and bills of quantities. The change  and consequent delay was due mainly to the security situation.

Also the process of nominating and clearing of individuals to participate  in training workshops and study tours, has been slow.

Lessons learnt

The planning of training activities and the nomination of trainees need to be initiated well in advance. Persistent reminders are also necessary.

Encouragement for local procurement may be appropriate in order to reduce the occurrence of unnecessary delays during implementation.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The implementation of this project involves key partnerships and collaborations which require a lot of coordination and consensus building processes. These partnerships include different institutions such as the three ministries directly involved in this peoroect (MOH, MOA, MOI) and other line Ministries and organisations involved in Food sector such as MOT, MOE, MOHE, Ministry of Sciences and Technology. Also this project requires the involvement of the private sector and Associations for consumer protection as well as legislative entities such as the parliament.

Collaboration is also necessary between the three UN agencies (WHO, FAO and UNIDO)  and other international organisations  interested in assisting Iraq to develop the sector.

Such collaboration and partnerships are key to ensuring integration of food control mechanisms and have proven important for efficiency, cost reduction and synergy. The collaboration has been also instrumental in the process of needs identification,  determination of inputs specifications, implementing training and distributing inputs.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2007.

Between July and December 2007, the following activities are planned:

- Continue to support the participation of Iraqis to Codex meetings and other codex activities

- Continue national training activities

- Ensure completion of the construction and operation of the check points and procuring the equipment needed for their operation

- Prepare IEC material including posters on other topics including pesticides and foods of animal origin

- Continue with other ToT courses: Fresh fruits and vegetables 19-16 July, GAP: foods of plant origin 2-5 Sept and GAP: foods of animal origin Dec 07.

- Decide on the design of training course for fellowship program and follow up on initial contact in Vienna or Damascus

- Proceed with the rehabilitation of Mosul dairy plant

- Follow up on procurement, delivery and distribution of lab equipment for food processing plants

- Organise the training on HACCP for the milling sector

- Continue the review and assessment of the status of the current food related law and legislation through international consultancy and organise a seminar on food legislation

- Proceed with the physical and functional rehabilitation of the three food control laboratories in Basrah, Mossul and Erbil, including procurement of related equipment and supplies

- Continue with agreed training programmes/packages including fellowships for overseas training.

At the time of preparing the present report, there are already some activities among the ones mentioned above which have been already implemented. Details will be provided in the next progress report.

# Text boxes

Report Formatting Instructions: We kindly ask that you review the instructions below and follow them in the preparation of your report:

- Do not put the narrative text into boxes as was done in the previous report and do not incorporate boxes, graphs, etc into the narrative report.

- Add additional information including charts, graphs, etc as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative

- Number all sections and paragraphs as indicated below

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.