n

Strengthening Disaster Risk Reduction and Emergency Preparedness

programme NARRATIVE progress report

# REPORT COVER PAGE

| Participating UN Organization(s): IOM, FAO, UNDP, UNFPA, UNICEF, UNIFEM, UN-HABITAT, WFP, WHO, UNAIDS |  | Cluster/Theme/Priority Area: Emergency Preparedness Disaster Risk Reduction |
| --- | --- | --- |
| Compiled by: Mairead Heffron (mairead.heffron@undp.org) |  |  |

| Programme No. and Programme Title: |  | Report Number: |
| --- | --- | --- |
| Strengthening Disaster Risk Reduction and Emergency Preparedness |  | 3rd Annual Report |

| Reporting Period: |  | Programme Budget: |
| --- | --- | --- |
| January 2010 – December 2010 |  | US$ 10,000,000 |

| List Implementing Partners: |  | Programme Coverage/Scope: |
| --- | --- | --- |

Definitions:

Capacity building Efforts aimed at developing human skills or societal infrastructures within a community or organization needed to reduce the level of risk.

Climate change The climate of a place or region is changed if over an extended period (typically decades or longer) there is a statistically significant change in measurements of either the mean state or variability of the climate for that place or region.

Disaster risk management The systematic process of using administrative decisions, organization, operational skills and capacities to implement policies, strategies and coping capacities of the society and communities to lessen the impacts of natural hazards and related environmental and technological disasters. This comprises all forms of activities, including structural and non-structural measures to avoid (prevention) or to limit (mitigation and preparedness) adverse effects of hazards.

Disaster risk reduction The conceptual framework of elements considered with the possibilities to minimize vulnerabilities and disaster risks throughout a society, to avoid (prevention) or to limit (mitigation and preparedness) the adverse impacts of hazards, within the broad context of sustainable development.

Early warning The provision of timely and effective information, through identified institutions, that allows individuals exposed to a hazard to take action to avoid or reduce their risk and prepare for effective response.

Emergency management The organization and management of resources and responsibilities for dealing with all aspects of emergencies, in particularly preparedness, response and rehabilitation.

Geographic information systems (GIS) Analysis that combine relational databases with spatial interpretation and outputs often in the form of maps. A more elaborate definition is that of computer programmes for capturing, storing, checking, integrating, analysing and displaying data about the earth that is spatially referenced

Hazard A potentially damaging physical event, phenomenon or human activity that may cause the loss of life or injury, property damage, social and economic disruption or environmental degradation.

Mitigation Structural and non-structural measures undertaken to limit the adverse impact of natural hazards, environmental degradation and technological hazards.

Recovery Decisions and actions taken after a disaster with a view to restoring or improving the pre-disaster living conditions of the stricken community, while encouraging and facilitating necessary adjustments to reduce disaster risk.

Relief / Response The provision of assistance or intervention during or immediately after a disaster to meet the life preservation and basic subsistence needs of those people affected. It can be of an immediate, short-term, or protracted duration.

Risk The probability of harmful consequences, or expected losses (deaths, injuries, property, livelihoods, economic activity disrupted or environment damaged) resulting from interactions between natural or human-induced hazards and vulnerable conditions.

Risk Assessment A methodology to determine the nature and extent of risk by analysing potential hazards and evaluating existing conditions of vulnerability that could pose a potential threat or harm to people, property, livelihoods and the environment on which they depend

NARRATIVE REPORT FORMAT

# Purpose

The Joint Programme on Disaster Risk Reduction and Emergency Preparedness was developed as one of the components of the “Delivering as One” United Nations Framework in Mozambique. This was done in recognition of the fact that risk reduction, disaster preparedness and mitigation, as well as vulnerability reduction, are fundamental factors contributing to development in Mozambique, a country which is affected by frequent natural disasters.

The overall goal of this Joint Programme is to strengthen national capacities at all levels to reduce the risk of disasters and mitigate their impact on the vulnerable populations in the country. The Joint Programme builds on the National Master Plan for Disaster Risk Reduction in order to strengthen institutional frameworks and systems for preparedness, response and disaster risk reduction at national, provincial, district and community levels within an overall vulnerability reduction perspective. For this purpose, in addition to the delivery of capacity building activities and the implementation of participatory projects at community level, the programme supports the Government in mainstreaming disaster risk management issues, developing plans and policies, and promoting inter-sectoral dialogues. These are all essential elements that are needed to carry out long-term mitigation strategies, and to ensure that a smooth transition mechanism is in place to facilitate movement from the emergency phase to the reconstruction/development phase.

The Joint Programme is articulated in terms of the following outcomes and outputs:

OUTCOME 1:

Mainstreaming of disaster risk and vulnerability reduction in national development plans and programmes, including the development of policy and norms.

OUTPUT 1.1:

Policy / norms developed for humanitarian response, DRR and vulnerability reduction.

OUTPUT 1.2:

DRR and vulnerability reduction are mainstreamed in national development plans and programmes.

OUTCOME 2:

Government and Civil Society capacities for disaster risk reduction are strengthened at central, provincial and local levels.

OUTPUT 2.1:

Central, provincial and district level institutions strengthened for DRR, contingency planning and emergency preparedness and response.

OUTPUT 2.2:

Inter-sectoral co-ordination capacity for DRR and emergency preparedness strengthened at central, provincial and district levels.

OUTPUT 2.3:

Participatory projects implemented to engage communities in disaster risk and vulnerability reduction and emergency preparedness.

OUTCOME 3:

National Information System including Early Warning System, inter-sectoral information sharing and knowledge management set up for disaster risk reduction.

OUTPUT 3.1:

Early Warning System (EWS) strengthened for natural hazards at central, provincial and local levels.

OUTPUT 3.2:

Information sharing and knowledge management strengthened between the different sectors for preparedness, contingency planning, response and early recovery.

- Resources

Financial Resources:

A total of US$8,109,183 was made available for the implementation of emergency preparedness and risk reduction activities in 2010, of which US$ 2,336,900 was contributed from the One Fund, and US$ 4,339,351 from UN Agencies own resources. The 2009 balance was US$ 1,432,932.  The One Fund contribution for 2010 represents 46% of the total resources available.

Human Resources:

- Each participating UN organization has designated a focal person for the Joint Programme, and UNDP, as convening agency, provides overall coordination support through its DRR team in the Crisis Prevention and Recovery / Environment Unit of UNDP.

- Technical Assistance has been provided through in-house technical capacities and/or international and national experts.

- Implementation and Monitoring Arrangements

Regular monitoring was carried out through the Joint Programme Matrix developed by the Joint Programme team. Regular reporting on activities was provided and monitoring field trips were carried out at least once a year by each of the JP agencies. Joint visits were conducted, as for instance in the context of the simulation exercises which were organized at provincial level, under the leadership of the National Disaster Management Institute (INGC).

Quarterly meetings of the Joint Programme were conducted for information sharing on the progress of activities carried out by different agencies and to discuss funding allocations and revisions. As a result, reallocations of funds were made amongst agencies according to the required individual needs. Annual Work Plan (AWP) activities were revised and the JP matrix updated to reflect the adjustments made to the agency-specific detailed activities.

An internal review of all of the UN Joint Programmes took place in July 2010, where opportunities for better synergies were discussed, in addition to results achieved thus far.

- Results

During 2010 all agencies continued to consolidate activities begun in previous years. Co-ordination efforts continued and examples of activities carried out include the support provided to contingency planning, simulation exercises, and regular planning meetings.

The crucial issue of Climate Change adaptation was highlighted in 2010. Notably, linkages between gender and climate change were reflected in the approval of a strategy on gender and climate change. Additionally in early 2010, a workshop was organised for the mainstreaming of DRR and climate changes issues into the UNDAF, with wide participation from UN agency representatives.

Strong partnerships were developed with various Government institutions such as MICOA, INGC, Ministry of Agriculture, SETSAN, as well as with local administration structures at provincial and district levels, the Red Cross, other Civil Society Organisations and local leaders.  Strong inter-agency collaboration was also established for various assessments and studies carried out jointly.

Assessment of the progress made per outcome

OUTCOME 1:

Mainstreaming of disaster risk and vulnerability reduction in national development plans and programmes, including the development of policy and norms

Expected Output 1.1: Policy / norms developed for humanitarian response, DRR and vulnerability reduction.

Various strategies and policies for disaster risk and vulnerability reduction, to ensure mainstreaming of these issues into development plans in Mozambique, were developed during the year with the support of the JP. Some of these were brought to approval stage, such as the strategy and Action Plan on “Gender, Environment & Climate Change”. This was developed by the Ministry for Co-ordination of Environmental Affairs (MICOA) and approved by the Council of Ministers in July 2010 in response to an explicit demand from MICOA, and following advocacy from UNIFEM, to ensure that women and gender equality issues become a central part of key emerging development issues such as climate change.  The Ministry for Coordination of Environmental Affairs (MICOA) and the Director of the NGO MUGEDE, with JP support, presented the Strategy in the COP 16 in Mexico. At this meeting they also had the opportunity to exchange ideas, to carry out advocacy concerning Gender and Climate Change and to increase cooperation between the Ministry and NGOs for its implementation.

The Strategy for Vulnerability Reduction and Sustainable Development in Flood Prone Areas was prepared and presented by UN-HABITAT at the Technical Council for Disaster Management (CTGC) in 2009, although it has not yet been approved. The active involvement of technicians from INGC (central and district) in the process of construction and transfer of technology of elevated platforms in Inhangoma Administrative Post – Mutarara reflected a level of commitment to the strategy. The strategy outlines three important strategic lines of intervention for the government:

- Establishment of “resettlement neighbourhoods” in adequate and safe areas;

- Installation of supporting platforms in fertile areas prone to moderate floods;

- Continuous process of institutional capacity and local training.

The development of the disaster management law was also a focus of attention for the JP, with substantial contributions provided by the various Joint Programme focal points to the draft Disaster Management Law. The draft law was prepared by a local company, under the direct management of INGC and with financial support from GTZ

In the area of health, information on a number of strategies was disseminated, for example the WHO six year strategy on health sector risk reduction and emergency preparedness, international health regulations relating to Influenza H1N1 prevention. Related advocacy targeted at key stakeholders, such as line ministries and institutions, in the areas of tourism, immigration, trade, foreign ministries, defence and trade was also was realised.

A number of studies took place in 2010, aimed at improving understanding of specific risk contexts for the purpose of more informed policies. One of these was a baseline study on Gender and Drought, conducted in 3 districts in the provinces of Inhambane and Gaza in 2009, which was finalised in 2010 and the findings and recommendations were presented to the Humanitarian Country Team. The study assessed the impact of INGC/Red Cross- implemented drought-related interventions on women and men, and analysed their role in the implementation.

Expected Output 1.2: DRR mainstreamed in national development plans and programmes.

National development plans and programmes saw the mainstreaming of disaster risk issues, with JP agencies providing inputs to the PARPA review process and the development of the new Poverty Action Plan (2011 – 2014). Disaster risk mitigation was reflected in the government five year plan, presented in 2010.It was also integrated into the UNDAF process, which benefitted from a training workshop on “Mainstreaming DRR and climate Change in the UNDAF”, facilitated by UNDP, EEG, UNU and CADRI, with full participation of JP agencies.

The Common Fund for disaster management, recognised as an essential tool to ensure mainstreaming of disaster risk reduction interventions throughout the different government sectors, was presented to CTGC members and to the Minister for State Administration. The JP, through UNDP and DFID´s support provided financial support and substantive inputs to this process.  The detailed implementation (Phase II) plan will be prepared for presentation in March 2011 to the Council of Ministers for final approval and implementation.

In order to ensure the mainstreaming of both DRR and gender issues in national programming, a consultancy on Integration of Gender into Disaster Risk Management and Climate Change in programming and activities in Mozambique was initiated in 2010, in cooperation with the National Institute for Disaster Management (INGC). Three documents are currently being developed: a literature review on relevant international best practices; a situation analysis examining the integration of gender into disaster and climate change programmes in Mozambique; and a needs assessment concerning gender issues for stakeholders working on disasters and climate change. The three documents will provide the basis for a practical kit (“the toolbox”) in Portuguese on the integration of gender into DRR and Climate Change programming, targeting stakeholders from government, donor community, Civil Society and the UN. In 2011 stakeholders at national and regional level will be trained in using the toolbox.

Other crosscutting issues were also mainstreamed into national contingency plans. The contingency plan of the Ministry of Woman and Social Affairs (MMAS) integrated SRH (sexual and reproductive health) and HIV components. A draft set of HIV guidelines for emergencies was produced to guide national and district-level planning on a comprehensive HIV Response during emergency situations to ensure minimum requirements are provided for in the priority areas of prevention, treatment, care and support programmes.

At various levels (INGC and other line ministries, District Administrations, Municipalities, NGOs, and other non-governmental partners) regular advocacy activities for DRR and vulnerability reduction ensured that the practical results and lessons learned from pilot interventions, such as building with the wind, learning to live with the floods, were understood by decision makers at national and decentralised level.

OUTCOME 2:

Government and Civil Society capacities for disaster risk reduction are strengthened at central, provincial and local levels.

Expected Output 2.1: Central, provincial and district level institutions strengthened for disaster risk reduction, contingency planning, and emergency preparedness and response.

Capacity of government and civil society for DRR was strengthened through a range of training and capacity building activities, and development and distribution of guidelines and manual

In the area of health, national and provincial health authorities’ capacities were strengthened through the dissemination of guidelines on disease prevention, treatment and control of water-borne diseases such as cholera and pandemic influenza AH1N1.  Cascade training of health staff was conducted on surveillance and response to diseases, including epidemics such as Cholera and Influenza A, as well as the basic principles of IDSR. Technical support was provided for national training of surveillance officers held in Beira, with the participation of staff from all 11 provinces and for the training of community drug distributors in drug treatment of schistosomiasis, filariasis and helminthiasis in 7 targeted provinces.

The production of manuals contributed to increased capacity at various levels. Through the JP a Meningitis Manual on surveillance, prevention and control of meningitis was developed with the Ministry of Health. A manual for facilitators of local risk management committee training was brought to a final draft stage through seminars involving technical staff and regional directors of INGC. The Code of Conduct to Prevent Sexual Exploitation and Abuse in emergency situations, although not yet approved, was made part of the training module for the civil protection unit (UNAPROC). UNFPA also advocated and worked with sectors to ensure that Sexual and Reproductive Health, Gender and HIV components are included in the development of DRR tools.

A training manual to build the capacity of community radio stations to produce relevant and engaging broadcasts around disaster risk reduction was designed and developed in 2010. IOM Mozambique, through the JP, worked in consultation with the National Institute for Disaster Management and the Institute for Social Communication, which is a local radio network. The first three training modules cover DRR broadcasting, early warning systems and floods, and can be used by trainers or for self-study. Each module will include background information on the issue, sources and contacts, ideas for community radio programming, case studies on how other radio stations or communities have approached this issue, and trainers’ notes.

This training ensured that these and other manuals were used to increase DRR capacity throughout the country. With JP support, INGC conducted training in DRR for its staff and local government staff in a number of regions throughout the country, thereby increasing awareness of DRR actions and benefits. This took the form of training of trainers in Disaster Risk Management, which were conducted for 30 heads of administrative posts and district administrators in Vilankulos and Caia.

A number of government staff also benefitted from international training, supported through the Joint Programme:

- Two MICOA officials participated in the Gender and Climate Change Adaptation and Mitigation Workshop in the Philippines, with the aim of increasing the capacity of MICOA staff in the area of Gender and Climate Change. This helped to strengthen capacity especially in relation to the development and implementation of the new Strategy and Action Plan for Gender, Environment and Climate Change.

- 1 technician from INAM attended GIS training at the Asian Disaster Preparedness Centre in Thailand.

- Officials from the INGC Directorate of Arid and Semi-arid Zones attended training related to dryland development in Galillee College, Israel.

- A gynecologist from the Ministry of Health participated in the regional ToT for the Minimum Initial Service Package, and the training will be replicated in 2011 at national level.

Other capacity building activities supported in 2010 included:

- Two INGC staff received on the job training on risk analysis, including GIS and Remote Sensing during 4 months (placed at WFP offices).

- A regional emergency preparedness response training workshop held in August 2010 served to better orient UNICEF staff on essential principles, standards and considerations in planning and response to emergencies. It also provided an opportunity for a deeper discussion on some of the key challenges facing humanitarian action in Mozambique in the context of emerging trends and experience in the region and globally.

- Awareness raising activities on Gender Based Violence, HIV/AIDS and Gender in resettlement areas (with the Provincial Directorate of Woman and Social Affair and Provincial Network of Women’s Associations).

- Social mobilisation and communication activities for the promotion of safe and good hygiene practices and behaviour change to prevent HIV.

- 70 peer educators trained in Adolescent Sexual Reproductive Health to disseminate information on Gender, HIV and AIDS in Maratane refugee camp (Nampula) and 1 YFS created to receive adolescents and young people.

- IHR core capacities assessment workshop took place with the participation of key departments from 11 provinces, as well as the development of the draft  Country  IHR plan 2010-2015  formulated to respond to public health concerns.

- Emergency kits were procured for local risk management committees (12 emergency kits were provided for 12 Local Disaster Management Committee) in Inhambane districts of Funhalouro, Mabote, Panda, Jangamo, Vilankulo and Inhassouro. The distribution of another 60 kits to committees was pending.

- UNICEF’s Emergency Specialist facilitated the discussions with the Government and other local authorities, along with other partners, to advocate for and assist counterparts in the formulation, implementation and evaluation of emergency assistance and coordination. The Emergency specialist supported national capacity building for emergency preparedness and response and the integration of the Core Commitments to Children in emergency coordination and response.

- A Reference Group of stakeholders working with disaster risk management and climate change has been established in order to create a forum for discussion on the integration of gender into these areas. The reference group is comprised of donors, NGOs, universities, several government institutions and UN agencies.

- A study on a special INGC remuneration scheme was conducted with the purpose of increasing staff motivation and preventing high staff turnover and brain drain.

- Support was provided to INGC to recruit 2 technicians  and cover salaries during the first six month of their contract, for mapping activities in DARIDAS

- One university graduate student was placed at INGC to support them on field assessment, and at the same time improving the capacity of UEM graduate students through practical experience, under the supervision of WFP to ensure the quality of the products.

- Through the principles described in the Strategy for Vulnerability Reduction and Sustainable Development in Flood Prone Areas, UN HABITAT strengthened the technical assistance of key government line ministries and their provincial and district branches, including MICOA, MAE, MOPH and MINED, to use the proposed strategy in order to integrate the technical concepts of territorial planning and building codes into their activities in vulnerable areas.

- Provincial meetings on Disaster Risk Reduction with the participation of district and provincial institution have been realised through the Tete Agricultural College (CPFA), where college and school students have been taught about DRR measures in the flood and drought prone areas.

A range of interventions supported through the JP addressed specific preparedness capacity and resource gaps at various levels.

Goods were pre-positioned, in line with national contingency planning.

UNICEF procured 19,000 nets for Gaza Province, which were received by DPS and routinely distributed to pregnant women in all districts. Nets were also distributed in flooded areas of the Zambezi River during the March 2010 floods. 6,000 LLIN were earmarked for emergency response, in addition to Certeza and calcium hypochlorite powder that were pre-positioned with DNA in Maputo and provincial DPOPH. WHO also pre-positioned emergency supplies at the Ministry of Health (including 85,000 litres of Lactate Ringer and 7500 kg of Hypochlorite Calcium).

Emergency preparedness gaps in the education sector were addressed by JP assistance for education in emergencies in Caia during the March 2010 floods. UNICEF in particular strengthened capacity in emergency preparedness and response in the 7 most disaster prone provinces through a multi-sectorial approach led by MINED jointly with MMAS, MINT and INGC. Additionally, new low-cost technology for the construction of school tents with community support was introduced this year in 7 districts of Sofala province and will be scaled-up to more disaster prone districts in 2011. The demonstration tents are expected to support requirements for any upcoming floods emergency.

In the context of the flood situation in Caia in March 2010, the JP agencies provided emergency response support in different ways, based on their relative expertise:

- Agencies sent human resources to the flood affected districts of Caia to give technical support for strategic orientation of the response, for example in monitoring and evaluation of the implementation of health nutrition and logistics activities (UNICEF).

- UNFPA supported the National Institute for Disaster Management (INGC) in responding to the needs of population affected by the 2010 floods, through the delivery of 500 dignity kits and 40 tents.

- UNICEF, under the coordination of the Government and in partnership with various non-governmental organizations, provided the following: (i) delivery of 15,500 emergency packages for vulnerable families, reaching approximately 46,500 children; (ii) establishment of  27 Child Friendly Spaces in 22 Resettlement Centres for approximately 6,500 children; and (iii) training for 200 police deployed to four flood-affected provinces to provide protection to children and women against violence and abuse.

- WFP supported INGC in carrying out an emergency needs assessment and in the deployment of ICT mobile equipment.

- All agencies worked together as part of the IASC cluster approach to coordinate response-related interactions between the government, UN and other partners.

A number of activities to increase capacity in relation to the management of disease and nutrition related risks and nutrition were achieved during the course of the year:

- UNICEF Funds helped to provide technical assistance at central level for universal coverage campaigns and at provincial level for monitoring of malaria interventions and epidemiology. Technical support was provided through participation in the Endemic Diseases Working Group and reinforcement of government drug stocks for case management. Support was also provided to local authorities, with $30,000 being given for cholera prevention activities, logistics support, formative supervision and monitoring. As a result of these and other measures, the total numbers of cholera cases from January to October 2010 is lower than the number of cases for the same period in 2009.

- Nutrition rehabilitation for the diagnosis and treatment of severe and moderate acute malnutrition was supervised in 7 districts in Sofala Province that are vulnerable to food deficiency and emergencies. Support was also providedby Save the Children for the expansion of the outpatient treatment with community involvement of severe acute malnutrition in Nampula, Gaza, Sofala and Zambézia provinces.  In addition, the provincial authorities of Sofala and Tete were supported to assess and monitor the situation of women and vulnerable children.

- A first mass treatments campaign for schistosmaisis was held in 18 districts of 4 provinces, namely Cabo Delgado, Nampula, Niassa and Zambezia. A total of 488,359 school children were treated with 64 % coverage. In addition, a second MDA campaign for LF was carried out in 36 districts of  7 provinces, namely Cabo Delgado, Nampula, Niassa and Zambezia with a coverage of 74 %.

Expected Output 2.2: Inter-sectoral co-ordination capacity for DRR and emergency preparedness strengthened at central, provincial and district levels.

Contingency Planning and Coordination Support

- All agencies provided inputs and support for the revision of the Government and Inter-Agency contingency plans at both national and provincial levels, and also worked closely with government counterparts to improve sectoral contingency plans (with MMAS, for example).

- Under the Education and Protection Cluster, MINED, MINT and MMAS were supported in decentralizing emergency preparedness and response plans and in resource mapping in coordination with CTGC in seven vulnerable provinces.

- One provincial CTGC training session for GOM staff was carried out in Beira.

- All agencies participated in the Government-led national emergency simulation exercise with ICT, logistical, financial and technical assistance.

- The first phase of the Sub-regional Centre for Disaster Mitigation and Sustainable Reconstruction (DIMSUR), in the Comoros, Malawi, Madagascar and Mozambique, was launched in April 2010 with UN Habitat as the primary facilitator. The main objective was the development of local, national and sub-regional capacities for reducing the impacts of natural disasters on human settlements.

- Gender and HIV/AIDS focal points in all the HCT clusters have been appointed. As a result of advocacy the IASC “Gender Marker” tool was integrated into the preparedness phase of the Contingency Plan 2011. As a result of the participation of the JP in the government’s 2010 disaster simulation exercise it has been recommended in the joint CTGC-HCT evaluation report that future emergency responses should provide sex disaggregated data and a stronger integration of gender and HIV/AIDS in the contingency plans and emergency exercise guidelines.

- UNICEF’s Gender Specialist is supporting WASH, Nutrition and Education/Protection Clusters to integrate gender into their preparedness and response, both at the national level and the local level. Two training sessions will be delivered in 2011 to cluster members in Sofala and Tete.

- S	ensitization on GBV at community level has been integrated as part of MMAS annual work plan.

Expected Output 2.3:  Participatory projects implemented to engage communities in disaster risk & vulnerability reduction and emergency preparedness

Vulnerability assessments

- One quantitative and one qualitative vulnerability assessment on food security and nutrition were produced in February and July with support to SETSAN.  The Reports were published by SETSAN.

- Food security and nutrition training sessions were held at decentralized levels in 3 provinces.

- M&E systems of food security indicators were supported twice in the year.

- Eight District Food Security Profiles were completed and made available for Chibuto, Guija, Chokwe, Mabalane, Massangena, Chigubo, Funhalouro e Mabote.

- One Urban Vulnerability Study for Maputo and Matola was completed with the draft report made available.

- One Comprehensive Food Security and Vulnerability Assessment, integrating food security and nutrition with risk analysis completed with the report published.

- Joint Crop and Food Security Assessment carried out in collaboration between WFP and FAO and mission carried out (CFSAM) in May 2010 that estimated that 250,000 persons are in need of food assistance until the 2010/11 harvest in critical districts of Tete, Gaza, Inhambane and Sofala provinces. Recommendations on food assistance and long term interventions were made as a result.

- FAO also contributed to the National Vulnerability Assessment, the results of which were released in August 2010.

Community level interventions

- Support provided to communities on asset creation through food for work and provision of non-food items in 10 districts - Matutuine and Magude (Maputo province), Chibuto, Mabalane, Chicualacuala, Massangena and Chigubo (Gaza province), Mabote (Inhambane province), Machaze (Manica province), Machanga (Sofala province) and Changara (Tete province). Assets created, involving around 20,000 beneficiaries, included small irrigation schemes, small water reservoirs, schools, drainage channels and conservation agriculture activities and reforestation. These assets were created in collaboration with local government/ districts and CERUMs.

- Support provided to income generation activities in Chigubo district, Gaza and Mutarara district and Tete in the form of training in local artisan techniques.

- Women’s associations in Zambézia were trained to ensure that SRH, gender and HIV elements are included in the risk identification assessment and awareness efforts at community level.

- UNICEF-supported partners (World Vision, Save the Children, ISAAC) to implement three Community-led total sanitation projects in resettlement areas of Mutarara District (Tete Province) and Mopeia District (Zambezia Province) that have been targeted as areas at high risk of waterborne disease outbreaks. More than 3,700 household latrines were constructed by families living in the target areas, benefiting around 18,840 people in the affected communities in Mutarara and Mopeia.

- Cholera affected, hard-to-reach localities of Zambezia, Sofala, and Cabo Delgado were accessed with prevention messages through multimedia mobile units (data reportedas part of the ICS). All affected districts of the four hardest hit provinces (Cabo Delgado, Niassa, Zambezia, Sofala) were provided with IEC materials for activists on the ground. Zambezia province, the worst hit province, was supported to enhance coordination efforts and integrate C4D interventions at provincial and district (Gurue) level.

- Emergency response videos on HIV, malaria, and cholera prevention were produced and used in the affected districts of Sofala and Zambezia.

- During the institutional red alert, approximately 5 million people were reached with daily radio messages, in Portuguese and local languages (Loló & Sena), and through radio programmes and debates on hygiene promotion and cholera/malaria prevention, aired in coordination with local health authorities in Zambezia, Sofala and Tete provinces (RM and four community radio stations).

- During the institutional red alert, an estimated 25,000 people were reached by messages on the promotion of good hygiene practices and malaria prevention through the  training of local risk management committees in six affected bairros in Mutarara and Mopeia districts.

- Social mobilisation efforts for the promotion of cholera and malaria prevention by multimedia mobile units were intensified in Marromeu district (Sofala province) and Mopeia district (Zambezia). Community theatre sessions for the promotion of good hygiene practices in Morrumbala and Mopeia districts (Zambezia province).  In Morrumbala members of risk management committees were trained on theatre techniques in order to replicate social mobilisation activities in other affected areas.

- Communities in floods and drought affected areas involved in participatory planning and implementation of Conservation Agriculture (CA) activities with capacity building activities for district extension officers and local community leaders in technologies for Disaster Risk Reduction.

- A total of 4,601 households, through 1,326 lead farmers, were supported with DRR and CA training activities including agricultural inputs in the four beneficiary semi-arid districts of Changara, Moatize, Mutarara and Cahora Bassa. The training covered crop diversification, nursery establishment, land preparation, soil fertilisation, increased horticultural production, conservation and irrigation.

- Through the participatory approach and local capacity building some pilot interventions have been developed to identify and test innovative small-scale mitigation interventions for floods and cyclones in vulnerable pilot areas (Vilankulo Municipality and Inhangoma District – Mutarara District), and to prepare the conditions for future replication. The cyclone resistant houses build in Vilankulo Municipality were a success and have already resulted in the construction of a Municipal kindergarten built using the same building techniques.

- As part of a set of materials that were produced in 2009, a book with the histories of the resettlement process was produced, discussed and approved by INGC and it is in the process of printing. The objective of the book is to help children to better understand the integration process in these new resettlement neighbourhoods.  The main idea is to use the different channels within the Government, the UN and NGO sector, in coordination with the INGC,  to disseminated the booklet in resettlement neighbourhoods affected by past flood events.

- Launched in March 2010, Bravos do Zambeze (Zambeze Braves) combined a high quality 26-episode serial radio drama produced in Portuguese and Sena, with training for community radio journalists. The purpose of the initiative was  to convey information around disaster risk reduction and floods, as well as to build local capacity for reporting on disasters and climate change. The drama was produced for the International Organization for Migration (IOM) in Mozambique by CMFD Productions. After identifying a need for a similar initiative in Gaza province, IOM commissioned CMFD to adapt and translate the drama into Changana, to be re-released as Leões do Limpopo in early 2011.

OUTCOME 3:

National Information System, including Early Warning System, inter-sectoral information sharing and knowledge management, set up for disaster risk reduction.

Expected Output 3.1: Early Warning System strengthened for natural hazards at central, provincial and district level.

An Early Warning System for the Licungo river basin in Zambezia has been initiated, through the support provided from UNDP to INGC, including study, design of system, and details of equipment specified, using the successful model of the Buzi basin community-based early warning system. A car was also provided to ensure logistical support to the INGC for the establishment of the system and the training of communities in the river basin.

A project for a National Tsunami Early warning system was also initiated, with initial training activities held for relevant stakeholders.

Links between EWS stakeholders were strengthened in a number of ways:

- Drought response plans were created through the provision of support to SETSAN and INGC. Flood response plans were also created at provincial level.

- Support was provided to scenario building and translations for the Government and UN Contingency Plan.

- Use of spatial information promoted for early warning and risk analysis, in collaboration with ITHACA (Information Technology for Humanitarian Assistance, Cooperation and Action/ Politecnico di Torino/ Istituto Superiore Sui Sistemi Territoriali per l’Innovazione), by INGC and other Government partners.

Various activities were carried out related to risk mapping;

- Installation of Mapping Unity at DARIDAS/ INGC, with the provision of two desktop computers, ArcGIS software, one laptop, and training on risk mapping.

- Four District Risk Mapping exercises completed for Guija, Massingir, Chigubo and Massagena with INGC (DARIDAS), MICOA and MINAG, and reports made available.

- Editing and multiplication of district profiles and risk mapping.

- More than 100 risk maps laminated in A0 format and distributed at district and community level.

Awareness activities utilising media to highlight certain DRR issues were conducted:

- Participation in radio programme “linha directa” with SETSAN, FAO, MINAG, INAM and INGC on drought risks and actions on the 20 February. Participation in STV programme  “Moçambique em Acção” on October 14 for the World Food Day

Equipment was purchased to enhance the capacity of community radio stations in Gaza Province, specifically all along the Limpopo valley in Mazivila, Chibuto, Mabalane and XaiXa:

- This equipment consists of transmitters, parabolic antennas and receivers, computers, zoom digital recorders and 13 KVA backup generators.

- IOM also fitted a new 50 m radio tower and new dipole FM antennas at Mutarara Community Radio Station.

- A BBC engineer was contracted to conduct an assessment of Community Radio Stations in Inhambane, Nampula and Zambezia. A total of 12 radios were assessed, and recommendations were made relating to strengthening the capacity of the radio stations.

Expected Output 3.2: Information sharing and knowledge management strengthened between the different sectors for preparedness, contingency planning, response and early recovery.

The GRIP (Global Risk Identification Programme) saw a number of INGC/UEM and UNDP led activities consolidated or completed:

- Country Situation Analysis (SIERA): A comprehensive inventory has been conducted to identify existing risk assessment studies and projects, publications and reports on risk assessment, data sources, organizations and institutions related to risk assessment, as well as key professional expertise and skills;

- Historical Disaster Database: Historical information on natural disaster losses in Mozambique for the last 30 years (1979 - 2009) has been collected and inputted into a national disaster database available at the following link http://moz.gripweb.org/DesInventar.

- Urban Risk Assessment: Initial work on seismic risk assessment for Maputo City has begun to be implemented by a technical team from Maputo municipality with technical support from NSET. Results of this work will provide a base for establishing shelter plans in advance of a disaster occurrence, and for developing Disaster Risk Reduction actions.

In the context of the knowledge management support activities of the Joint Programme, participating agencies contributed to an ECHO funded (UNDP led) regional project on knowledge management. Technical and financial support was provided for a knowledge fair held in Johannesburg in March, with participation from various Government, Academic and International NGOs from Malawi, Comoros, Madagascar and Mozambique. Community based disaster risk reduction best practices were shared during the workshop and a Documentary, Standard Operations  Procedures guidelines and a best practices book produced in the context of this project with inputs and support from DRR project staff were shared. The materials were also translated into French and Portuguese. A meeting with SADC DRR unit was also conducted to revise the DRR SADC Strategy.

Four strategic areas of comparative advantage

The UN system in Mozambique has four key comparative advantages in the context of its efforts to advance the Joint Programme for Emergency Preparedness and Disaster Risk Reduction. The results for this period have had impacts across all four of these areas of strategic advantage.

- Policy and advocacy

Policy and advocacy efforts were carried out to mainstream Disaster Risk Reduction and Climate Change Adaptation into the Poverty Reduction Strategy (PARPA), into the UNDAF and into other national development plans. Of note here is the approval of the “Gender, Environment & Climate Change” Strategy and Action Plan and the progress made on the establishment of a common fund. Discussions continued on the revision of the Draft Disaster Management Act. It is hoped that the discussions on the strategy for vulnerability reduction and sustainable development in flood prone areas will be renewed again in the CTGC in the coming year.  The results are explained in more detail under Output 1.1.

- Normative and technical support

Normative and technical support consisted of inputs to improve the national normative and legislative standards for DRR, emergency preparedness and response. In addition the tools, checklists, guidelines and national contingency plans as described in previous sections of this report (Outputs 1.1, 1.2., 2.1 and 2.2) were developed with JP support.

- Capacity Development

Support for the strengthening of existing Government capacity from central to district level was provided across most of the activities carried out in the context of the current Joint Programme, particularly through the provision of equipment and training activities, including simulation exercises. A detailed description of interventions in this context is provided under outputs 2.1, 2.2 and 2.3.

- Civil Society Partnerships

Partnerships with civil society were further strengthened through their collaboration with various agencies involved in the Joint Programme. This collaboration took place at both national and local level.

UNDP has started the development of a small grants initiative aimed at increasing civil society participation in disaster risk reduction initiatives. This initiative suffered some delays in 2010 but will be taken up again in 2011, in coordination with INGC. It is expected that the initiative will reinforce the role of community based organisations and local risk management committees in the implementation of DRR activities at decentralised level.

Implementation constraints and lessons learned

Through this JP, UN Agencies have consolidated efforts to support several Ministries and Institutions on DRR and Emergency Preparedness issues. However, it is important to understand that the implementation of the proposed DRR strategies and interventions needs time. Capacity development of INGC and CENOEs has registered positive progress but the strengthening of provincial and district level capacity should continue with a clear focus on institutional arrangements at decentralised levels, and implementation of disaster mitigation and prevention activities at local level.

The Internal Review of the Joint Programmes, conducted in mid 2010, served as a beneficial exercise for examining the level of collaboration between JP agencies, and the opportunities for future synergies. In this respect it was observed that there were many areas of implementation in which agencies could and should work more closely together. This resulted in a more strategic planning exercise for the 2011 work plans and a renewed commitment to working in a more synergistic manner.

The Internal Review also highlighted the need for improved monitoring plans for the JP, and this has begun to be addressed through meetings and discussions on improvements to the monitoring matrix. The coordination workload, which falls on the lead agency, was seen as an impediment to the development of synergised plans, as the lead agency often does not have the requisite time to devote to the high level of coordination required.

### V.  Future Work Plan

This Joint Programme has further strengthened co-ordination and collaboration among UN Agencies in their support to National DRR Institutions, and particularly the INGC. The role of this JP as an overall framework for UN interventions in disaster preparedness, response and recovery was strengthened through reinforced synergies amongst UN agencies, which reinforces the idea that there are many opportunities to ‘Deliver as One’ and that strategies for joint implementation of activities in this field are now clearer.

The challenges for 2011 include the continuing decentralisation of Disaster Risk Reduction capacities (at provincial and district levels), improving intersectoral coordination, and information sharing.

The focus in 2011 will mainly be on the consolidation and completion of on-going activities, but key priority areas will include:

- Support to the integration of DRR in decentralization processes and policies implemented by GOM (DRR integrated in district plans is a particular priority).

- Increase dissemination of strategies and tools from national to provincial and district levels, and increase collaboration in the development of these tools.

- Adoption of the Strategy for the Reduction of Vulnerability and Sustainable Development in Flood Prone Areas in Mozambique.

- Decentralization and exit strategies to ensure empowerment of the communities directly impacted by the JP.

- Focus on empowering CTGCs at the provincial level and increased independent activity amongst the decentralized government actors (CTA hired to focus on decentralization).

- Strengthen emergency preparedness through definition,  dissemination and training related to standard operation procedures. Simulations should then be used to test these procedures.

- Two training sessions with community radio stations will be conducted  in Gaza and Zambezia provinces in early 2011to maximise the impact of the DRR training manual for community radio stations.

- Strengthen information management capacity at central and provincial levels.

- Increase capacity building for the inclusion of cross-cutting issues (Gender and HIV/AIDS), and increase the capacity of local communities and districts to communicate and access information with ease.

- UNDP, UN HABITAT, UNV and INGC will continue with an initiative that will represent the UN Volunteer’s contribution to the Joint Programme through recruitment of UN volunteers to work on DRR activities with INGC, with a special focus on the National Emergency Operational Centres (CENOE). The aim of this project is the transfer of knowledge, technical assistance and practical experiences at the regional, provincial and local levels.

- Support MICOA and other national partners in the implementation of the Strategy and Action Plan “Gender, Environment & Climate Change” through training and technical assistance.

- Continue with the efforts already started to establish a legal framework for DRR interventions with the specific aim of finalising a Disaster Management Act.

- Continue to build the capacity of CENOEs and COEs (Emergency operations centres at regional, provincial and district level).

- Strengthen efforts to revise the national Early Recovery Strategy with the involvement of all relevant stakeholders.

- Carry out the National Risk Assessment and conduct Seismic Risk assessments in Maputo and other major cities in Mozambique, and complete efforts already initiated to establish a National Disaster Observatory.

- Approval of a Code of Conduct to Prevent Sexual Exploitation and Abuse in emergency situations.

In order for these and other interventions to be implemented, the funding requirements   highlighted in the attached 2011 AWP will need to be met.

| 2011 Annual Work Plan |
| --- |
| EXPECTED RESULTS | KEY ACTIVITIES | TARGET BY AGENCY |  |  |  |  | UN AGENCY | PLANNED BUDGET |
|  |  |  | TIMEFRAME |  |  |
|  |  |  | Q1 2011 |  | Planned Amount | Available Funds (Parallel Funding Modality) | One Fund |
| 1. DRR and vulnerability reduction mainstreamed in national development plans and programmes | 1. Policy/Norms developed for humanitarian response, DRR and vulnerability reduction (Output 1.1) | 1.1. Provide technical assistance and knowledge to the further development and approval of the Disaster Management Act, especially in the areas of disaster preparedness, mitigation and early recovery mechanisms, making their link to long-term vulnerability reduction strategies more explicit. (All agencies)* | Draft disaster management law shared with various stakeholders | X | X | X | X | UNDP | 3,000 | 1,500 | 1,500 |
|  |  |  | Draft disaster management law inclusive of FSN aspects & support to right to food law | X | X | X | X | WFP | 15,000 | 5,000 | 10,000 |
|  |  |  | Strategy for the Reduction of Vulnerability and Sustainable Development in Flood Prone Areas in Mozambique adopted by the government | X | X | X | X | UN-HABITAT | 85,000 | 0 | 85,000 |
|  |  | 1.2. Develop joint advocacy activities linking disaster risk reduction to climate change. | Technical assistance provided and synergies developed | X | X | X | X | UNDP | 0 | 0 | 0 |
|  |  |  | WFP CO strategy document on DRR and climate change adaptation issues prepared; National Productive Safety Net Programme and | X |  |  |  | WFP | 35,000 | 20,000 | 15,000 |
|  |  |  | agricultural technical assistance guidelines linking DRR issue to climate change developed | X | X | X | X | FAO | 150,000 | 100,000 | 50,000 |
|  |  | 1.3. Support the integration of disaster risk reduction in the national decentralization framework. (UNDP & UN-HABITAT)* | DRR integrated in 10 district plans (1 district in each province - 4 district plans already have DRR mainstreamed)- | X | X | X | X | UNDP | 6,000 | 4,000 | 2,000 |
|  |  |  | 3 training sessions carried out |  | X | X | X | UN-HABITAT | 75,000 | 0 | 75,000 |
|  |  | 1.4. Develop guiding principles to mainstreaming DRR throughout the One UN. | DRR mainstreamed in UNDAF , and other UN Strategies | X | X | X | X | UNDP | 0 | 0 | 0 |
|  |  | 1.5. Ensure SRH, Gender and HIV components are included in thedevelopment of the Disaster Management Act and efforts to integrate EP and DRR in the decentralization framework. (Support from UNAIDS, UNIFEM & UNFPA to all agencies).* | Cross-cutting areas mainstreamed in DRR efforts carried out by various agencies |  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | X | X | X | X | UN WOMEN |  |  |  |
|  |  |  |  |  |  |  |  | UNAIDS | 0 | 0 | 0 |
|  |  | 1.6 Support dissemination and training on Code of Conduct to Prevent Sexual Exploitation and Abuse in emergency situations (with INGC) - (UNAIDS; UNIFEM)* | Code of Conduct approved and disseminated at national, provincial, district and community levels and amongst humanitarian actors. |  |  | X | X | UNFPA | 30,000 | 0 | 30,000 |
|  |  |  | INGC Ethical Code of Conduct for Humanitarian Workers for the Prevention of Sexual Abuse and Exploitation in Emergency Settings adopted by the government and disseminated | X | X | X | X | UNICEF | 20,000 | 0 | 20,000 |
|  |  | 1.7 Support the design and implementation/administration of the Common Fund for DRR | Disaster Risk Management Common Fund approved and under implementation | X | X |  |  | UNDP | $6,000.00 | $6,000.00 | 0 |
|  | 2. DRR mainstreamed in national development plans and programmes (Output 1.2) | 2.1. Undertake targeted advocacy in key development sectors to promote the development of policy and regulatory tools, promoting lessons learned and best practices from other countries in the region.(UNDP, WFP)* | 2 exchange of experiences visits bygovernment. officials to countries that have good practices in DRR |  |  | X |  | UNDP | 20,000 | 18,000 | 2,000 |
|  |  |  | Participate in regional and international forums; exchange visits |  |  | X | X | WFP | 50,000 | 20,000 | 30,000 |
|  |  |  | Technical assistance provided | X | X | X | X | UN-HABITAT | 0 | 0 | 0 |
|  |  | 2.2. Promote Discussion of Government Emergency Preparedness and DRR priorities in sector specific development and humanitarian assistance for SWAPs, Clusters, etc. (WHO & UNICEF)* | Capacity of the WASH cluster enhanced (coordination and leadership on emergencies and climate change adaptation). 1 workshop on climate change held and emergency coordination meetings conducted. | X | X | X | X | UNICEF | 15,000 | 15,000 | 0 |
|  |  |  | Capacity of MOH and NGOs increased and joint training carried out at central and in some targeted provinces as well as coordination and monitoring of health cluster activities | X | X | X | X | WHO | 22,500 | 5,000 | 17,500 |
|  |  | 2.3. Provide Technical Assistance to line ministry counterparts in order to integrate DRR norms into development frameworks such as PES, PARPA, Agenda 2025, etc. | Technical assistance provided on emergency preparedness and DRR to ensure the integration of the Core Commitments to Children in emergency preparedness and response. DRR and emergency tools developed containing the core commitments to Children in Emergencies | X | X | X | X | UNICEF | 20,000 | 3,000 | 17,000 |
|  |  |  | Support to the implementation of the MICOA Gender, Environment and Climate Change Action Plan provided through a Gender Advisor and financial support to the action plan | X | X | X | X | UN WOMEN | 265,000 | 265,000 | 0 |
|  |  |  | Support preparation of food security study for CC adaptation national strategy |  |  |  |  | WFP | 50,000 | 0 | 50,000 |
|  |  |  | Clear indicators for cross cutting issues in PARPA & UNDAF (TA) | X | X |  |  | WFP | 40,000 | 0 | 40,000 |
|  |  |  | Technical assistance provided on emergency preparedness and DRR including emergency and DRR tools | X | X |  |  | WHO | 7,500 | 5,000 | 2,500 |
|  |  | 2.4. Provide technical assistance for supporting the development of an institutional framework and strategy for early recovery. (UNDP, UN-HABITAT)* | Early Recovery Strategy approved and Institutional Framework established |  | X |  |  | UNDP | 15,000 | 11,000 | 4,000 |
|  |  |  | Technical Assistance |  |  |  |  | UN WOMEN | 0 | 0 | 0 |
|  |  |  | Technical Assistance |  |  |  |  | UN-HABITAT | 0 | 0 | 0 |
|  | TOTAL OUTPUT 1 | 930,000 | 478,500 | 451,500 |
| 2. Government and Civil Society capacities for disaster risk reduction strengthened at central, provincial and local levels. | 3. Central, provincial and district level institutions strengthened for disaster risk reduction, contingency planning and emergency preparedness and response. (Output 2.1) | 3.1. Provide technical and financial assistance for the development and dissemination of EP, DRR and vulnerability reduction tools and guidelines. To include guidelines on public health interventions, including the surveillance and control of communicable diseases such as cholera and malaria, mental, environmental health and guidelines on sexual and reproductive health and HIV prevention. (All agencies - joint tool development)* | Curriculum for DRR in schools developed; Manuals, tools and guidelines for local risk management committees and facilitators produced | X | X |  |  | UNDP | 20,000 | 10,000 | 10,000 |
|  |  |  | Contingency plans translated, with current food security situation, and disseminated. | X |  | X |  | WFP | 30,000 | 25,000 | 5,000 |
|  |  |  | INGC / UN Women toolbox on gender and DRR and CC finalized;Crosscutting issues strategy for INGC developed (UNAIDS to collaborate) | X | X | X | X | UN WOMEN | 184,658 | 88,158 | 96,500 |
|  |  |  | Guidelines to integrate gender aspects in DRR and EP tool disseminated (UNAIDS to collaborate) | X | X | X | X | UNFPA | 20,000 | 0 | 20,000 |
|  |  |  | Tools and guidelines on shelter, social and basic services and spatial planning produced. Dissemination of the booklet "A minha aldeia" in resettlement areas along the Zambezi valley | X | X | X | X | UN-HABITAT | 63,000 | 0 | 63,000 |
|  |  |  | Disaster response plans, with a focus on shelter and land use planning, developed by Provincial Public Works and Environmental Directorates | X | X | X | X | UN-HABITAT | 0 | 0 | 0 |
|  |  |  | Tools and guidelines on public health interventions, including the surveillance and control of communicable diseases such as cholera and malaria, mental and environmental health, developed | X | X | X | X | WHO | 75,000 | 15,000 | 60,000 |
|  |  | 3.2 Provide capacity building / training / kits for local risk management committees | Refresher training for 90 Committees to be provided. Emergency Kits to be provided for 60 committees | X | X | X | X | UNDP | 165,000 | 85,000 | 80,000 |
|  |  |  | 12 Emergency kits to be provided to Local Committees |  |  | X | X | WFP | 60,000 | 0 | 60,000 |
|  |  | 3.3 Creation of risk management committees in cities | 12 Committees established in 2011 |  | X | X |  | UNDP | 4,000 | 4,000 | 0 |
|  |  | 3.4. Strengthen capacity of the regional CENOEs and provincial COEs with the provision of telecommunications equipment and on-the-job training | Construction support and equipment and related training provided to provincial COES | X | X | X | X | UNDP | 80,000 | 56,800 | 23,200 |
|  |  |  | CENOE staff trained on ICT and equipment provided |  | X | X |  | WFP | 100,000 | 44,000 | 56,000 |
|  |  | 3.5.Support malaria prevention activities | LLINS for vulnerable people distributed through universal access campaigns and during emergencies, and IEC activities for malaria prevention and sensitization. Number of nets distributed depends on the needs during the emergency. | X | X |  |  | UNICEF | 150,000 | 83,000 | 67,000 |
|  |  | 3.6 Strengthen the capacity of all WASH partners for emergency preparedness / response, planning and effective monitoring and supervision of programme activities, including management of UNICEF resources | WASH Contingency Plan prepared and implemented, including an update of WASH emergency supply inventory and human resources and the pre-positioning of emergency supplies | X | X | X | X | UNICEF | 15,000 | 15,000 | 0 |
|  |  |  | 2 training sessions delivered to clusters (Sofala and Tete) and gender mainstreaming tools produced to support WASH, Nutrition, and Education / Protection Clusters to integrate gender into their preparedness and response, both at national level and local level. | X |  |  |  | UNICEF | 0 | 0 | 0 |
|  |  | 3.7. Provide technical support to line ministries in the development and implementation of sector specific emergency preparedness, contingency and response plans, including HIV/AIDS, Reproductive Health and Gender. | Support provided to MoH in emergency preparedness and response in the area of HIV (PEP kits pre-positioned in emergency prone area) | X | X | X | X | UNICEF | 20,000 | 10,000 | 10,000 |
|  |  |  | Support to MoH in emergency preparedness and response provided, including new health kits and technical support at provincial level for contingency plan including HIV/AIDS in Emergencies | X | X | X | X | WHO | 120,000 | 15,000 | 105,000 |
|  |  |  | Sector specific goods pre-positioned for emergency response in Sexual and Reproductive Health and HIV (clean delivery kits and condoms prepositioned in emergency prone areas) - UNAIDS to collaborate |  |  | X | X | UNFPA | 30,000 | 0 | 30,000 |
|  |  |  | Technical support to HCT and cluster focal points for cross cutting issues provided through meetings with focal points and workshop on the IASC Gender and HIV Marker. | X | X | X | X | UN WOMEN | 23,000 | 0 | 23,000 |
|  |  | 3.8. Support training at all levels for Emergency Preparedness, DRR, Minimal Initial Service Package (MISP), HIV/AIDS guidelines, gender guidelines, shelter and spatial planning, surveillance and control of communicable diseases, and nutrition | 11 Provincial INGC officers trained as trainers in DRR | X | X | X |  | UNDP | 20,000 | 16,000 | 4,000 |
|  |  |  | Training in DRR carried out at decentralised level (for administrators, head of administrative post, district permanent secretaries, directors of planning and infrastructure, provincial secretaries) | X | X | X | X | UNDP | 48,600 | 23,600 | 25,000 |
|  |  |  | International technical training (GIS, information management) provided for INGC- DPM and INAM staff | X | X | X | X | UNDP | 83,000 | 43,000 | 40,000 |
|  |  |  | Decision makers, 1000 beneficiary farmers, 100 extension workers and lead farmers trained on DRR and integration into agricultural programmes | X | X | X | X | FAO | 150,000 | 35,000 | 115,000 |
|  |  |  | Health focal points on disaster prone areas trained in Minimal Initial Service Package (MISP) |  | X | X | X | UNFPA | 50,000 | 10,000 | 40,000 |
|  |  |  | Training provided on the surveillance and control of communicable diseases such as cholera and malaria, including targeted districts at risk, as well as stockpiling | X | X | X | X | WHO | 225,000 | 20,000 | 205,000 |
|  |  |  | 400 Health Workers trained on the revised Manual for Nutrition Rehabilitation | X | X | X | X | UNICEF | 450,000 | 260,000 | 190,000 |
|  |  |  | Training materials produced and Protection / Education Cluster Members trained in (1) child rights and women's rights national legal framework and (2) psycho-social support in emergencies. | X | X | X | X | UNICEF | 30,000 | 0 | 30,000 |
|  |  |  | Emergency food security assessment training |  | X |  |  | WFP | 40,000 | 35,000 | 5,000 |
|  |  |  | GIS training provided to 20 UNAPROC members. |  |  | X |  | WFP | 30,000 | 0 | 30,000 |
|  |  | 3.9 Support emergency nutrition interventions when needed | Therapeutic foods (therapeutic milk and/or RUTFs) procured, and children affected by severe malnutrition identified through national surveillance. | X | X | X | X | UNICEF | 150,000 | 40,000 | 110,000 |
|  |  | 3.10. Strengthen the capacities of the protection sector to respond to an emergency, including strengthening the Government's systems to monitor and report on violence against children at national and provincial levels | Minimum standards for care and support for OVCs have been finalized and integrated, including in emergency settings. | X | X | X | X | UNICEF | 10,000 | 10,000 | 0 |
|  |  | 3.11. Support awareness-raising activities on Gender Based Violence, HIV/AIDS and Gender in emergencies and resettlement contexts (with INGC, MMAS, and NAFEZA) | Disaster risk management and prevention integrated in ministries and Civil Society Organizations, and UNAPROC plans and sensitization activities implemented in communities. UNAIDS to collaborate | X | X | X | X | UNFPA | 100,000 | 0 | 100,000 |
|  |  | 3.12. Strengthen the MEC capacity in emergency preparedness and response. | Technical assistance provided to monitor multi-sectoral (education and protection) preparedness and planning capacity in 7 disaster prone provinces; database finalised and coordination support provided for the Education and Protection Cluster. | X | X | X |  | UNICEF | 30,000 | 20,000 | 10,000 |
|  |  |  | Technical support to health school programme in disaster prone affected districts | X | X | X | X | WHO | 150,000 | 30,000 | 120,000 |
|  |  | 3.13. Contribute technical and financial support for simulation exercises. | Simulation exercise realised at various levels |  |  | X |  | UNDP | 25,000 | 15,000 | 10,000 |
|  |  |  | Emergency procedures protocols and response plans improved and used in simulation exercises |  | X | X |  | UNDP | 15,000 | 10,000 | 5,000 |
|  |  |  | Support to national simulation |  |  | X |  | WFP | 15,000 | 10,000 | 5,000 |
|  |  |  | High level CTGC staff trained on emergency response/ reaction |  | X |  |  | WFP | 100,000 | 10,000 | 90,000 |
|  |  |  | Simulation exercise realized at various levels and ensuring that Core Commitments to Children in Emergencies is applied during the simulation. |  |  | X |  | UNICEF | 15,000 | 15,000 | 0 |
|  |  | 3.14. Ensure the distribution of dignity kits to the most vulnerable populations affected by natural disasters, especially women, children heads of families, the elderly and disabled people. | Dignity kits distributed in timely manner to most vulnerable groups | X |  |  | X | UNFPA | 75,000 | 30,000 | 45,000 |
|  |  | 3.15 Institutional support to INGC | 15 Motorbikes provided for use by DPM |  | X |  |  | UNDP | 50,000 | 25,000 | 25,000 |
|  |  |  | 5 motorbikes provided |  |  | X |  | WFP | 50,000 | 0 | 50,000 |
|  |  |  | Two national meetings held (plan & balance); dissemination of daridas guide | X |  |  | X | WFP | 100,000 | 0 | 100,000 |
|  |  |  | Support to financial management capacity in INGC provided (financial advisor and assistant) | X | X | X | X | UNDP | 80,000 | 0 | 80,000 |
|  |  |  | Technical advisor for DARIDAS placed | X | X | X | X | UNDP | 80,000 | 80,000 | 0 |
|  | 4.Inter-sectoral coordination capacity for DRR and Emergency Preparedness strengthened at central, provincial and district level | 4.1. Disseminate district food security and vulnerability profiles and risk mapping at provincial level | Editing and multiplication of 20 district profiles & risk mapping completed; two provincial workshops held | X |  |  | X | WFP | 150,000 | 5,000 | 145,000 |
|  |  | 4.2. Strengthen the capacity of the CTGC at national and provincial levels as a forum for more effective inter-sectoral coordination through technical assistance to the INGC and Line Ministry members. | Training provided for CTGC members on 3 areas; DRR Mainstreaming; role of CTGC members and functioning of Central to District structures; monitoring of DRR sectoral activities |  | X | X |  | UNDP | 35,000 | 23,000 | 12,000 |
|  |  |  | 5 training sessions for CTGC at provincial level conducted. | X | X | X | X | WFP | 80,000 | 10,000 | 70,000 |
|  |  |  | At least 4 technical assistance meetings carried out at national and provincial levels. | X | X | X | X | UN-HABITAT | 50,000 | 0 | 50,000 |
|  |  |  | Technical assistance on Emergency Preparedness and DRR provided, including central and provincial level | X | X | X | X | WHO | 15,000 | 5,000 | 10,000 |
|  |  | 4.3 Provide technical assistance to develop a multi-sectoral package of Emergency Preparedness, contingency planning and response tools for use by national and international humanitarian actors, including for assessment, registration, monitoring and evaluation. | Tools developed for the integration of the Core Commitments to Children in Emergency in emergency preparedness and response. | X | X | X | X | UNICEF | 35,000 | 15,000 | 20,000 |
|  |  |  | Support to depth health assessment and rapid alert investigation of outbreaks and team support for control of outbreaks in the affected populations at provincial level | X | X | X | X | WHO | 105,000 | 20,000 | 85,000 |
|  | 5. Participatory projects implemented to engage communities in disaster risk and vulnerability reduction and emergency preparedness (Output 2.3) | 5.1. Provide technical assistance to carry out vulnerability analyses, including sector specific analysis, in identified disaster prone districts to prioritise communities for implementing disaster risk reduction, mitigation and vulnerability reduction activities. | Emergency response activities coordinated through rapid assessment and delivery of supplies to schools to enable the rapid resumption of schooling; education materials pre-positioned. | X | X |  |  | UNICEF | 30,000 | 20,000 | 10,000 |
|  |  |  | Needs assessments and vulnerability assessments supported through SETSAN or Provincial Agricultural Directorates | X | X | X | X | FAO | 100,000 | 35,000 | 65,000 |
|  |  |  | 2 vulnerability analyses carried out |  | X |  | X | UN-HABITAT | 50,000 | 0 | 50,000 |
|  |  |  | Support in vulnerability assessment and mapping of high risk districts provided | X | X | X | X | WHO | 24,000 | 5,000 | 19,000 |
|  |  |  | Urban VA in conducted in Maputo / Matola, Tete, Beira & Nampula | X | X |  | X | WFP | 255,000 | 250,000 | 5,000 |
|  |  | 5.2 Support vulnerability assessments with SETSAN and INGC | 2 VA completed. | X | X | X | X | WFP | 70,000 | 0 | 70,000 |
|  |  | 5.3 Implement productive safety nets (risk reduction and climate change adaptation) through FFW or Cash / vouchers. | In place in 14 districts (Caia, Marromeu, Buzi, Mutarara, Magude, Chicualacula, Matutuine, Chibuto, Chigubo, Panda, Funhalouro, Macossa, Chemba, Machanga, Chibabava) covering 40,000 beneficiaries | X | X | X | X | WFP | 2,500,000 | 2,000,000 | 500,000 |
|  |  | 5.4. Support identified communities in participatory planning and implementation of priority interventions from EP and DRR action plans, including vulnerability reduction measures. | 1 provincial and 4 district participatory meetings held; 1,000 direct beneficiaries supported on participatory DRR linked to agriculture activities |  |  |  |  | FAO | 80,000 | 30,000 | 50,000 |
|  |  |  | Community training sessions on FSN and risk 15 conducted | X | X | X | X | WFP | 30,000 | 0 | 30,000 |
|  |  |  | 10 participatory planning meetings carried out in Angoche (6), Mogincual (3) and Manica (1) districts; Cyclone resistant demonstration models developed, tested and replicated at community level in Angoche and Mogincual; Architectural models for housing construction more resistant to cyclones and earthquakes submitted to government for adoption. | X | X | X | X | UN-HABITAT | 240,000 | 140,000 | 100,000 |
|  |  | 5.5. Strengthen civil society capacity through development of a portfolio of local risk reduction management initiatives to be executed by NGOs. | Small grants provided to NGOs, in collaboration with DARIDAS, DPM and provincial NGO forums | X | X | X | X | UNDP | 331,900 | 184,900 | 147,000 |
|  |  | 5.6 Reduce vulnerability and risk reduction for communities living in drought prone areas | Income generation projects realised in Chiibuto district | X | X | X | X | UNDP | 170,540 | 118,500 | 52,040 |
|  |  | 5.7 Training of teachers in schools on introduction of DRR in school curriculum | Training carried out in 20 schools |  | X | X |  | UNDP | 40,000 | 20,000 | 20,000 |
|  |  |  | In collaboration with SAVE, the development of a strategy on disaster risk reduction in pilot provinces supported | X | X |  |  | UNICEF | 0 | 0 | 0 |
|  |  | 5.8. Promote communication and social mobilization activities and public awareness campaigns for DRR, Emergency Preparedness and related public health issues (cholera, malaria and HIV) through radio, community theatre, posters, leaflets and community activists | Social change communication tools and materials focused on migration health in emergencies developed and disseminated in 6 Provinces. |  | X | X | X | IOM | 40,000 | 0 | 40,000 |
|  |  |  | Production and distribution of Health promotion materials (waterborne diseases) including communication and mobilsation activities in provinces at risk | X | X | X | X | WHO | 135,000 | 30,000 | 105,000 |
|  |  |  | Social mobilisation strategy integrating gender and HIV aspects prepared. UNAIDS to collaborate | X | X | X | X | UNFPA | 5,000 | 0 | 5,000 |
|  |  |  | IEC material distributed and communication and mobilisation activities carried out in at least three provinces and five districts (C4D activities) |  |  |  |  | UNICEF | 100,000 | 50,000 | 50,000 |
|  |  | 5.9 Support the development of community awareness tools and materials on floods, cyclones and earthquakes. | DRR awareness materials (floods, cyclones and earthquakes) developed and disseminated | x | x | x | x | UNDP | 48,550 | 34,200 | 14,350 |
|  |  |  | Awareness materials to mitigate the impact of future earthquakes developed; Dissemination of the manual "construir com os ventos" in 9 communities in Angoche and Mogincual; Dissemination of the video "As vezes o Rio" in flood prone areas. |  |  | X | X | UN-HABITAT | 50,000 | 0 | 50,000 |
|  |  |  | Technical assistance meetings held |  | X | X |  | UN-HABITAT | 20,000 | 0 | 20,000 |
|  |  | 5.10 Support the inclusion of agricultural risk and vulnerability reduction efforts in community plans, such as Input Trade Fairs, Conservation Agriculture, Water Management and Trans-boundary Animal Disease Management. | 4 small-scale irrigation schemes established, including training for 2000 farmers on water management techniques; 2000 beneficiary farmers supported with Conservation Agriculture technologies; 2000 beneficiary farmers supported with seeds and agricultural implements (e.g. jab planters for CA) | X | X | X | X | FAO | 750,000 | 120,000 | 630,000 |
|  |  | 5.11. Support populations in emergency prone areas with facilities and supplies for drinking water, treatment and for environmental sanitation. | Water points in areas affected by floods, cholera and cyclones constructed / rehabilitated; water treated and distributed to affected areas and households, and community latrines constructed. Target- 25,000 people assisted | X | X | X | X | UNICEF | 230,000 | 230,000 | 0 |
|  |  | 5.12 Support training activities of activists in refugee center in Marretane on SRH and Gender-Based Violence | Peer educators in Adolescent Sexual and Reproductive Health trained to spread information on Gender and HIV and AIDS in Maretane refugee camp. UNAIDS to collaborate |  | X | X |  | UNFPA | 30,000 | 0 | 30,000 |
|  |  | 5.13. Ensure community based assessments and risk reduction efforts include SRH, Gender and HIV components. UNAIDs to collaborate | Tools developed that are gender and HIV sensitive and include HIV and AIDS aspects | X | X | X | X | UNFPA | 0 | 0 | 0 |
|  |  | 5.14 Support expansion of capacity building of TARPA tents in disaster prone provinces | TARPA tent capacity building extended in disaster prone provinces. Target: 7 districts | X | X |  |  | UNICEF | 30,000 | 20,000 | 10,000 |
|  | TOTAL OUTPUT 2 | TOTAL OUTPUT 2 |  |  |  |  |  |  | 9,161,248 | 4,554,158 | 4,607,090 |
| 3. National Information System set up for disaster risk reduction | 6. Early Warning System (EWS) strengthened for natural hazards at central, provincial and local levels (Output 3.1) | 6.1. Provide technical assistance and tools for strengthening flood EWS at central, provincial and district levels, including through EWS simulations to test early warning information flows and assess response capacity. | Community based Flood EWS in operation in Licungo river basin; information on flood early warning systems to be disseminated nationally | x | x | x | x | UNDP | 390,500 | 158,800 | 231,700 |
|  |  |  | District and communities of Angoche and Mogincual strengthened on EWS issues |  |  | X | X | UN-HABITAT | 0 | 0 | 0 |
|  |  | 6.2. Enhance national early warning capacities through the strengthening of systems and the training of relevant staff at national, provincial and district levels. | Technical assistance to early warning capacity at SETSAN supported. | X | X | X | X | FAO | 60,000 | 10,000 | 50,000 |
|  |  |  | Capacity development with UEM and SETSAN and INGC carried out | X | X | X | X | WFP | 30,000 | 30,000 |  |
|  |  | 6.3. Strengthen existing national disaster risk information systems, through the implementation of the GRIP (global risk identification project) | Disaster database and disaster observatory operational; urban risk assessment completed; national risk assessment completed | x | x | x | x | UNDP | 106,400 | 78,000 | 28,400 |
|  |  | 6.4 Preparation of district mapping and profiling | Risk mapping carried out for 5 districts |  | X | X | X | WFP | 90,000 | 10,000 | 80,000 |
|  |  |  | 11 district profiles for food security and nutrition profiles completed (Mutarara, Magude, Massingir, Govuro, Panda, Massinga, Cabora-Bassa, Changara, Magoe, Memba, Machanga) |  | X | X |  | WFP | 200,000 | 20,000 | 180,000 |
|  |  | 6.5 Support early monitoring and action, through monitoring and support as well as secondary data collection | EW bulletins regularly issued and shared with HCT/ FS cluster | X | X | X | X | WFP | 70,000 | 20,000 | 50,000 |
|  |  |  | CTGC linked to FS cluster planning and response; 12 FS cluster meetings held | X | X | X | X | WFP | 10,000 | 4,000 | 6,000 |
|  |  | 6.6. Support SETSAN planning and surveillance capacity (FAO, WFP, WHO)* | Technical and financial support provided for vulnerability assessments | x | x | x | x | UNICEF | 10,000 | 10,000 | 0 |
|  |  |  | Technical assistance provided to SETSAN for vulnerability assessments. | X | X | X | X | FAO | 50,000 | 10,000 | 40,000 |
|  |  |  | Technical and financial support provided for vulnerability assessments | x | x | x | x | WFP | 10,000 |  | 10,000 |
|  |  | 6.7 Improve links between EWS stakeholders (INGC, FEWS Net, SETSAN) through better communication and information dissemination and strengthen sector stakeholder contributions with technical assistance. | CTGC, early warning meetings attended; 12 cluster meetings promoted;Production of EW communication material supported | X | X | X | X | FAO | 60,000 | 10,000 | 50,000 |
|  |  | 6.8. Support risk identification at community level through periodic direct consultations and awareness raising efforts on risks through radio programming. | Three DRR radio dramas focusing on flood and cyclone prone regions produced |  |  |  |  | IOM | 50,000 | 0 | 50,000 |
|  |  | 6.9 Strengthen the capacity of existing community radio stations in disaster prone districts through the training of community radio staff and increasing broadcast range and provide standardised programming materials for disaster preparedness. | Community radio stations in Caia, Marromeu, Mutarara, Morrumbala, Xai-Xai, Chibuto, Mabalane and Mazivila, Nampula, Nacala, Monapo, Namialo, Mossuril, Ilha de Mocambique, Iuluti and Angoche rehabilitated. | X | X | X | X | IOM | 721,500 | 0 | 721,500 |
|  |  | 6.9. Establish community radio stations in disaster prone districts where no radio presently exists. | Assessment in Massingir, Nametil and Moma districts conducted. |  | X | X |  | IOM | 6,000 | 0 | 6,000 |
|  | Information sharing and knowledge management strengthened between the different sectors for preparedness, contingency planning, response and early recovery | 7.1. Support the institutionalization of M&E Toolkit / Database and reestablishment of TAD info within MINAG (Veterinary Services) | Distribution of CA M&E toolkit increased | X | X | X | X | FAO | 30,000 | 5,000 | 25,000 |
|  |  | 7.2 Creation and introduction of an online database for management of goods and logistics at national level | Database created in collaboration with WFP |  | x |  |  | UNDP | 15,000 | 0 | 15,000 |
|  |  |  | Database created in collaboration with UNDP |  | X |  |  | WFP | 10,000 | 0 | 10,000 |
|  |  | 7.3 Improve the rapid assessment process through adaptation / analysis of existing IRIS database in CENOE | IRIS database in use | x |  |  |  | UNDP | 3,000 | 0 | 3,000 |
|  |  | 7.4 Capacity building in systematic recording and processing of information related to disasters (GRIP, Information Management, data collection and analysis, terminology, disaster observatory) | Training held for total of 60 people in South, North and Central Regions |  | x |  |  | UNDP | 46,000 | 41,000 | 5,000 |
|  |  | 7.5 Capacity building / international training for CENOE Staff | Training for 5 CENOE officers conducted |  | x | x |  | UNDP | 20,000 | 10,000 | 10,000 |
|  |  | 7.6 Human resource support to CENOE | 3 contractors for support to IT and to CENOE identified | x | x | x | x | UNDP | 13,000 | 13,000 | 0 |
|  | TOTAL OUTPUT 3 |  |  |  |  |  |  |  | 2,001,400 | 429,800 | 1,571,600 |
| TOTAL BUDGET |  |  |  |  |  |  |  |  | 12,092,648 | 5,462,458 | 6,630,190 |

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.

Please note that Mitigation in the disaster risk reduction community has a different meaning when compared with terminology in the climate change community (where it refers to reduction of carbon emissions)

# Text boxes

| Acronyms: CENOE - National Emergency Operations Centre COE – Emergency Operations Centre CPFA- Centro Provincial de Formação Agraria (provincial centre for agrarian training) CTGC - Conselho Técnico de Gestão das Calamidades (technical council for disaster management) DARIDAS- Directorate for Arid and Semi Arid Zones DNA- National Directorate for Waters DPOPH – Provincial directorates for Public Works and Housing DRM - Disaster Risk Management DRR - Disaster Risk Reduction ECHO - European Commission for Humanitarian Aid and Civil Protection EWS - Early Warning System GRIP – Global Risk Identification Programme HCTWG – Humanitarian Country Team Working Group HFA - Hyogo Framework for Action IASC – Inter-Agency Standing Committee IDSR - Integrated Disease Surveillance and Response IHR- International Health regulations INGC - National Disaster Management Institute JP - Joint Programme LLIN- Long Lasting Insecticidal Net MEC - Ministry of Education and Culture MICOA - Ministry for the Coordination of Environmental Affairs MINED- Ministry for Education MINT -Ministry of the Interior MISAU-Ministry of Health MMAS- Ministry of Women and Social Affairs MOPH- Ministry of Public Works and Housing OVC- Orphans and Vulnerable Children PAP-Programme Aid Partnership PARPA-Action Plan for the Reduction of Absolute Poverty PMT- Programme Management Team SADC- Southern African Development Community SRH- Sexual and Reproductive Health TDU- Training and Demonstration Unit UEM – University Eduardo Mondlane UNAPROC- National Entity for Civil Protection UNDAF- UN Development Assistance Framework UNICEF- United Nations Childrens Fund WHO- World Health Organisation YFS- Youth Friendly Services |  | Programme Duration/Closed Programme: 2007-2009 (extended to 2011) |
| --- | --- | --- |

Report Formatting Instructions

Kindly review the instructions below and follow them in the preparation of your report

- Do not put the narrative text into boxes and do not incorporate boxes, graphs, etc. into the narrative report.

- Add additional information including charts, graphs, etc. as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative.

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point Times New Roman & do not use colours.