### FUTURE WORK PLAN 2011

- Support the government in the implementation of key interventions defined in the PNI to achieve MDGs 4 and 5 to ensure the continuum of care.

- Support the government in the consolidation of the RED approach in 66 existing districts selected as of 2010 through routine interventions and through national health weeks, as well as assist in facilitating dialogue with the MoH and partners on the use of RED as platform for health system strengthening.

- Given the limited access to health facilities, a key priority for addressing the burden of malaria is to support community-based preventive and curative health services.  Support will be given for the reinforcement of IMNCI and C-IMNCI in focused districts. Support will be provided for the distribution and social mobilization of the effective use of bed nets procured by funds from the Gloabal fund (GFATM).

- Improve the nutritional status of children by improving the Basic Nutrition Package, Micronutrient Supplementation, further strengthening Outpatient Treatment for SAM and MAM with community involvement, and further strengthening the fortification of iodised salt and staple foods.

Estimated Budget Required: Period 2011

| Agency | Total Budget (US$) | Total Allocated (US$) | Total Unfunded (2011 AWP requirement) |
| --- | --- | --- | --- |
|  |  | Agency resources | Balance from 2010 JP |  |
| UNFPA | 1,740,787 | 256,976 | 246,996 | 1,236,815 |
| UNICEF | 3,430,000 | 1,508,700 | 0 | 1,921,300 |
| WFP | 1,900,000 | 700,000 | 0 | 1,200,000 |
| WHO | 1,290,000 | 115,000 | 269,120 | 835,880 |
| Total | 8,360,989 | 3,096,792 | 516,116 | 5,193,995 |

UN Mozambique

Title: Enhance the Quality and Accessibility of Sexual and Reproductive Health Services, Neonatal, Child Health Services and Nutrition. (One UN Joint Programme)

UNDAF Outputs:    2.2.3, 2.2.4, 2.2.5; 2.2.6

UNDAF Pillar Outcomes:

Human Capital:  Increased access to and use of quality basic services and social protection for the most disadvantaged populations, particularly children, youth and women, to reduce their vulnerability by 2011.

Expected UNDAF CP Outcomes:

HC 2.2 Access to and use of quality basic health services increased, especially for the most disadvantaged populations.

Expected UNDAF CP Outputs:

HC: 2.2.1 MDGs 4 and 5 well reflected in the national and provincial plans; 2.2.2 Improved access to SRH services through the implementation of defined interventions packages; 2.2.3 Reinforced implementation of institutional & community IMNCI at all levels, including the neonatal component; HC 2.2.4 At least 95% of 1 year old children are fully immunised through implementation of the RED (Reaching Every District) approach in 99 districts; HC 2.2.5 Malaria treatment and prevention packages (ACTs, IPT, home based treatment, LLINs) implemented in all districts; HC 2.2.6  Capacity of the health sector enhanced for emergency preparedness and response to reduce mortality and morbidity levels in districts affected by natural disasters and high cholera incidence; 2.2.7. Health Information System providing quality disaggregated data on key variables in accordance with international guidelines for the collection of selected indicators of health; 2.2.10 The capacity of the MoH enhanced to improve health promotion, and 2.2.11. Expansion of the treatment of moderate malnutrition to children 6-59 months of age from 22 districts to 72 districts

Implemented by: Ministry of Health (MoH),

Other Partners: MIC, INNOQ, Save the Children, PSI, Malaria Consortium, HKI, other NGOs, USAID,

Agreed by Ministry of Health: __________________________________________

Agreed by (UN Agency): _________________________________________________

UN Mozambique Annual Work Plan

Implementing Partner

FACE authorization specimen:

-------------------------------------

Name and Title: Enhance the Quality and Accessibility of Sexual and Reproductive Health Services, Neonatal, Child Health Services and Nutrition.

| Component 1: |  |
| --- | --- |
| CPAP Output(s): |  |
| EXPECTED RESULTS | KEY ACTIVITIES | TIMEFRAME (2011) | RESPON-SIBLE PARTY | PLANNED BUDGET | Unfunded Amount |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Planned Amount | Amount Allocated | Source of Funds |  |
| Output 1. Development and/or formal approval of the key strategic documents to support access, quality and use of maternal, neonatal and child health services and nutrition supported | 1.1.Key MNCH policy documents approved, reproduced and disseminated, including nutrition component | x | x |  |  | MISAU |  |  |  |  |
|  |  |  |  |  |  | WHO, | 30,000 | 15,000 | WHO -RR | 15,000 |
|  |  |  |  |  |  | UNFPA, UNCEF & WFP |  |  |  |  |
|  | 1.2. Reproduce and disseminate the orientation / advocacy package on MNCH for key stakeholders; IEC materials, media, protocols and norms; |  | x |  |  | MISAU |  |  |  |  |
|  |  |  |  |  |  | WHO | 30,000 | 15,000 | WHO - RR | 15,000 |
|  |  |  |  |  |  | UNFPA | 150,000 | 120,000 | UNFPA OR | 30,000 |
| Output 2 Capacity for planning, monitoring and evaluation of maternal & child health and nutrition programmes at national and sub-national level strengthened. | 2.1. Report on the National Integrated Plan (NIP) for MDG 4 and 5 implementation progress | x | x |  |  | WHO, UNFPA, UNICEF & WFP MISAU | 0 | 0 | 0 | 0 |
|  | 2.2 Translate and adapt the RMR tool and train health managers on the RMR process |  |  |  |  | WHO | 50,000 | 30,000 | OR | 20,000 |
|  | 2.3.Revise and update the NIP for MDG 4 and 5 |  | x |  |  | WHO, UNFPA, UNICEF & WFP | 20,000 | 10,000 | WHO- OR | 10,000 |
|  |  |  |  |  |  | MISAU |  |  |  |  |
|  | 2.4. Train district/ provincial MNCH programme managers on planning, M&E and MNCH programmes | x | x | x | x | WHO MISAU | 80,000 | 40,000 | OR | 40,000 |
|  | 2.5 Conduct an IMCI Health Facility Survey |  |  |  | x | MISAU, WHO | 120,000 | 39,120 | OR | 80,880 |
| Output 3 Government & community capacity improved for the implementation of integrated MNCH and nutrition key interventions including specific nutrition interventions in RED- Plus districts. | 3.1 Support the planning and implementation of 2 rounds of National Health Weeks for mothers and children |  | x |  | x | MISAU, DPSs |  |  |  |  |
|  |  |  |  |  |  | WHO | 200,000 | 55,000 | WHO OR | 145,000 |
|  |  |  |  |  |  | UNFPA | 574,899 | 298,664 | UNFPA- OR | 276,235 |
|  |  |  |  |  |  | UNICEF | 630,000 | 200,000 | UNICEF-OR | 430,000 |
|  | 3.2. Support implementation, monitoring and supportive supervision of IMNCI and C-IMNCI activities at provincial, district & HF levels in RED districts. (provide 66 Neonatal resuscitation kits to 33 maternities ) | X | X | x | X | MOH |  |  |  |  |
|  |  |  |  |  |  | UNICEF | 100,000 | 10,000 | UNICEF RR | 90,000 |
|  |  |  |  |  |  | WHO | 60,000 | 50,000 | WHO-RR | 10,000 |
|  | 3.3. Support training and refresher course for 300 health workers in IMNCI, ENBC and neonatal resuscitation /EmOC in RED districts, corresponding to 50% of PES training plan (at least 150 trained in Emergency Neonatal care/EmOC and 150 trained in IMNCI) | x | X | X | X | MOH UNICEF WHO | 100,000 100,000 | 10,000 50,000 | UNICEF –RR - WHO-OR | 90,000 50,000 |
|  | 3.4 Provide support for logistics, supplies, social mobilization, and resources for implementation of MNCH integrated services at HF and outreach levels in RED districts & districts affected by emergency | X | X | X | X | MOH |  |  |  |  |
|  |  |  |  |  |  | UNICEF | 500,000 | 230, 000 | UNICEF- OR | 270,000 |
|  |  |  |  |  |  | WHO | 500,000 | 80,000 | WHO OR/RR | 420,000 |
|  | 3.5 Support for procurement and distribution of LLINS to pregnant women, and to children under 5 years of age through ANC clinics and universal access campaigns. | X | X | X | X | MOH |  |  |  |  |
|  |  |  |  |  |  | UNICEF | 1,100,000 | 738,700 | UNICEF – OR | 361,300 |
|  | 3.6 Conduct joint review meetings between MoH, community and key partners in selected districts | x | x | x | x | MISAU |  |  |  |  |
|  |  |  |  |  |  | WHO, | 50,000 | 30,000 | WHO- OR | 20,000 |
|  |  |  |  |  |  | UNFPA,UNCEF & WFP |  |  |  |  |
|  | 3.7. Acquisition of 67 communication radios |  |  | x |  | UNFPA | 600,000 | 85,308 | UNFPA - OR | 514,692 |
|  | 3.8. Acquisition of 6 ambulances |  |  | x |  | UNPFA | 80,000 | 0 |  | 80,000 |
|  | 3.9. Support training of HW through the procurement of anatomical models (1624 vacuum delivery; 41 pediatric simulators, 27 neonatal simulators, 1459 IUDs) | x | x |  |  | UFNPA | 279,888 | 0 |  | 279,888 |
|  | 3.10 Procurement & acquisition of 1,800 MVA Kits |  | x | x |  | UNFPA | 124,000 | 0 |  | 124,000 |
|  | 3.10. Rehabilitation of 8 waiting homes |  | x | x |  | UNFPA | 56,000 | 0 |  | 56,000 |
| Output 4 Government and community capacity improved to strengthen key nutrition interventions, reducing vulnerability and improving nutritional status of the mothers and children in selected districts | 4.1. Support the finalization of the Basic Nutrition Package (BNP) evaluation, revision of BNP manuals and training /supervision materials, and initiate support to training of atleast 50 health workers in the revised BNP. |  |  |  |  | MISAU, DPSs |  |  |  |  |
|  |  |  |  |  |  | UNICEF, | 200,000 | 20,000 | UNICEF: OR | 180,000 |
|  |  |  |  |  |  | WHO | 20,000 | 20,000 | WHO OR/RR |  |
|  | 4.2. Support the implementation of the Nutrition Rehabilitation Programme for children under five and pregnant and lactating women (this includes technical support, training HWs on treatment of severe and moderate acute malnutrition, and use of recording, reporting, planning and monitoring tools, reproduction of materials, and supervision) | x | X |  |  | MISAU |  |  |  |  |
|  |  |  |  |  |  | DPS, Save the Children |  |  |  |  |
|  |  |  |  |  |  | WFP | 126,000 | 126,000 | WFP-RR | 0 |
|  |  |  |  |  |  |  |  |  | WFP- USAID |  |
|  |  |  |  |  |  | UNICEF: | 500,000 | 200,000 | UNICEF: RR/OR | 300,000 |
|  |  |  |  |  |  | WHO | 30,000 | 20,000 | WHO: RR | 10,000 |
|  | 4.3. Provide monthly nutritional supplements to approximately 8000 moderately malnourished pregnant and lactating women per month in MCH services | x | X | x | X | MISAU |  |  | WFP: One UN funds, USAID |  |
|  |  |  |  |  |  | WFP | 774,000 | 274,000 |  | 500,000 |
|  | 4.4. Provide nutritional supplements to up to 10.000 moderately malnourished children under five per month in MCH on a monthly basis | x | X | x | X | MISAU/ |  |  | WFP: One UN USAID |  |
|  |  |  |  |  |  | WFP, | 1,000,000 | 300,000 |  | 700,000 |
|  | 4.6 In the context of staple food fortification and salt iodisation: |  |  |  |  | MISAU, |  |  |  |  |
|  | Support standard development; |  |  |  |  | MIC, INNOQ, |  |  |  |  |
|  | Feasibility studies; |  |  |  |  | UNICEF, | 300,000 | 100,000 | UNICEF:RR+OR | 200,000 |
|  | Quality assurance /quality control |  |  |  |  | WFP |  |  |  |  |
|  | National iodine deficiency study. |  |  |  |  | WHO | 20,000 | 10,000 | WHO/OR | 10,000 |
|  |  | UNFPA | 1,740,787 | 863,693 |  | 1,236,815 |
|  |  | UNICEF | 3,430,000 | 1,508,700 |  | 1,921,300 |
|  |  | WFP | 1,900,000 | 700,000 |  | 1,200,000 |
|  |  | WHO | 1,290,000 | 384,1200 |  | 835,888 |
|  |  |  |  |  |  | TOTAL | 8,360,989 | 3,096,792 |  | 5,193,995 |

Repeat the exact same table for other components if applicable

M&E Framework

| AWP Expected Results | Indicators, Baselines and Targets | Means of Verification |
| --- | --- | --- |
| List the expected results as in the AWP above | Against each expected result, include the indicator(s) that will be used to measure achievement and the baseline and target for each indicator | Provide the source of data that will be used to measure the indicator |
| National budgets, policies, sectoral strategies and annual plans (POA) prioritise issues related to maternal, neonatal and child health, and nutrition is adequately addressed at all levels. | Basic Nutrition Package Evaluation finalized Number of selected provinces and its districts with NIP operationalized Baseline: 1/6 (2010); Target: 6 | MOH reports and partner reports DPS and MoH monthly reports |
| At least 80% of health facilities and community outreach services have improved quality of care in the prevention and the management of maternal and neonatal conditions, childhood illness in all districts in eight provinces, and during emergencies. | % of health services implementing IMNCI Baseline: Estimated at 75% (2009); Target: 80% Number of APEs trained and equipped to implement CCM Baseline: 0; Target 580 Percentage of pregnant women who received a LLIN through antenatal care services Baseline: 73% (2010); Target (2011): 80% Number of districts implementing Universal Access to LLIN Baseline(2009): 14; Target (2011): 45 | MOH reports and partner reports |
| At least 85% of children under 1 year of age immunized with pentavalent vaccine and 90% against measles through implementation of the Reach Every District (RED) approach in 66 existing RED districts, and follow up Mass Measles Campaign | % children 0-11Months immunized with DPT Baseline:80%; Target: 85% % of children immunized against measles during the 2011 follow up measles campaign Target: 90% | MOH Reports and partners reports |
| At least 70% of vulnerable children under five receive health facility and/or community-level preventive and curative interventions addressing nutritional deficiencies as required in all targeted districts. | Nº of health workers trained in the Nutrition Rehabilitation Programme Baseline: 0 (2010) - only ToTs for new protocols Target: at least 400. Nº of children with severe acute malnutrition that received outpatient treatment Baseline: 22,322 (2010); Target: at least 30,000 Nº of children with moderate acute malnutrition that received supplementation Baseline: 11,471 (2010); Target: 20,000 Nº of pregnant and lactating women HIV+ receiving nutritional support in HCs with MCH-PMTCT Baseline: 4500; Target 2011: 15,000 Nº of children under five at risk and HIV+ receiving nutritional support in HCs with MCH Baseline: 4500; Target 2011: 15000 Coverage of vitamin A supplementation in each round of the National Health Weeks and via routine services Baseline: 2010: >85%; Target: > 85% | MOH Reports and partners reports |
| At least 85% of health facilities offering SSR/Maternal health interventions package according to the level of service provision in selected districts. | Nº of HF offering the complete essential obstetric care package Baseline: A (2010) Target: (85%) Nº of HF in selected districts offering BEmOC Baseline: 2HF/districts (2010) Target: at least 3HF/districts | MOH Reports and partners reports |
| At least 12 districts with a functional referral system. | Nº of selected districts with functional referral system (at least 1 ambulance and radio communication at district health facility) Baseline: 6 Target: 12 | MOH Reports and partners reports |
| Studies, surveys and evaluation (list below all surveys, evaluation and studies that will be conducted during the year – ensure that each activities are also listed and budgeted for in the AWP above) |
| 1. National iodine deficiency survey | National iodine deficiency survey report available | MOH Reports and partners reports |

# Text boxes

Estimated annual budget:   US$ 8, 3360,989

Allocated resources:	 US$ 3,096,792

Government:                       See POA 00

Regular Resource:	 US$ 735,000

Other Resource:                  US$ 2,361,792

Pledged:                              US$

Unfunded budget:               US$ 5,193,995

Programme Period: 2007-2011

Programme: MNCH & Nutrition

Budget Code:

Year: 2011

Narrative

The programme will be implemented by the Ministry of Health and its provincial directorates within the framework of the Health SWAp. It will support interventions to address the underlying causes of the high mortality and poor nutritional status of mothers and children, including inadequate access for the most vulnerable to integrated MNCH and nutritional services and gaps in health policy, institutional capacity and quality of service. The programme will contribute to the progressive attainment of the health related Millennium Development Goal targets through the implementation of cost-effective interventions, focusing on health systems-strengthening and support to service delivery at national and sub-national levels. By 2011, the SSR / maternal and Child Health and Nutrition programme will achieve the following results:

- National budgets, policies, sectoral strategies and annual plans (POA) prioritise issues related to maternal, neonatal and child health and nutrition and are well addressed at all levels.

- At least 85% of health facilities and community outreach services have improved quality of care in the prevention and the management of maternal and neonatal conditions, as well as childhood illness in all districts in eight provinces, and during emergencies.

- At least 95% of children under 1 year of age immunised against pentavalent and 95% against measles through the implementation of the Reach Every District (RED) approach in 99 districts.

- At least 70% of vulnerable children under five receive health facility and / or community-level preventive and curative interventions addressing nutritional deficiencies as required in all targeted districts.

- At least 85% of health facilities offering SSR / Maternal health intervention packages according to the level of service provision in selected districts.

- At least 12 districts with a functional referral system.

To ensure the appropriate level of  support to the national efforts, the JP will focus on strengthening institutional capacity and boosting access to and use of integrated Maternal, Neonatal and Child Health (MNCH) and Nutrition services by (i) promoting, supporting and mediating policy dialogue to ensure the development and/or adoption of the keys strategic documents related to SRH, NCH and nutrition; (ii) supporting the establishment of efficient and sustainable planning, monitoring and evaluation systems at national and sub-national levels; (iii) advocating for and supporting the design and implementation of MNCH packages, ensuring in this way that every mother and child, and even the hard to reach, are provided with an integrated package of maternal and child survival interventions, especially good access and quality of sexual and reproductive health; and (iv) strengthening capacity at national and sub-national levels to improve service delivery, focusing on support for sustainable integrated models that can provide evidence for national scale-up.

This AWP for 2011 will focus on accelerating cost-effective maternal, neonatal and child interventions in the following key areas: SSR/maternal health: Promoting and/or reinforcing Essential & Emergency Obstetric Care at health facility and community level, with special attention given to the promotion of family planning services and community and male involvement; Child survival: Re-enforcing IMNCI, C-IMNCI and Community Case Management (CCM) for common diseases, strengthening EPI, implementing the RED approach and measles elimination plan, expanding delivery of LLINs through routine and universal access campaigns and distribution of LLINs, with special attention to children under five years, pregnant women, OVCs, PLWHA and other vulnerable groups. The JP will also focus on accelerating Nutrition elements of the ACSD package and the implementation of the Multi-sectoral Action Plan on Chronic Under-nutrition, by supporting infant and young child feeding interventions at health facility and community level, strengthening the Basic Nutrition Package, the distribution of Vitamin A supplements and de-worming and the National Salt Iodisation Programme and creating demand for iodised salt, introducing the fortification of staple foods and implementing the nutrition rehabilitation programme, including supplementary feeding and the further roll out of outpatient treatment of severe acute malnutrition with community involvement.

The primary geographical focus of the JP in 2010 will continue to be in the 12 selected districts: Maputo province - Manhiça and Matola; Gaza- Chokwe and Xai-Xai; Sofala – Buzi and Dondo; Nampula - Ribaue and Nacala Porto; Zambezia – Maganja da Costa and Pebane; Niassa - Mandimba and Marrupa. However, the JP will continue providing support for the consolidation of the RED approach in the existing 66 districts. This JP will also support nutrition interventions in priority districts that might not be part of the 66 RED districts, though efforts will be in place to ensure complementarities and prioritization in these districts.