Future Work Plan

During the coming year (2011) activities supported under the One Fund will continue to provide the following support:

- The UN will continue to support policy dialogue to enhance the creation of political and fiscal space to raise public expenditure on social protection (including new taxation opportunities on export-led activities);

- The UN will provide technical support to the elaboration of the PARP with the aim to ensure that Social Protection remains high on the political agenda in this key strategic planning and programming document;

- Technical assistance will continue to be provided to improve efficiency in the delivery of social protection benefits by government institutions, and enhance advocacy to obtain additional resources for the social protection sector to expand coverage and impact in the context of the operationalization of the Basic Social Security Strategy;

- Design of the operational plan of the National Basic Social Security Strategy and associated new programmes will be supported, notably in regard to productive social assistance and regular social transfers to the poorest and  most marginalised groups;

- The UN will support the establishment of a SWAp in Social Protection and the creation of a related Common Fund. Although the Joint Programme will be discontinued after 2011 the current support will be continued in the context of the new UNDAF and the establishment of a SWAp / Common Fund will ensure aligned and harmonised support to the Government from all partners involved in the area of Social Protection.

More specifically the UN will support:

- The design of a monitoring and evaluation system for social protection programmes;

- The establishment of the Multi Sectoral Council  for Basic Social Security that will oversee and coordinate the operationalization of the Strategy;

- The implementation of a comprehensive information system for INAS programmes;

- The design of an alternative delivery mechanism for delivery of social transfers (cash and  in-kind assistance);

- The establishment of a comprehensive model in Sofala Province that creates local demand for and access to high quality safety net interventions;

- Provincial and district authorities to increase coordination and implementation capacity to deliver social safety net programmes;

- Improved poverty and vulnerability mapping and development of capacity for more progressive policies and budgetary allocations.

(Page 1 of 6)							 ANNUAL WORK PLAN – Main Table

Country: Mozambique           Work Plan for:  Social Protection	 	Outcome: Social protection safety nets for the most disadvantaged are strengthened and expanded	 	Period: 2010

| JP Outcome(s): Social protection safety nets for the most disadvantaged are strengthened and expanded |
| --- |
| Specific Outputs | Annual Target Indicators | Planned Activities towards stated outputs | TIME FRAME | Implementing Partner | PLANNED BUDGET |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget / Input Description | Amount US$ |
| JP Output 1: National policy and strategy formulated that integrates safety net interventions, including cash transfers, by Government and partners and promotes the allocation of adequate budgets for social safety net programmes, (2.5.2), Comprehensive models are established and operationalised in 7 provinces that create local demand for and access to high quality safety net interventions. |
| Output 1: Stronger common vision on SP created and reinforced | Indicator 1: Basic Social Protection Strategy approved by the Council of Ministers and operational plan elaborated and approved Baseline 2010: Y/N; Target 2011 : Y/Y) | 1.1 Promote the harmonization of concepts and programmes and the dissemination of the SP law, the Regulations for Basic Social Security and Compulsory Social Security and the Basic Social Security Strategy | X | X | X | X | MMAS INAS MoL INSS ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time Staff time |  |
|  |  | 1.2 Strengthen PARP Social Action WG as the forum for discussions on Social Protection, including the revision of the group’s architecture to ensure multi sectoral participation and a harmonised support to MMAS and INAS | X | X | X | X | MMAS ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time Staff time |  |
|  |  | 1.3 Support the establishment and functioning of the “Conselho de Coordenação do Subsistema de Segurança Social Básica” | X | X | X | X | MMAS MPD MINED MISAU MINJUS MAE MINAG etc Civil Society rep ILO WFP UNICEF | ILO WFP UNICEF | US$ 15.000 Staff time Staff time | Funded: Unfunded: US$ 15.000 (ILO) |
|  |  | 1.4 Support the training of major policymakers and partners on social protection programmes | X | X | X | X | MMAS INAS MISAU MINED MINJUS MAE etc ILO WFP UNICEF | ILO WFP UNICEF | US$ 120.000 Staff time Staff time | Funded: US$ 40.000 (ILO) Unfunded: US$ 80.000 (ILO) |
|  |  | 1.5 Support MMAS in the implementation of an Advocacy Strategy as envisioned in the Basic Social Security Strategy | X | X | X | X | MMAS ILO WFP UNICEF | ILO WFP UNICEF | US$ 15.000 Staff time Staff time | Funded: US$ 10.000 (ILO) Unfunded: US$ 5.000 (ILO) |
|  |  | 1.6 Support the operationalisation of the Basic Social Security Strategy via support to the redesign and creation of Direct Social Action programmes. | X |  |  |  | MMAS INAS ILO WFP UNICEF | ILO WFP UNICEF | US$ 60.000 Staff time Staff time | Funded: US$ 40.000 (ILO) Unfunded: US$ 20.000 (ILO) |
|  |  | 1.7 Support the establishment of institutionalised training capacity in the area of Social Security within INSS | X | X | X | X | INSS ILO | ILO | US$ 30.000 | Funded: US$ 20.000 (ILO) Unfunded: US$ 10.000 (ILO) |
|  |  | 1.8 Provide support in the process of an Expenditure and Performance Review of Social Protection Programmes | X |  |  |  | MMAS INAS WB ILO WFP UNICEF | ILO WFP UNICEF | US$ 30.000 Staff time Staff time | Funded: US$ 30.000 (ILO) |
| Output 2: Government capacity for planning, budgeting and for the expansion of coverage of social protection programmes increased | Indicator 2: Budget for Social Protection programmes allocated in line with INAS targets for 2011 (with a specific focus on the expansion of the PSA) (Y/N) – Baseline 2008 N; Target 2011 Y) | 2.1 Provide assistance to INSS in the development of an actuarial study | X | X | X | X | INAS ILO | ILO | US$ 100.000 | Funded: US$ 10.000 (ILO) Unfunded: US$ 90.000 (ILO) |
|  |  | 2.2 In the context of the Basic Social Security Strategy support key line Ministries to leverage additional external resources for the Direct Social Action Programmes, and institutional capacity development. | X | X | X | X | MMAS INAS ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time Staff time |  |
|  |  | 2.3 Support MMAS in the development of the Social Protection component in the PARP and provide support for the development of the 2012 CFMP proposal, with the aim of ensuring government funding for the expansion of current programmes and funding of new programmes. | X | X |  |  | MMAS INAS ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time Staff time |  |
|  |  | 2.4 Provide support to the identification and enrolment of eligible indirect beneficiaries of the PSA with a focus on children. | X | X |  |  | INAS ILO UNICEF | ILO UNICEF | Staff time US$ 320.000 | Funded: US$ 320.000 (UNICEF) (One fund 2010) Unfunded: US$ 680.000 |
|  |  | 2.5 Support INAS in the implementation of a new IT management and information system (including an M&E component, and the connection of all the delegations to e-Sistafe) | X | X | X | X | INAS ILO UNICEF | ILO UNICEF | US$ 687.270 Staff time | Funded: US$ 507.270 (ILO)(One fund 2010) Unfunded: US$ 180.000 (ILO)(possible SIDA funds) |
|  |  | 2.6 Support the design, testing and implementation of a social assistance card that will facilitate case management and a harmonised approach to service delivery for vulnerable households | X | X | X | X | INAS MMAS ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time US$ 400.000 | Funded: Unfunded: US$400 .000 (UNICEF) (possible SIDA funds) |
|  |  | 2.7 Provide support to the revision and implementation of the PSA and PASD manuals and development of manuals for new programmes, with a specific focus on the (re) definition of the targeting and delivery mechanisms. | X | X | X | X | INAS ILO WFP UNICEF | ILO WFP UNICEF | US$ 110.000 Staff time US$ 20.000 | Funded: US$ 70.000 (ILO) US$20.000 (UNICEF) Unfunded: US$ 50.000 (ILO) |
|  |  | 2.8 Support the development and implementation of a Productive Social Safety Net Programme, targeting vulnerable populations in the rural and urban areas | X | X | X | X | INAS ILO WFP UNICEF | ILO WFP UNICEF | Staff time US$ 194.000 Staff time | Funded: Unfunded: US$ 194.000 (WFP) (possible SIDA funds) |
|  |  | 2.8 Support MPD (DNEAP) to organise training seminars focused on productive social protection to support implementation of the Urban Poverty Strategy (PERPU) in selected municipal centres (Maputo, Matola, Beira and Nampula) | X | X | X | X | MPD INAS ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time US$ 30,000 | Funded: 20,000 (UNICEF) Unfunded: US$ 10.000 (UNICEF) |
|  |  | 2.10 Provide support to the design and implementation of a Transfer to cover Households with Children in the context of the Basic Social Security Strategy | X | X | X | X | INAS MMAS ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time US$ 425.000 | Funded: US$ 175.000 (UNICEF) Unfunded: US$ 250.000 (UNICEF) (Possible SIDA funds) |
|  |  | 2.11 Provide technical assistance to the piloting of an alternative delivery mechanism for the WFP food support via the PASD Programme (WFP) and the outsourcing of the cash transfer delivery mechanism (UNICEF) | X | X | X | X | INAS WFP UNICEF | WFP UNICEF | Staff time US$ 370.000 | Funded: 254.863 (UNICEF)) Unfunded: US$ 115.137 (UNICEF) |
|  |  | 2.12 Support capacity development of provincial OVC committees and NGOs regarding targeting, operational planning, monitoring and quality assurance of basic services provided (related to WFP support) | X | X | X | X | MMAS INAS WFP | WFP | US$ 35.000 | Funded: US$35.000 (WFP) Unfunded: |
|  |  | Assist in the launch of a SWAP in Social Protection, including the establishment of a Common Fund | X | X | X | X | INAS DFID EKN ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time Staff time |  |
|  |  | 2.15 Support research and advocacy efforts to strengthen awareness of social protection issues and identify gaps / issues to advance the social protection agenda: Analysis of funding opportunities and solutions for SP, within the economic and fiscal context in Mozambique (ILO) Mapping of Vulnerabilities (built with data from the most recent national surveys), to create a basis for a discussion on geographical targeting (WFP) Disseminate and advocate results on alternative modalities in supporting social protection measures for vulnerable children (WFP) |  |  |  |  | MMAS/INAS ILO WFP WB | ILO WFP | Staff time US$ 140.000 | Funded: US$ 40.000 (WFP) Unfunded: US$ 100.000 (WFP) |
|  |  | 2.16 Develop multi-media advocacy tools to highlight south-south cooperation and best practices in social protection |  |  |  |  | MPD ILO WFP World Bank UNICEF | ILO WFP World Bank UNICEF | Staff time Staff time Staff time 100.000 | Unfunded: US$ 100.000 (UNICEF) |
|  |  | 2.17 Provide technical support to the application and dissemination of the PSA impact evaluation | X | X | X | X | INAS MMAS ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time US$ 5.000 | Funded: US$ 5.000 (UNICEF) Unfunded: |
| Output 3: Key social assistance programmes evaluated and informing the development of the INAS Intervention Strategy for Social Protection | Indicator 3: A comprehensive system of information for INAS programmes being implemented (Y/N) – Baseline 2008 N; Target 2011 Y | 3.1 Support INAS with the finalization of INAS Intervention Strategy | X | X | X | X | MMAS/INAS MPD ILO WFP UNICEF | ILO WFP UNICEF | Staff time Staff time Staff time |  |
|  |  | 3.2 Support the development of a harmonised OVC M&E system for outcome monitoring | X | X | X | X | DPMAS Del. INAS WFP IRD International HIV Alliance | WFP | US$ 10.000 | Funded: US$ 10,000 (WFP) |
|  |  | 3.3 Establishment of quality assurance, programme oversight and accountability mechanisms at provincial level | X | X | X | X | DPMAS Del. INAS and other Provincial authorities WFP | WFP | US$ 10,000 | Funded: US$ 10,000 (WFP) |
| Output 4: A comprehensive model is established and operationalized In Sofala Province that creates local demand for and access to high quality safety net interventions; Capacity of provincial and district authorities increased for greater coordination and implementation of social safety net programmes | Indicator 4.1 DPMAS Sofala has an updated information system on civil society interventions in the province and feeds information to MMAS central level Baseline 2008 information system installed; Target 2010: information system maintained/updated and information fed to MMAS central level Indicator 4.2 Provision of in-kind assistance by UNICEF and WFP aligned with INAS programme implementation and an alternative delivery mechanism for delivery of in-kind assistance piloted (Baseline 2009 N; Target 2010 Y) Indicator 4.3 Number of beneficiaries from services provided by LEDA to the most vulnerable in rural areas – Baseline 500; Target 1000 |  |  |  |  |  |  |  |  |  |
| Output 5: Selected target groups have access to a comprehensive set of basic services OVC AIDS affected households Vulnerable households unable to work | Indicator 5.1 # of children receiving food support in Sofala Province (Baseline 2008- 428 (PASD);Target 2010 – 409) Indicator 2 # of children with access to monthly food baskets and a comprehensive set of basic services (Baseline 2008 – 11,000/Target 2010 – 11,180 Indicator 3 # of AIDS affected households with access to monthly food baskets (Baseline 2008 – 2000/Target 2010 – 2,000 | 5.1 Delivery of monthly food baskets through community based organizations to 20,000 OVC (including access to basic services) 4,500 AIDS affected households (total 22,500 beneficiaries) | X | X | X | X | MMAS/INAS WFP | WFP | US$ 3.000.000 | Funded: Unfunded: US$ 3.000.000 (WFP) |
| Please see the comment above on sustainability and phasing out |  |  |  |  |  |  |  |  |  | Funded: ILO US$ 687.270 WFP US$ 55.000 UNICEF US$ 770.976 TOTAL US$ 1.513.246 Unfunded: ILO US$ 450.000 WFP US$ 3.194.000 UNICEF US$ 1.330.000 TOTAL US$ 4.974.000 |
|  |  |  |  |  |  |  |  |  |  | US$ 6.487.246 |
| GRAND TOTAL |  |  |  |  |  |  |  |  |  |  |

* Note: This amount is to cover not only food costs but also other activities.