## Sheet1
EDPR Work plan 2011 - Valdiated 23rd February, 2011
Component: | Economic Diversification and Poverty Reduction
National Priorities & Goals | Vision 2016: A Prosperous and Innovative Nation; A Just and Compassionate Nation
NDP 10: Eradication of Absolute Poverty; Equitable Income Distribution; Adequate Social Protection; Full Employment
MDGs: Eradicate Extreme Poverty and Hunger; Develop a Global Partnership for Development
UNDAF Outcome | A diversified Economy whose growth is rapid, inclusive, sustainable and generates decent employment opportunities by 2016
Country Programme Outcome | CPO 2.1: Enhanced national and district capacity to support inclusive community driven development
Country Programme output | 2.1.1: National & district frameworks for Local Economic Development (LED) developed in all districts
Key Results by Output/Project | 2.1.1.1:National policy and strategy frameworks for sustainable LED are elaborated and harmonised through an inclusive process
Budget
Planned Activities | Activity Output | Implementing Partners | Q1 | Q2 | Q3 | Q4 | Sources of Funds | Budget Description | Planned Budget | Expenditure | Remarks
Formulate a National LED policy, implementation Strategy, communication strategy and M&E plan | LED Concept Paper and Communications Strategy finalised/developed | MLG |  |  |  |  | UNDP | Technical Assistance | 20000
| Study Tour | MLG |  |  |  |  | UNDP | Travel & Subsistence | 20000
| LED Communication Materials – ppts, videos, pamphlets, fliers and memorabilia developed | MLG |  |  |  |  | UNDP |  | 50000
| Adequate stakeholder awareness about LED secured | MLG |  |  |  |  | UNDP | Travel and Subsistence | 20000
| Policy advisory and project management services to MLG | MLG |  |  |  |  | UNDP | Policy Advisor | 193000
[8 empty] | Financial & Admin Assistant | 0
| LED Trainers of Trainers developed | MLG |  |  |  |  | UNDP | Facilitation Costs | 10000
[8 empty] | Conference Costs | 5000
Strengthen national & district capacity to implement LED | Enhanced district capacity to manage, process and use development data | MLG |  |  |  |  | UNDP | Facilitation Costs Travel & Subsistence | 100000
| Two CRP feasibility Studies undertaken | [5 empty] | UNDP | Technical Assistance | 60000
| Total for CPO 2.1 | [7 empty] | 478000
Country Programme Outcome | CPO 2.2: Technical and institutional capacity to develop, implement and monitor inclusive development policies and strategies is strengthened in key ministries
Country Programme Output | 2.2.1: Regulatory instruments to improve poor people's access to financial services and productive assets/resources are strengthened
Key Results by Output/Project | 2.2.1.1: Mechanisms & institutions supporting improved access to financial services for poor people, the un-banked, and the under- banked, especially women and youth, are strengthened
Planned Activities | Activity Output | Implementing Partners | Q1 | Q2 | Q3 | Q4 | Sources of Funds | Budget Description | Planned Budget | Expenditure | Remarks
Monitor trends in access to financial services for Botswana’s poor, un-banked and under-banked populations | Analytical report on access to financial services for poor people | MFDP |  |  |  |  | UNDP | Technical Assistance, printing, publishing & Seminar Costs | 50000
| Report on stakeholder views on access to financial services for poor people | MFDP |  |  |  |  | UNDP
| Advocacy material on access to financial services for the poor developed and disseminated | MFDP |  |  |  |  | UNDP
Key Results by Output/Project | 2.2.1.2:Policy oriented research and institutional analysis on access to productive assets/resources for poor people is strengthened
Key Results by Output/Project | 2.2.1.3: Policy provisions and guidelines on housing for poor people are reviewed, updated and strengthened.
Country Programme output | 2.2.2 Enhanced technical and oversight capacity of the Ministry of Finance and Development Planning (MFDP) to manage the implementation of the National Strategy for Poverty Reduction
Key Results by Output/Project | 2.2.2.1: Enhanced MFDP capacity to provide policy advisory services on poverty to the MSCPR and line ministries
Planned Activities | Activity Output | Implementing Partners | 1 | 2 | 3 | 4 | Sources of Funds | Budget Description
Strengthen MFDP’s technical capacity to provide policy and Technical Assistance on poverty | Policy advisory and programme management services (policy/programme advisory and review notes, study reports, progress reports etc.) provided to the MSCPR Secretariat | MFDP |  |  |  |  | UNDP | Policy Advisor | 193000
[8 empty] | Project Coordinator | 74998.81
[8 empty] | Financial & Admin Assistant | 47000
| Annual Poverty Report prepared and published | [5 empty] | UNDP | Technical Assistance | 10000
| Poverty Policy Matrix and poverty audit of NDP 10 completed | [5 empty] | UNDP | Technical Assistance | 10000
| Carry out 3 annual mini-surveys on the impact of the economic crisis | MFDP |  |  |  |  | UNICEF | Technical Assistance, seminar costs | 130500 |  | 2 surveys have been completed. 60,527.00 is requestd for the 3rd round survey.
| Data analysis for the survey based evalutation of the Destitute Programme | [5 empty] | UNDP | Technical Assistance | 25000
Strengthen systems for measuring, monitoring and analysing poverty, inequality and the impact of poverty policies and programmes | Poverty analysis of the results of the 2009/10 Botswana Core Welfare Indicator Survey (BCWIS) is undertaken | MFDP,CSO |  |  |  |  | UNDP | Technical Assistance, Training Costs | 50000
[7 empty] | World Bank | Technical Assistance | TBA
| Provisional - Child poverty and welfare analysis of the results of the 2009/10 BCWIS is undertaken | MFDP, CSO |  |  |  |  | UNICEF | Technical Assistance | 50000
| Enhanced capacity to measure, monitor and analyse poverty in key national institutions (CSO, MFDP, UB, BIDPA) | MFDP, CSO |  |  |  |  | UNDP | Technical Assistance, Training Costs | 30000
[7 empty] | World Bank | Technical Assistance, Training Costs | TBA
| Preparatory work for the design of a Poverty & Vulnerability Monitoring and Information System (PMIS) is done | MFDP, CSO |  |  |  |  | UNDP | Technical Assistance | 30000
[7 empty] | UNDP | Benchmarking | 35000
[7 empty] | UNDP | Software costs | 30000
[7 empty] | UNDP | Training Costs | 30000
| Feasibility Report on the Botswana Centre for Poverty Analysis | MFDP, UB |  |  |  |  | UNDP | Technical Assistance | 60000
| Social Impact Analysis of Ipelegeng is completed | MLG |  |  |  |  | UNICEF | Technical Assistance | 70000
| Assessment of child-friendliness of Botswana's budget | MFDP |  |  |  |  | UNICEF | Technical Assistance | 30000
| High profile commemoration of IDEP | MFDP |  |  |  |  | UNDP | Facilitation costs | 15000
Key Results by Output/Project | 2.2.2.2: Institutional capacity for evidence-based integration of environment and development concerns into poverty reduction strategies enhanced
Planned Activities | Activity Output | Implementing Partners | 1 | 2 | 3 | 4 | Sources of Funds | Budget Description
Undertake strategic analytical studies to inform key policy reviews, developments & dialogues | PEI related policy advisory and programme management services (policy/programme advisory and review notes, study reports, progress reports etc.) provided to the MSCPR Secretariat | MFDP,MEWT |  |  |  |  | UNDP | Policy Advisor | 32000
[7 empty] | UNEP |  | 32200
[7 empty] | UNDP | Project Coordinator | 16000
[7 empty] | UNEP |  | 16000
[7 empty] | UNDP | Finance &Administration Assistant | 7900
[7 empty] | UNEP |  | 7900
| Poverty and Social Impact Analysis of ISPAAD is completed | MFDP,MEWT,MOA |  |  |  |  | UNDP | Technical Assistance | 30000
[7 empty] | UNEP |  | 30000
Strengthen knowledge management networks on poverty and environment and promote exchange of best practices and lessons | Evidence based policy briefs, presentations and communication materials prepared & disseminated | MWET,MFDP |  |  |  |  | UNDP | Technical Assistance | 10000
[7 empty] | UNEP |  | 10000
| Policy dialogues/debates and briefing sessions with key stakeholders, e.g. legislators, are organised | MWET,MFDP |  |  |  |  | UNDP | Technical Assistance, Conference costs, publications | 10000
[7 empty] | UNEP |  | 10000
| A core of PEI expertise is developed in in MFDP, MEWT and partner institutions | MWET,MFDP |  |  |  |  | UNDP | Conference costs | 20000
[7 empty] | UNEP |  | 20000
| Enhanced capacity for district planners and decision makers to identify and integrate P/E issues into development plans, budgets and M&E processes | MWET,MFDP, MLG |  |  |  |  | UNDP | Training Costs | 10000
[7 empty] | UNEP |  | 10000
Key Results by Output/Project | 2.2.2.3: Enhanced capacity for evidence-based integration of population concerns into poverty reduction strategies and national development plans
Planned Activities | Activity Output | Implementing Partners | 1 | 2 | 3 | 4 | Sources of Funds | Budget Description
Strengthen capacity to Coordinate, monitor and implement population programs and the MDGs. | National Population Policy M&E framework/Implementation Plan developed | MFDP |  |  |  |  | UNFPA | Technical Assistance, Conference costs | 15000
| Advocacy and Communication Strategy for the Revised Population Policy developed and implemented | MFDP |  |  |  |  | UNFPA | Technical Assistance, Conference costs | 13000
| Enhanced capacity of national & district personnel to coordinate and implement population programmes | MFDP |  |  |  |  | UNFPA | Technical Assistance, Conference costs | 7000
| P&D integrated database maintained and district population profiles developed | MFDP |  |  |  |  | UNFPA |  | 3000
| Policy dialogue/seminars and fact sheets on topical and emerging population issues | MFDP |  |  |  |  | UNFPA | Personnel Costs, Technical Assistances, Training Costs & Printing and publishing | 7500
| Training on research methodologies and analysis conducted | MFDP |  |  |  |  | UNFPA | Training Costs | 10000
| National Disability Policy and Implementation Plan | OP |  |  |  |  | UNFPA | Facilitation Costs, Conference Costs | 10000
| Strategic plan for the improvement of health and livelihood of the elderly | MFDP |  |  |  |  | UNFPA | Facilitation Costs, Conference Costs | 10000
| MDG related advocacy, coordination, and advisory support services and MDG Reporting improved | MFP |  |  |  |  | UNDP | MDG Communications Officer | 60000
| Launch and disemmination of Botswana 's MDG Report 2010 | MFDP |  |  |  |  | UNDP | Seminar costs | 20000
| School level MDG Activities: Debates, Essay Competions supported | MFDP, MOESD |  |  |  |  | UNDP | Facilitation Costs | 10000
| Enhanced media capacity to report on the MDGs | MFDP, MISA |  |  |  |  | UNDP | Training costs, award | 20000
Country Programme Output | 2.2.3 Poverty is mainstreamed into national and district development plans
Key Results by Output/Project | 2.2.3.1 Instruments/tools and evidence for mainstreaming poverty into policies and plans developed
Planned Activities | Activity Output | Implementing Partners | 1 | 2 | 3 | 4 | Sources of Funds | Budget Description
Review the growth, employment and poverty nexus as an input towards a draft employment policy | Policy note on the growth and employment imperatives for poverty reduction in Botswana | MFDP |  |  |  |  | UNDP | Technical Assistance | 10000
Integrating Environmental sustainability into national, sector and district development plans | Review Report on the poverty and environment policy imperatives of the Revised NSPR | MFDP, MEWT |  |  |  |  | UNDP | Technical Assistance | 80000
Synthesis of the NSPR reviews into a revised National Strategy on Poverty | Revised National Strategy on Poverty | MFDP |  |  |  |  | UNDP |  | 60000
Key Results by Output/Project | 2.2.3.2 Mechanisms to improve access to education for vulnerable and disadvantaged children developed
Planned Activities | Activity Output | Implementing Partners | 1 | 2 | 3 | 4 | Sources of Funds | Budget Description
Develop a methodology to assess quality in education | Quality assessment tool for education | MOESD |  |  |  |  | UNICEF | Technical Assistance | 48000
Support development of guidelines to improve access to education for vulnerable children | Guidelines for improving access to education for vulnerable children | MOESD |  |  |  |  | UNICEF | Technical Assistance | 40000
Country Programme Output | 2.2.4: Vulnerability and social protection mechanisms strengthened based on vulnerability assessments, research and analysis
Key Results by Output/Project | 2.2.4.1 A comprehensive vulnerability and social protection system is developed
Planned Activities | Activity Output | Implementing Partners | 1 | 2 | 3 | 4 | Sources of Funds | Budget Description
Review vulnerability assessment and social protection systems, including options for a comprehensive social security system | Report on the Social Protection Expenditure Review | MLHA, MLG |  |  |  |  | ILO,TBA |  | 10000
| Draft paper on options for an integrated social security policy | MLHA, MFDP |  |  |  |  | ILO, TBA | Technical Assistance | 22000
| Policy Brief on Social Protection | MLHA, MFDP |  |  |  |  | UNDP | Technical Assistance | 10000
[7 empty] | ILO | Technical Assistance
| Total for CPO 2 | [7 empty] | 1665998.81
Country Programme Outcome | CPO 2.3: The institutional and regulatory environment for inclusive trade and private sector development is strengthened
Country Programme output | 2.3.1: Institutional capacity to provide and coordinate private sector development and support services, especially for the SMME and informal sectors, is strengthened | [9 empty] | Media education programme on credit and debt management Needs Assessment Report on rural consumers Functioning CA website and links
Monitor and evaluate enterprise development and related policy and strategy issues | Feasibility Study on the Establishment of a Centre for Enterprise Development at UB completed. | MTI, UB |  |  |  |  | UNDP | Technical Assistance cost | 90000
| Botswana Enterprise Monitor designed and institutionalised | MTI, UB |  |  |  |  | UNDP | Technical Assistance cost | 30000
Support national and district initiatives to enhance productive/supply capacity | Report on the feasibility of cluster development in Botswana prepared | MTI |  |  |  |  | UNDP | Techncial Assistance, Seminar Costs | 100000
Key Results by Output/Project | 2.3.1.2: MTI capacity to develop, implement and monitor a revised Industrial Development Policy (IDP) as a key instrument for economic diversification is strengthened
Review of Industrial Development Policy and Act and implementation mechanisms | Dissemnination of the revised Industrial Development Policy | MTI |  |  |  |  | UNDP, UNIDO | Technical Assistance | 30000
| Capacity to implement the IDP is strengthened in the DIA and key partner institutions | MTI |  |  |  |  | UNDP, UNIDO | Technical Assitance | 40000
Development of a collaborative trade research programme | Key DIT staff trained on the management and maitenance of trade data and data analysis | MTI, UB |  |  |  |  | UNDP | Techcnical Assistance, Seminar Costs | 10000
| Operational strategy on Aid for Trade and Trade Facilitation | [5 empty] | UNDP | Techcnical Assistance, Seminar Costs | 15000
Strengthen the technical and oversight capacity of the NCTPN and its partners | Study report on the implications of the SACU Agreement on the economy of Botswana | MTI |  |  |  |  | UNDP | Technical Assistance, Seminar Costs | 40000
| Capacity building workshops for the NCTPN and its sub-committees are held | MTI |  |  |  |  | UNDP | Techcnical Assistance, Seminar Costs | 50000
| Key trade negotiations personnel receive training on trade negotiations | [5 empty] | UNDP | Techncial Assistance | 20000
| Negotiation position papers on Tourism, Legal Services and Communications developed | MTI |  |  |  |  | UNDP | Techncial Assistances | 80000
| Total for CPO 2.3 | [7 empty] | 505000
Key Results by Output/Project | 2.3.1.3: Institutional & regulatory frameworks for the development of the creative industries- crafts,culture,music,food etc- are strengthened
Key Results by Output/Project | 2.3.1.4: Capacity for the development of culture of competition and consumer protection is enhanced
Support the establishment of the institutional and regulatory framework for the enforcement of Competition and Consumer protection legislation | Development of Commissions’ regulations, guidelines and manuals on the implementation of the Competition Law. | MTI |  |  |  |  | UNDP | Technical Assitance | 40000
| CA Commissioners, staff and judiciary trained on key aspects of the implemntation of the Competition Policy and Law | MTI |  |  |  |  | UNDP | Techncial Assitance, Training Costs | 40000
| IT and documentation system developed | [5 empty] | UNDP | Technical Assistance | 20000
Support advocacy on competition & consumer protection | Development of outreach programme on competition law awareness | MTI |  |  |  |  | UNDP | Technical Assistance | 20000
| Competition Authority’s website developed | MTI |  |  |  |  | UNDP | Training Costs, Travel and Subsistence | 10000
| Total for CPO 2.3 | [7 empty] | 635000
| Grand Total | [7 empty] | 2820499
Note on B13: sennye.obuseng: Zero draft LED Concept Exists
Note on D13: sennye.obuseng: CP by 03/11
Note on E13: sennye.obuseng: C/Strategy by 04/11
Note on J13: sennye.obuseng: Concept Paper 5,000 C/Strategy 15,000
Note on E14: sennye.obuseng: By 04/11
Note on E15: sennye.obuseng: Full suite by 04/11
Note on E16: sennye.obuseng: 16 districts mobilised by 05/11
Note on E17: sennye.obuseng: Advisor to be in post by 04/11
Note on J17: sennye.obuseng: P4
Note on J18: sennye.obuseng: Shared CCG resource paid under CPO2.2
Note on E19: sennye.obuseng: - Comprehensive training and tools for 4 HQ planners & 32 district planners by 04/11. Other agencies to be invited to participate
Note on E21: sennye.obuseng: Continuous, commencing March 04/11. Includes
Note on G21: sennye.obuseng: Indicators - Executive buy in(via seminars on district development data - Development data needs assessment for districts - District indicator frameworks and no of up to date district databases - No. of personnel trained on maintenance of district databases
Note on E22: sennye.obuseng: - Dairy project in Maunatlala - Leather project in Hukuntsi
Note on B30: sennye.obuseng: - Links between access to financial services and poverty - Situational analysis - Constraints on poor people's access to financial services - Policy Issues on access to financial services - Recommendations for action
Note on B31: sennye.obuseng: Required to secure stakeholder perspectives
Note on E43: sennye.obuseng: February
Note on F43: sennye.obuseng: June
Note on G43: sennye.obuseng: October
Note on F45: sennye.obuseng: - Revised Poverty Line - Poverty Profile - Mulit dimensial poverty analysis [Thematic reports e.g. child poverty, education, health etc.] - Dissemination of survey results
Note on E48: sennye.obuseng: - Training on the use of Stata and ADePT - Training on basic concepts of poverty
Note on B50: sennye.obuseng: Conditional on compliance with GoB e-government requirements
Note on F50: sennye.obuseng: - Consultations on Indicator Frameworks - Benchmarking
Note on G50: sennye.obuseng: The World Bank is a prospective partner and should be courted seriously
Note on E68: sennye.obuseng: Should include conferences
Note on F72: sennye.obuseng: - Training (seminar and/or external short course) for key PE personnel at MEWT, MFDP and partner institutions - Training on PE mainstreaming for technical committee members - Training of 30 participants from CSO, MFDP, MEWT, MoA, MLG, MMEWR on PE mainstreaming
Note on E74: sennye.obuseng: - Integration of PE indicators into national, sector and district developmentl indicator frameworks - Development of PE mainstreaming guidelines for district planners
Note on G74: sennye.obuseng: - PE mainstreaming sensitization seminars for district planners - training sessions (in Gaborone & Francistown) for district planners on the use of mainstreaming guidelines conducted
Note on G86: sennye.obuseng: - MDG Coalitions mobilised - Quarterly MDG Updates
Note on E87: sennye.obuseng: - Media - Parliament - House of Chiefs - Four selected councils when sitting - Civil Society - Business
Note on E89: sennye.obuseng: - Media Training - Media Award
Note on F94: sennye.obuseng: - Technical/Review Report - Policy Note
Note on G95: sennye.obuseng: Draft NSPR Poverty Strategy Pitso - GEDP - P/E - Social Protection
Note on B121: sennye.obuseng: Target should be four (4)