**Afghanistan**

|  |  |
| --- | --- |
| **Programme Title:**  | Strengthened Approach for the Integration of Sustainable Environmental Management into the ANDS/PRSP |
| **Programme number & MDTF ref:** | MDGF-1713-E-AFG Integr.of Sust (67162) |
| **Window:** | Environment & Climate Change |
| **Approved Budget by NSC (US$):** | 5 million |
| **Participating Organizations:** | UNDP, FAO, (UNEP in advisory role) |
| **First Tranche transferred on:** | 5-Nov-2008 |
| **Second Tranche transferred on:** | 2-Jun-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| National Environmental Mainstreaming (EM) Guidelines developed. Environmental Concerns reflected in MRRD Strategic Intent. Provincial and local structures such as Environmental Advisory Councils and Environmental Sub-committees established. Environmental concerns reflected in the Provincial Strategic Planning process (Up to date 4 Herat, Balkh, Bamyan and Laghman). Environmental mainstreaming awareness toolkit developed. EM taskforce formed and operationalized. Provincial Environmental Advisory Councils (PEAC) Guideline developed, 200 PEAC brochure, 200 Environmental Sub-committee ToRs produced and disseminated. GPS training manual produced and disseminated, Water quality training manual produced, Training module for community extension worker of – AFGHANISTAN INSTITUTE FOR RURAL DEVELOPMENT (MRRD) produced. Training in environmental matters provided. Kitchen gardens in Herat and Ghor provinces established. Production facility for seed multiplication established. Preparation of technical maps completed.  |
|  |
| **Problems and lessons learned:**UN Agency Coordination. Managerial. External to the JP (security, inaccessibility). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

