**Angola**

|  |  |
| --- | --- |
| **Programme Title:**  | Children, Food Security and (Mal)Nutrition in Angola |
| **Programme number & MDTF ref:** | MDGF-1997-I-AGO (67239) |
| **Window:** | Children, Food Security & Nutrition |
| **Approved Budget by NSC (US$):** | 4 million |
| **Participating Organizations:** | UNICEF, WHO, IOM, FAO, UNDP |
| **First Tranche transferred on:** | 14-Dec-2009 |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| * Food security and nutrition strategy prepared and disseminated.
* 88% children under 5 received one dose of vitamin A and 82 % children received albendazole.
* More than 80% of the population have the access to full high impact interventions in 9 selected municipalities of Bie, Moxico and Cunene for revitalization.
* Total of 4,166 severely acute malnourished children have been treated in 2010 both at community and facility based care unit using therapeutic feeding protocol in Bie, Moxico and Cunene.
* 20 % vulnerable families assisted for food security.
* Essential supplies distributed to municipal governments.
* Training of trainers on food security and nutrition ongoing.
 |
| **Problems and lessons learned:** |
| * Ensuring a good understanding of the JP and promoting strong National and provincial ownership
* High mortality rate of Severely malnourished children at Facility based care unit
* Rapidly building the skills of providers for scaling up of planned interventions at the municipality level
* Sustaining the commitments of the Provincial and municipality authorities
* Promoting Community involvement and full participation
* Building an effective health management information system to monitor and measure progress linked to the existing system
* Coordination with government and Coordination within government
 |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place**: No (There are several communication activities embedded on the programme) |

CHARTS & FIGURES

As of 31 December 2010

