Annex 6 - PROJECT SHEET

Immediate Response Facility (IRF) of the Peace-Building Fund (PBF)

2nd UN Proposal

| Agency(s): | UNHCR, UNICEF |
| --- | --- |
| Project Title: | Strengthening Media Capacity to Promote Peace and Tolerance In The Kyrgyz Republic |
| Beneficiaries: | Primary beneficiaries: national and local media Secondary beneficiaries: general public, decision-makers, government press services and conflict-affected communities |
| Implementing Partner(s): | INTERNEWS Kyrgyzstan, I-Media, Schools of Journalism, national and local media |
| Project Duration: | July 2011 – June 2012 (or 12 months) |
| Total Project Budget: | USD 330,108 |
| Outcomes of the project (up to 3): | Infrastructure for peace is strengthened through active participation of media in peace-building and reconciliation processes in the country |
| Government priorities addressed by the project: | Culture and mass media development |

# Project Justification

Most Kyrgyz media failed to provide consistent and balanced coverage of the tragic June 2010 events. Out of a hundred national and local media outlets, which reported on the situation in the south, only a handful kept to the principles of neutrality and professionalism, according to some media experts. Although the overall tone of reporting improved after the crisis, there is still a high level of intolerance observed in the local media. The intolerance is showing a tendency to increase as the presidential elections approach.

The presidential elections in late 2011 pose another challenge to the media, which undoubtedly will be manipulated by political rivals. This in turn may lead to a further increase in nationalism and societal polarisation. Therefore, there is an immediate need to equip the media with skills and knowledge so that it can play an active and positive role in strengthening peace-building and reconciliation processes in Kyrgyzstan, especially before the forthcoming presidential elections.

Unfortunately, there has not been a thorough investigation into the media’s role during and after the conflict in the south. At a roundtable held in Bishkek last December, media experts, journalists and some human rights NGOs pointed out that a lack of analytical and investigative skills of many local journalists continues to hinder media involvement in conflict resolution and reconciliation. It was also mentioned that a lack of a professional ethic and core journalism principles among journalists, inability or unwillingness to resist political manipulations, stigmatisation, a “them and us” mentality and pursuit of sensation contribute to the polarisation of society.

The report of the National Commission into the Osh and Jalalabad events provides an example of when an article about the inter-ethnic conflict between Uzbek and Kyrgyz in 1990 posted on a news agency website and repeated on the eve of the tragedy, incited heated discussions in on-line forums and continued in the smaller groups in Osh before the events. The report also underlined that both national and international media, in pursuit of sensation, often published unverified information.

The June 2010 events changed the media status quo in the south. The two television channels previously owned by ethnic Uzbeks and broadcasting programmes in Uzbek language have seen changes in ownership and language policy. Many independent and professional journalists have left Osh and Jalalabad. The office of the Jalalabad television station was looted and burnt down. The ethnic communities in the south have little trust in local media. In this information vacuum, rumours and propaganda have become the primary local information source, which undoubtedly makes population vulnerable to manipulation and could potentially lead to recurrence of communal violence.

The media in Kyrgyzstan recognises its social responsibility to some extent and the majority of the journalists and editors are receptive and open to cooperation. Yet there are certain weaknesses and gaps, which the project can effectively address in the next 6-12 months. The media has goodwill but often lacks resources and skills. The project is intended to provide both.

The Government of the Kyrgyz Republic is drafting a concept note on Ethnic Development and Society Consolidation. In a letter to the UN system in February 2011, Ms. Mira Karybaeva, the Head of the Department on Ethnic and Religious Policy and Civil Society Interaction under the President’s Office requested the UN to support the Government’s priority areas including mass media development.

In addition, the National Commission recommended that the Kyrgyz Government take measures to prevent media reports instigating nationalism and extremism, especially in the south. The Commission recommended making amendments to legislation on mass media including strengthening of administrative and legal responsibility of media organisations inciting interethnic and religious hatred.

# Since media development is one of the key priorities outlined by the President, it will be an integral part of the new concept of ethnic development and society consolidation. In this way the results of the project will be sustained by the government with support from the international community.

The suggested media interventions contribute to Outcome 1 of UNDAF 2012-2016: ‘A national infrastructure for peace (at local, regional and national levels), involving government, civil society, communities and individuals, effectively prevents violent conflict and engages in peace-building’.

In the concept of ‘infrastructures for peace’, media is considered an important space for dialogue on the peace-building challenges of the country. While encouraging people to have face-to-face dialogue in a post-conflict setting is often challenging, balanced and impartial media can be an entry point for people to hear their voices and listen to the opinions of different sides of the conflict. Through the promotion of editorial values / standards and the production of media outputs, media can connect people across divides. Developing media at different levels in Kyrgyzstan can therefore strengthen the infrastructure for peace in the country.

The effect of this project will have positive implications on other peace-building initiatives carried out in the country. Through media initiatives and press tours this project will support peace-promotion initiatives among youth, school children, and rural communities and propagate successful stories of conflict prevention and reconciliation from other PBF proposals.

- Project description

By its nature, the media is mostly interested in covering conflicts, not peace-building because the media tend to favour four values: immediacy, drama, simplicity and ethnocentrism. The objective of this project is to strengthen media capacity and engage it in promotion of peace-building and reconciliation, fully recognising its role and responsibilities in these processes.

# This project will address access of journalists to resources and the development of professional skills and resources for the media in Kyrgyzstan to promote peace and reconciliation and prevent the recurrence of violence.  As a result of this project, journalists will have increased access to resources and strengthened conceptual understanding of peace reporting so that they can contribute to building peace and reconciliation. Moreover, media has a role to play in early warning and the project will sensitise media professionals in this regard as well.

# A public awareness campaign conducted before and during the presidential election campaign will help to counteract rumours and avoid undesirable manipulation of public opinion by politicians using nationalism and intolerance in their political agenda.

This project is not part or a substitute for a regular programme of any UN agency. However, if implemented in the next 12 months it will greatly amplify the impact and create publicity for other peace-building activities funded by the IRF. The project has synergies with all proposed peace-building activities and is the only project which targets the media directly, as a primary beneficiary, in a most comprehensive way.

The country-wide project will have a quick impact. For example, the first activities, such as capacity building of media resource centres in all regions, with a primary focus on the conflict-affected south will have an impact within 1-2 months of the start of the project. These centres will serve as media hubs and provide access and resources to independent media to produce and transmit professional and objective reports.

Another immediate project result will be felt after involvement in training of the government press services, which in light of the forthcoming presidential elections, may become a source of biased and unverified information or openly promote the political agendas of certain politicians.

The media training and public awareness campaign components of the project will be conducted simultaneously and the critical mass of positive and peace-sensitive reports, PSA and other products will be reached by the time of the presidential election campaign. Therefore, it is vital to start the project at least 5-6 months before the elections, scheduled for the end of 2011.

# The project has two components:

# 1. Strengthening national and local media capacity for peace-building and reconciliation

# 2. Increasing public awareness through targeted media campaign on conflict resolution, peace-building and reconciliation.

# Outcome: 	Infrastructure for peace is strengthened through active participation of media in peace-building and reconciliation processes in the country

# Output 1: 	Capacities of the media for peace-reporting (peace journalism) is strengthened

# Key Activities:

- Upgrade media resource centre and improve registration (computer equipment, office supplies, Internet)

- Provide grants for media peace initiatives. The grants will be provided on the basis of the competition.

- Conduct training of trainers (TOT) on peace reporting for representatives of media development organisations, media outlets, schools of journalism, media experts, and media resource centres

- Conduct cascade training for provincial media journalists and students of schools of journalism in peace reporting. The training will also benefit the Presidential, Ombudsman, Parliament and other government press-services, helping them integrate conflict prevention and peace building into their agenda.

- Monitoring & Evaluation: Carry out pre- and post-training content analysis to assess changes in the quality of peace-reporting in media.

# Output 2:	Public awareness about conflict resolution, peace-building and reconciliation is raised through a targeted media campaign

# Key Activities:

- Produce and broadcast media and communication materials (Public Service Announcements for TV and radio, billboards, newspaper and web ads, etc). Produce special programmes, reportages, talk shows, etc on peace-building.

- Organize press-trips to the field to collect and disseminate best practices and conflict resolution stories from peace building initiatives.

- Evaluation and monitoring: conduct pre- and post-intervention survey on changes in public perceptions.

- Partnerships

UNICEF and UNHCR will be working in close collaboration on the project implementation with specific areas of responsibility. Although each agency will be responsible for particular outputs / activities the project will require very close coordination between and contributions from the participating agencies. UNICEF and UNHCR will have joint visibility and a coordinated approach to developing partnership with national and local media, media development organisations, press services, the Press Club, media resource centres, and others.

# In the planning process the agencies consulted a range of national and international stakeholders, who will be partners and beneficiaries of the project. This includes the press services of the Government and the President, INTERNEWS Agency, media experts, and Osh, Jalalabad and Batken media centres. The press service of the President’s Office and other stakeholders expressed great interest and made assurances of support to the project.

- Logical framework

|  | Measurable indicators and targets | Means of verification | Assumptions |
| --- | --- | --- | --- |
| Outcome(s) (to be achieved): Infrastructure for peace is strengthened through active participation of media in peace-building and reconciliation processes in the country | Number of materials promoting peace messages (stories, PSA, documentaries, articles etc) produced and printed/broadcasted - Broadcasting time, audience & statistics for materials produced within the project - Number of journalists and editors benefited from project (obtained grants and participated in training) and proportion of those who became change agents - Number of journalists outreached/journalists registered by the media resource centres/benefited from strengthened capacities of the centres - Change in public opinion and perception (indicators of the pre and post survey) - Decreased number stories containing hate speech transmitted by media | Content analysis (quality and quantity) Pre-and post intervention surveys Progress reports Project control means Feedback from partners and beneficiaries | The political and the security situation remain stable. No further conflict or violence occurs. Government policy toward media remains the same, no changes to restrict freedom of press is introduced. |
| Output 1. Capacities of the media for peace-reporting (peace journalism) is strengthened Output 2. Public awareness about the conflict resolution, peace-building and reconciliation is raised through targeted media campaign | Output 1. - Number of journalists trained - Quality of reporting increased Output 2. % of population of 16-45 heard of conflict-resolution, peace-building and reconciliation in the media | Progress Report Content analysis Narrative reports Pre-and post intervention surveys | Political situation remains stable. |
| Main Activities | Inputs | Rough Cost Estimate | Agencies responsible for mobilizing inputs |
| Activities under Output 1: 1.1. Upgrade media resource centres and improve registration of media (computer equipment, office supplies, Internet) | 1.1. Supplies, transportation, logistic | $25,749 | UNHCR |
| 1.2. Provide grants for media peace initiatives. The grants will be provided on the basis of the competition | 1.2. Local consultancy to disburse grants | $45,000 | UNICEF |
| 1.3. Conduct training of trainers (TOT) on peace reporting for media representative, media development organizations, schools of journalism, media experts, and media resource centres | 1.3. International consultancy, travel, honorarium, per diem, training facilities, training supplies, handouts, accommodation, overheads | $35,000 | UNICEF |
| 1.4. Conduct cascade trainings for provincial media journalists and students of schools of journalism in peace reporting. Involve government press services wherever possible. | 1.5. Local consultancy, honorarium, travel, per diem, training facilities, training supplies, handouts, etc | $30,764 | UNICEF |
| 1.5. Monitoring and evaluation: pre- and post-training content analysis to assess changes in the quality of peace-reporting in media. | 1.6. Local consultancy, contract fee | $15,000 | UNICEF |
| Activities under Output 2: 2.1. Produce and broadcast media and communication materials (Public Service Announcements for TV and radio, billboards, newspaper and web ads, etc). Produce and air special programmes, reportages, talk shows, etc on peace-building. | 2.1. Local consultancy, production/contract fee, creative company | $83,400 - | UNHCR |
| 2.2. Organize press-trips to the field to collect and disseminate best practices and conflict resolution stories from peace building initiatives | 2.3. Travel, per-diem, transportation, etc. | $10,000 | UNHCR |
| 2.3. Monitoring and evaluation. Conduct pre- and post-intervention survey | Local consultancy, contract fee | $10,000 | UNHCR |

- Budget

| PBF PROJECT BUDGET - UNHCR / UNICEF (Annex 6) |
| --- |
| CATEGORIES | UNICEF | UNHCR | Consolidated |
| 1. Supplies, commodities, equipment and transport | 0 | 35,749 | 35,749 |
| 2. Personnel (staff, consultants and travel) | 30,000 | 23,600 | 53,600 |
| 3. Training of counterparts | 65,764 | 0 | 65,764 |
| 4. Contracts | 60,000 | 83,400 | 143,400 |
| 5. Other direct costs | 0 | 10,000 | 10,000 |
| Sub-Total Project Costs | 155,764 | 152,749 | 308,513 |
| Project Support Cost (7%) | 10,903 | 10,692 | 21,595 |
| TOTAL | 166,667 | 163,441 | 330,108 |

Total requested by Agency for operations and staffing

UNICEF: $ 166,667

UNHCR: $ 163,441

Total:     $ 330,108, including 7% project support cost

- Monitoring and evaluation

The components of the project will be monitored by regular field monitoring reports and activity reports from implementing partners. They will also be evaluated at the end of the project. Both components have initial studies and post-activity evaluations that will help assess the changes. There is a special focus on monitoring quantitative and qualitative indicators. Not only will the number of journalists trained be monitored but also the quality of their peace reporting.

Means and tools for the project monitoring: direct monitoring and participation in the project activities; reports by implementing partners; feedback from beneficiaries and partners involved in the project; media coverage and media products.

7.  Analysis of risks and assumptions

A major risk for project implementation pertains to the overall deterioration of the socio-economic, political and security situation in the country. Although it has stabilised to a certain extent during the second half of 2010 and beginning of 2011, the overall situation in the country and in southern Kyrgyzstan in particular remains precarious. More political turbulence or severe worsening of economic conditions could lead to civil unrest, escalation of violence and even population displacement. This could all negatively affect and disrupt implementation of the project.

Another risk is related to Government policy toward media development. As long as the Government does not change its media development policy from relative freedom to censorship, the project will fulfil its objectives. Previous regimes have restricted media.

UNHCR and UNICEF also assume that the public will be receptive to the media campaign on peace and reconciliation as it will be developed based on the findings of the initial survey, taking into account all cultural and language peculiarities, as well as stereotypes among the population.

# Footnotes

Report of the National Commission posted on Fergana.ru on 20.01.2011