## all agencies
Annex A: Work Plan (Year III) - MDG Achievement Fund Culture - Bosnia and Herzegovina
|  |  | Expected BiH UNDAF Outcome 1: | Strengthened accountability and responsiveness of governments to pro-active citizens.
|  |  | Outcome 2: | Improved access to and quality of education, health and social protection services.
JP Outcome 1: Developed and implemented cultural policies and legal frameworks
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Source of Funds | Budget Description (Expenditure Account) |  | Remaining funds from Year II | Planned Budget Y III
[13 empty] | Total Amount | Total Amount
(List of Output & Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
1.1 | Improved policies & legal frameworks in culture and education sectors | [11 empty] | 332265.1199 | 373678.9358
•Working groups for statistics uses improved instruments for data collection and reporting on cultural statitstics |  | 1.1.1. | Complete mapping of the culture sector and related industries using gender-sensitive approach to identify economic and social potentials and complete Culture Portal implementation by line ministries. |  |  |  |  | UNDP | MoCA | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 19082.78 | 15000
•Institutional web culture portal funtioning and in use by state and enity level ministries for dissemination of information to citizens and non-governmental sector | [8 empty] | MoCs |  | 1.2 | Personnel (staff, consultants, travel and training) | 3805.59 | 1189.93
•Data for Compendium (relevant data for culture sector) updated and trends in the sector reported on. | [8 empty] | Statistical Agencies |  | 1.3 | Training of counterparts | 8422.81 | 0
•Gender trainings in cooperation with Agencies for gender equality prepared for culture workers at all levels of government. |  | a. | Implement activities related to culture sector and related culture industries overview using gender-sensitive approach. | [7 empty] | 1.4 | Contracts | 19924.94 | 42000
[11 empty] | 1.5 | Other direct costs | 127.02 | 29000
[11 empty] | 2.0 | Indirect support costs 7% | 3595.4198 | 6103.2951
|  | b. | Improve cultural statistics and align methodology with EUROSTAT and NACE cultural industry classification. |  |  |  |  | UNDP | MoCA | MDG-F
MoCs
|  | 1.1.2 | Assist programme stakeholders in policy development. |  |  |  |  | UNDP | MoCA, MOCs | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 6054.55 | 0
|  | a. | Facilitate the production and implementation of the Action Plan based on National Cultural Policy Strategy through a participatory process and with inclusion of all relevant institutions. | [7 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 103390.45 | 1500
•Action plan for implementation of culture strategy promoted among cantonal level of government and civil society sector. | [10 empty] | 1.3 | Training of counterparts | 0 | 0
•Priorities from the Action plan supported through MDGF Programme (reccommendations for young talents; analysis of capacities of institutes for cultural heritage) | [10 empty] | 1.4 | Contracts | 0 | 88000
•Analysis of culture industries prepared | [10 empty] | 1.5 | Other direct costs | 3.19 | 20590
•Prepation of action plan for strengthening of culture industries |  | b. | Provide technical assistance to governmental Working Groups for incorporating cross-cutting issues: gender, youth, and social inclusion in the Action Plan for implementation of the National Cultural Policy Strategy. | [7 empty] | 2.0 | Indirect support costs 7% | 7661.3733 | 7706.3
• Training from protection of author's copyrights for state and entity officials
•Culture management training for culture workers fully implemented and analysis of best pracitses presented to government partners.
•Public private partnership training and best practises analysis prepared and presented to cultural workers and government partners. |  | c. | Hold third-party-led consultations (study visits and exchange programmes) on cultural policy priorities and reporting procedures.
|  | d. | Arrange conferences on specific priorities in the cultural sector
|  | e. | Provide technical assistance to sectoral Working Groups for developing and targeted implementation of selected priority areas in the Action plan for Culture Strategy
|  | f. | Support Sectoral working group in continuing development of the Culture portal concept and visibility improvements for all three ministries in presentation of the culture sector.
|  | g. | Promote gender awareness through tailored trainings with policy makers, local stakeholders and media.
|  | 1.1.3 | Improving policies and their implementation to ensure access to quality multi-cultural education. |  |  |  |  | UNICEF | MoE, PI, PS in Core Localities | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 35046.63 | 4800
1 | Providing trainings for Junior Lectures at pedagogical academies/faculties in the area of intercultural education | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 248 | 59777.41
2 | Conducting workshops for Education WG to develop Code of Ethics | a. | Conduct studies and research on curricula and school environment and assist in implementation of recommendations. | [7 empty] | 1.3 | Training of counterparts | 0 | 0
3 | Organizing conference for presenting results of the WG from Y1 to Y3 | [9 empty] | 1.4 | Contracts | -10665.34 | 0
|  | b. | Facilitate the development of a multi-cultural ethics code for teachers, schools, pupils and parents and engage in exchange of experiences. | [7 empty] | 1.5 | Other direct costs | 36528.81 | 33983.6
[11 empty] | 2.0 | Indirect support costs 7% | 1050.02 | 6899.2707
|  | 1.1.4 | Supporting the preparation of policy documents, reporting mechanisms and legal frameworks (Capacity development). |  |  |  |  | UNESCO | MoE | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 0 | 0
| Further development of system for implementation monitoring of international conventions related to culture to which BiH is a signatory. Support to participation to all UNESCO conferences, round tables etc. related to UNESCOs conventions linked to 311a | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 24919.5 | 0
[11 empty] | 1.3 | Training of counterparts | 0 | 0
|  | a. | Facilitate the harmonisation of legal frameworks and methods of reporting with existing international conventions. | [7 empty] | 1.4 | Contracts | 33587.2 | 0
| Joint action with UNDP / see UNDP component, section 111 a and b | [9 empty] | 1.5 | Other direct costs | 1299.63 | 0
|  | b. | Provide technical support to the development of Action plan based on National Cultural Policy Strategy in BiH through a participatory process and with inclusion of all relevant institutions. | [7 empty] | 2.0 | Indirect support costs 7% | 4186.4431 | 0
Reccommendations for fostering responsivness of institutions dealing with cultural and natural heritage prepared.
|  | c. | Train major stakeholders on cultural diversity, policies and legal frameworks
Improvement of management capacities of culture sector institutions in connection with findings from Culture sector review findings.
1.2 | Strengthened capacities of State and Entity-level governments in monitoring and evaluation of cultural development
•Monitoring proces harmonised between ministries at state and entity level and system put into practise. |  | 1.2.1 | Providing monitoring and evaluation training activities to relevant government agencies. | [7 empty] | 1.1 | Supplies, commodities, equipment and transport | 4000
[8 empty] | UNDP | MoCA | MDG-F | 1.2 | Personnel (staff, consultants, travel and training) | 13910.11 | 0
|  | a. | Facilitate the harmonization of the collection of cultural data and ensure gender-sensitive collection of cultural data. | [5 empty] | MoCs |  | 1.3 | Training of counterparts | 11795.8
[11 empty] | 1.4 | Contracts | 0 | 18000
|  | b. | Technical assistance to establishment of functioning Working Groups for improved Monitoring and Evaluation mechanisms in the key government counterpart ministries (state and entity level). | [7 empty] | 1.5 | Other direct costs | 0
[11 empty] | 2.0 | Indirect support costs 7% | 2079.4137 | 1260
|  | 1.2.2 | Developing a system to monitor implementation of improved educational policies |  |  |  |  | UNICEF |  |  | 1.1 | Supplies, commodities, equipment and transport | 0 | 0
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 0 | 0
1 | Conducting workshops for Education WG to develop plan for monitoring and evaluation of quality assurance in education including list of indicators for intercultural education | a. | Technical assistance to the Agency for Pre-primary, Primary and Secondary Education to gauge childhood education performance versus international achievements | [7 empty] | 1.3 | Training of counterparts | 0 | 0
2 | Conducting workshops for staff of PI and MoE is involved in monitoing and evaluation | [9 empty] | 1.4 | Contracts | 2063.42 | 35350
[11 empty] | 1.5 | Other direct costs | 0 | 41.71
[11 empty] | 2.0 | Indirect support costs 7% | 147.36 | 2477.42
JP Outcome 2: Improved cross-cultural understanding at a community level | [12 empty] | 2248.7419 | 564444.1513
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Planned Budget
[10 empty] | Source of Funds | Budget Description (Expenditure Account) |  |  | Total Amount
(List of Output Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
2.1 | Promoted models of social inclusion in primary schools of project target communities.
1 | Carrying out monitoring visits to schools for evaluation of their projects | 2.1.1 | Developing community level educational approaches to address ethnically-based inequalities. |  |  |  |  | UNICEF | MoCA, MoE, PI, PS in Core Localities | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 0 | 0
2 | 2 day workshops for primary school teacher training | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 26176.47 | 45450.66
3 | Provison of grants to NGOs | [9 empty] | 1.3 | Training of counterparts | -27206.27 | 115000
4 | Implementation of the NGOs projects | [9 empty] | 1.4 | Contracts | 17434.69 | 45000
5 | Public presentation of primary schools projects results | [9 empty] | 1.5 | Other direct costs | 2334.47 | 1443.85
6 | Translation into English and printing of the publication “ABC on culture and tradition of BiH people” | [9 empty] | 2.0 | Indirect support costs 7% | 1311.76 | 14482.61
7 | Printing and distribution of the publication of “Child Friendly School”
8 | Printing and distribution of publication “Learning to Live Together” | [9 empty] | `
1 | Establishing and interviewing focus group before the campaign | 2.1.2 | Analysing and addressing barriers to cross-cultural tolerance. |  |  |  |  | UNICEF | Core Localities | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 15200 | 0
2 | Interviewing focus group after the campaign | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 0 | 0
3 | Analysis of the results and dissemination of the information | [9 empty] | 1.3 | Training of counterparts | 0 | 0
[11 empty] | 1.4 | Contracts | -3994.65 | 25250
[11 empty] | 1.5 | Other direct costs | 47.74 | 29.8
[11 empty] | 2.0 | Indirect support costs 7% | 787.72 | 1769.59
2.2 | Enhanced local initiatives delivering positive cross-cultural messages.
•Local partner municipality project fully implemented and sustainability measures secured |  | 2.2.1 | Supporting community-based creative initiatives that improve cross-cultural understanding. |  |  |  |  | UNDP |  | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 2506.07 | 0
•CSO projects fully implemented addressing intercultural understanding through improved access to culture and Performing Arts for Understanding | [10 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 65932.77 | 1140
|  | a. | Building on Cultural Memory for improving understanding | [7 empty] | 1.3 | Training of counterparts | 0 | 0
•New activity: Association of blind and poor sighted people based on priorities in both entities assisted with equipment for improved living |  | b. | Supporting building Social Capital through culture and performing arts | [7 empty] | 1.4 | Contracts | -197104.25 | 248452.7
• Trainings on Intercularalism (Intercultural navigators) fully implemented in all 10 priority municipalities of the programme in cooperation with British Council. | [10 empty] | 1.5 | Other direct costs | 1051.97 | 500
|  | c. | Ensuring inclusion of minorities or socially excluded categories through implementation of culture projects | [7 empty] | 2.0 | Indirect support costs 7% | -8932.9408 | 17506.489
|  | 2.2.2 | Reinforcing stakeholder capacities in the field of intercuturalism. |  |  |  |  | UNESCO | Policy makers | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 2000 | 0
| 30 participants (local decision makers) from related ministries at all three levels, selected municipalities and CSOs trained in cultural diversity focusing on intercultural understanding and mediation. The training is to be jointly organized with UNICEf including provison of traning to managment staff from 83 scholls from selected municipalities. | [7 empty] | CSOs |  | 1.2 | Personnel (staff, consultants, travel and training) | 43499.66 | 12250
[11 empty] | 1.3 | Training of counterparts | 0 | 0
|  | a. | Build capacity of local level decision-makers to manage cultural diversity in their communities focusing on intercultural education and mediation skills using a gender-sensitive approach. | [7 empty] | 1.4 | Contracts | 48400 | 32500
[11 empty] | 1.5 | Other direct costs | 5822.95 | 500.89
[11 empty] | 2.0 | Indirect support costs 7% | 6980.5827 | 3167.5623
|  | b. | Build capacity of community-based organisations in approaches to cultural sensitivity (focus on intercultural mediation). |  |  |  |  | UNESCO |  | MDG-F
|  | c. | Organise in partnership with universities and civil society, workshops and public debates about cultural diversity.
|  | d. | Engage civil society in European and regional cooperation projects and networks. |  |  |  |  | UNESCO |  | MDG-F
JP Outcome 3: Strengthened cultural industries | [12 empty] | 307135.6569 | 490990.9
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Planned Budget
[10 empty] | Source of Funds | Budget Description (Expenditure Account) |  |  | Total Amount
(List of Output Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
3.1 | Increased employment and profitability levels within the cultural industries.
Guidelines for Directory developed and the tentative list of Intangible Heritage completed. |  | 3.1.1 | Supporting artistic-entrepreneurs through strategising, marketing and vocational training. |  |  |  |  | UNESCO |  | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 2000 | 0
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 51403 | 0
[11 empty] | 1.3 | Training of counterparts | 0 | 0
|  | a. | Create a directory of intangible cultural heritage of Bosnia and Herzegovina and provide trainings to relevant stakeholders. | [7 empty] | 1.4 | Contracts | 23806.83 | 0
[11 empty] | 1.5 | Other direct costs | 7612.63 | 0
[11 empty] | 2.0 | Indirect support costs 7% | 5937.5722 | 0
30 participants trained from 10 core localities and additional 13 municipalities, further trained in 2011, |  | b. | Assist cultural organisations in targeting local and international markets and obtaining financial sustainability.
|  | c. | Provide training for artists on quality standards, labelling, regulatory frameworks and copy-rights.
•Local partner municipality project fully implemented and sustainability measures secured |  | 3.1.2 | Promoting cultural industries and cultural tourism. |  |  |  |  | UNDP |  | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 514.77 | 4500
•CSO projects fully implemented addressing innovative craft design and Culture Tourism |  | a. | Run professional courses for culture workers and tourism providers. | [7 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 133184.68 | 1770
[11 empty] | 1.3 | Training of counterparts | 39887.71 | 0
•Priorities in Mostar, Trebinje and Ravno reconstructed and revitalised in cooperation with UNESCO. |  | b. | Improving the economic role of cultural industries | [7 empty] | 1.4 | Contracts | 15176.2 | 452000
•Selected priorities from technical fund supported for culture heritage rennovation. | [10 empty] | 1.5 | Other direct costs | 13456.85 | 600
|  | c. | Development of sustainable cultural tourism products in BiH and branding cultural products in BiH. | [7 empty] | 2.0 | Indirect support costs 7% | 14155.4147 | 32120.9
|  | d. | Support to the museum sector and cultural institutions in BiH
JP Outcome 4: Improved tolerance towards diversity | [12 empty] | 760442.663 | 351089.6906
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Planned Budget
[10 empty] | Source of Funds | Budget Description (Expenditure Account) |  |  | Total Amount
(List of Output Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
4.1 | Increased number of positive public discourses on interculturalism.
•Documentary films prepared and publisized on different film festivals and other filmmaking industry events - promoting filmmaking in Bosnia and Herzegovina and strengthening the concept of interculturalism. |  | 4.1.1 | Promoting intercultural awareness and sensitivity through media and stakeholder partnerships. |  |  |  |  | UNDP |  |  | 1.1 | Supplies, commodities, equipment and transport | 0 | 0
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 23822.19 | 100
•Web portal on interculturalism for citizens fully functional |  | a. | Analyse the degree to which messages in the media are delivered in a culturally-sensitive and gender-sensitive manner and present findings. | [7 empty] | 1.3 | Training of counterparts | 28708.15 | 0
•Ensure education for media and culture workers through promotion of interculturalism and diversity in media. •Training for journalists fully prepared and implemented in order to measure positive results related to culture sensitivity in media. | [10 empty] | 1.4 | Contracts | 24181.53 | 70500
|  | b. | Undertake gender-sensitive information campaign and support media production of cultural diversity, tolerance and understanding. | [7 empty] | 1.5 | Other direct costs | 20.57 | 100
[11 empty] | 2.0 | Indirect support costs 7% | 5371.2708 | 4949
|  | c. | Production of documentaries and feature films on intercultural understanding and support of young talent for cinematography
|  | d. | Development of interactive culture mapping and cultural ID forum for BiH
1 | Carrying out workshops with students, parents, local authorities, media in 10 localities to develop specific messages | 4.1.2 | Promoting intercultural sensitivity in the education sphere. |  |  |  |  | UNICEF |  |  | 1.1 | Supplies, commodities, equipment and transport | 10000 | 0
2 | Production and dissemination of materials for the campaign | [9 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 88200 | 0
3 | Production and dissemination of web game | a. | Organise a gender-sensitive Behaviour Change Communication (BCC) campaign. | [5 empty] | Media, Core Localities | MDG-F | 1.3 | Training of counterparts | 7000 | 17737.7
4 | Media Campaign for dissemination of messages | [9 empty] | 1.4 | Contracts | 50000 | 0
[11 empty] | 1.5 | Other direct costs | 2038.14 | 20.93
[11 empty] | 2.0 | Indirect support costs 7% | 22.09 | 1243.1
|  | b. | Develop and disseminate specific messages at community level.
|  | 4.1.3 | Rehabilitating and restoring major symbols of interculturalism. |  |  |  |  | UNESCO |  | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 21000 | 6000
Restoration of 11 monuments/ sites (identified by MoE with entities MCs and endorsed by PMC) completed as follows: | [10 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 369 | 60000
Derventa 2, Banja Luka, Jajce, Mostar 2, Tesanj, Foca-Sutjeska, Trebinje, Ravno |  | a. | Initiate the restoration of ten (10) monuments - tangible symbols of BiH inteculturalism. Activities on restoration of monuments for culture tourism promotion. | [7 empty] | 1.3 | Training of counterparts | 0 | 0
[11 empty] | 1.4 | Contracts | 439468.8 | 168662.58
|  | b. | Prepare a cultural tourism framework for restoration activities. | [7 empty] | 1.5 | Other direct costs | 26151.66 | 5000
[11 empty] | 2.0 | Indirect support costs 7% | 34089.2622 | 16776.3806
JP Monitoring and Evaluation | [12 empty] | 26869.6153 | 82715.9648
Annual Targets |  | Activities |  | Time Frame (Year II) |  |  |  | UN Agency | Responsible Party | Planned Budget
[10 empty] | Source of Funds | Budget Description (Expenditure Account) |  |  | Total Amount
(List of Output Annual Targets) |  |  |  | Q1 | Q2 | Q3 | Q4
Monitoring of projects implemented in line with Guidelines for joint programme implementation for achieveing MDGs. |  | M&E | Monitoring and Evaluation |  |  |  |  | UN RC | Agencies | MDG-F | 1.1 | Supplies, commodities, equipment and transport | 17518.96 | 5333.33
[11 empty] | 1.2 | Personnel (staff, consultants, travel and training) | 1028.81 | 37331.31
[11 empty] | 1.3 | Training of counterparts | 0 | 0
[11 empty] | 1.4 | Contracts | 0 | 27000
[11 empty] | 1.5 | Other direct costs | 6564.02 | 7640
[11 empty] | 2.0 | Indirect support costs 7% | 1757.8253 | 5411.3248
Total | [12 empty] | 1428961.797 | 1862919.6425
JUSTIFICATION FOR HARMONISED BUDGET CATEGORY OVER-EXPENDITURE
*Under Activity 113 Agency UNICEF; 1.4 Contracts: -10,665.34 : This activity was over expended under this harmonized budget category due to the fact that the actual work on policy support was implemented both by the government institution (Agency for Pre,Primary and Secondary Education) and international consultant (individual) providing technical and expert assistance. Therefore two contracts were signed (one institutional and one individual) for this activity and their total amount is slightly higher from the initially budgeted amount.
*Under Activity 211 Agency UNICEF; 1.3 Trainings: -27,206.27 :T he training for schools from selected project locations took place as part of the Agreement that UNICEF signed with the government institution (Pedagogical Institute Bihac). The activity started at the beginning of the school year and is carried forward into 2011 (school year 2010/2011 ends in June 2011)
*Under Activity 212 Agency UNICEF; 1.4 Contracts: -3,994.65: This budget category is slightly over expended due to the fact that UNICEF signed one individual and one institutional contract with “Partner MCA” and Mr. Josip Tvrtkovic to conduct a complex behavior study.
*Under Activity 221 Agency UNDP; 1.4 Contracts: -197,104.25 : This negative balance is presented due to commitment of overall contract values for CSO projects while tranches for completion of projects will be realised in year 3.. Sufficient funds for these activities are allocated in year 3.
*UNESCO will transfer all unspent amounts from year 2 to the account code 'Contracts'. This will not cause changes to any of the proposed results as originally planned in the project document.
NOTE: Amounts per agency for the third tranche have been modified as per communication with MDTF secretariat and adjusted request for funds will be sent out. This is due to savings incurred under M&E budget line that was administered under UNDP budget. Amount of US$ 10,606.49 is split among agencies using the % of agency share in the overall JP budget. Allocation between agencies is the following: UNICEF -US$ 2,329.83; UNESCO-US$ 2,442.27;UNDP-US$ 5,834.39

## Table 1
Table 1: Summary of Results Framework - MDG Spain Culture - Bosnia and Herzegovina (BiH)
| Expected BiH UNDAF Outcome 1: | Strengthened accountability and responsiveness of governments to pro-active citizens.
| Outcome 2: | Improved access to and quality of education, health and social protection services.
| Overall JP Outcome |  | Strengthened Cross-cultural Understanding in Bosnia and Herzegovina. | [7 empty] | 7999999.9986
JP Outputs |  | SMART Outputs and Responsible |  | Reference to Agency priority or Country Programme | Implementing Partner | Indicative activities for each Output |  | Resource allocation and indicative time frame
|  | UN Organization | [5 empty] | Y1 | Y2 | Y3 | Total
| Joint Programme Outcome | 1: | Improved policies & legal frameworks in culture and education sectors. | [7 empty] | 2318678.338
1.1 | Improved policies & legal frameworks in culture and education sectors. |  | Comprehensive cultural statistics collected to enable evidence-based analysis, planning and monitoring of Culture sector in BiH. | UNDP | MoCA/ MoCs | 1.1.1. | Providing the evidence-base for strategy implementation in the culture sector. | 241003.5686 | 99713.2786 | 93293.2251 | 434010.0723
| Indicator: Culture Sector mapped, including detailed analysis of culture public sector (legislative, financial, infrastructure and human resources analysis), new classification of cultural industries and comprehensive culture sector research. Baseline: No complete overview of cultural resources in BiH available. |  |  |  |  | a. | Map the cultural sector and related industries using gender-sensitive approach to identify economic and social potentials and create Culture Portal.
| Indicator: Cultural web framework developed following the pre-approval of the conceptual framework. Baseline: No systematic promotion and communication platform for BiH culture sector (2008) |  | Comprehensive and multi-functional BiH culture web framework developed that enables systematic promotion of BiH culture sector and improved communication among BiH's culture institutions and culture sector. |  |  | b. | Improve culture statistics and align methodology with EUROSTAT with ref. to NACE cultural industries registration.
| Indicator: BiH Action Plan based on National Cultural Development Strategy developed through a participatory process and agreed by institutional partners and PMC. Baseline: BiH Culture Strategy developed and adopted in Dec 2008. |  | Strengthened development, management and planning capacities of culture sector institutions. | UNDP | MoCA/ MoCs | 1.1.2. | Assist programme stakeholders in policy development. | 466533.9121 | 391781.57 | 117796.3 | 976111.7821
| Indicator: Cross-cutting issues: Gender, Youth and Social Inclusion in the Culture Sector addressed in the BiH Action Plan based on National Cultural Development Strategy. Baseline: Cross-cutting priorities identified in the BiH Culture Strategy. |  |  |  |  | a. | Facilitating the production and implementation of the Action Plan based on National Cultural Development Strategy through a participatory process and with inclusion of all relevant institutions.
| Indicator: Evidence-based research (KAP study) conducted in select municipalities to ensure greater understanding of perceptions of intercultural understanding and the importance of social inclusion (2009 and 2011) Baseline: 0 |  |  |  |  | b. | Provide technical assistance to Governmental Working Groups for incorporating cross-cutting issues: gender, youth, social inclusion in the Action plan for implementation of the National Cultural Development Strategy.
[6 empty] | c. | Hold third-party-led consultations (study visits and exchange programmes) on cultural policy priorities and reporting procedures.
| Indicator: # of activities/issues identified in the BiH Action Plan based on National Cultural Development Strategy, jointly addressed by institutional partners (2011). Baseline: BiH Culture Strategy developed and adopted in Dec 2008. |  |  |  |  | d. | Arrange mini-conferences on specific priorities in the cultural sector identified in the research conducted in activities 1.1.1.
[6 empty] | e. | Tailored methodological support to policy making.
| Indicator: # of policy recommendations from the Cultural Mapping included in the Culture Strategy Action Plan (2011) Baseline: BiH Culture Sector Mapping findings and Culture Sector Development Plan (2010) |  |  |  |  | f. | Provide technical assistance to sectoral Working Groups for developing Cultural Strategy and Culture Portal.
| Indicator: Institutional capacities in planning and management for the culture sector improved Baseline: Existing institutional practices (2008) and Training Needs Analysis (2009) |  |  |  |  | g. | Build capacities of relevant institutions in preperation for the implementation of Culture Strategy.
[6 empty] | h. | Promoting gender-sensitive awareness through tailored trainings with policy makers, local stakeholders and media.
| Indicator: Report on existing curricula from the perspecitve of intercultural understanding prepared through the MoE Working Group (2009) Baseline: Lack of systematic analysis of curricula and school practices from an intercultural perspective. |  | Improved policies and legal frameworks in education sector to ensure access to quality multi-cultural education. | UNICEF | MoES | 1.1.3 | Improving policies and their implementation to ensure access to quality multi-cultural education. | 346285.6355 | 219262.6331 | 105460.28 | 671008.5485
| Indicator: (Contribution to) positive assessment of education sector of BiH (2011) Baseline: Report on existing curricula from an intercultural perspective (2009) | [5 empty] | Conduct studies and research on curricula and school environment and assist in implementation of recommendations.
| Indicator: Improved modalities for accessing and enhancing in-service teachers’ competences for intercultural and inclusive education Baseline: No analysis on teachers’ competences for intercultural and inclusive education (2008) | [5 empty] | Facilitate the development of a multi-cultural ethics code for teachers, schools, pupils and parents and engage in exchange of experiences.
| Indicator: State law on protection of cultural heritage adopted (2011). Baseline: No law on cultural heritage. |  | Improved legislative framework for culture protection and adherence to UNESCO conventions. | UNESCO | MoCA | 1.1.4 | Supporting the preparation of policy documents, reporting mechanisms and legal framework (Capacity development). | 50402.7352 | 28968.7841 | 0 | 79371.5193
Facilitate the harmonisation of legal frameworks and methods of reporting with existing international conventions.
| Indicator: Publication with all conventions to which BiH is a State Party produced. (2009) Baseline: No overview of (translated) systematically presented conventions to which BiH is a State Party. | [5 empty] | Provide technical support to the development of Action plan based on Cultural Strategy through a participatory process and with inclusion of all relevant institutions.
Train major stakeholders on cultural diversity, policies and legal framework.
1.2 | Strengthened capacities of State and Entity-level Governments in monitoring and evaluation of cultural development. |  | Strengthened M&E capacity of the culture sector institutions | UNDP | MoCA, MoCs | 1.2.1 | Providing monitoring and evaluation training activities to relevant government agencies. | 23540 | 39638.15 | 19260 | 82438.15
Facilitate the harmonisation of the collection of cultural data and ensure gender-sensitive collection of cultural data.
| Indicator: Institutional M&E functions strengthened and M&E systems introduced (2011) Baseline: No systematic M&E practices in place (2008) | [5 empty] | Technical assistance to establishment of functioning Working Groups for improved Monitoring and Evaluation mechanisms in the key government counterpart ministries (state and entity level).
| Indicator: One operational and accessible monitoring system for cultural development indicators for policy development in education (2011). Baseline: No systematic monitoring of education policy in BiH (2008) |  | Strengthened capacities and M&E function of the BiH Agency for pre-school, primary and secondary education in monitoring education policy in BiH. | UNICEF | SAA | 1.2.2 | Developing a system to monitor the implementation of improved educational policies. | 0 | 37869.1329 | 37869.1329 | 75738.2658
Provide cultural indicator monitoring assistance to the 'Agency for Pre-, Primary and General Secondary Education' to gauge childhood education performance versus international achievements.
| Joint Programme Outcome | 2: | Improved cross-cultural understanding at the community level. | [7 empty] | 1949959.9682
2.1 | Promoted models of social inclusion in primary schools of project target communities. |  | Ethnically-based inequalities addressed in primary schools in project target communities by Year III. | UNICEF | Education Ministries | 2.1.1 | Developing community level educational approaches to address ethnically-based inequalities. | 151477.2537 | 333891.8385 | 221377.1276 | 706746.2198
| Indicator: Evidence-based research conducted in select municipalities (KAP Study) to ensure greater understanding of individual perceptions of pupils, parents teachers on cross-cultural understanding and importance of social inclusion (2009 and 2011) Baseline: 0 | [5 empty] | Develop educational models for joint interventions promoting social inclusion in formal and non-formal environments.
Provide small infrastructure grants to create spaces for multicultural interactions among students.
Provide teacher training programmes on interculturalism, equality and social justice.
Prepare the consolidated and standardised Child-friendly School "tool kit" to 1,000 schools.
Support local civil society organisations for multicultural activities outside traditional school settings.
| Indicator:Targeted educational interventions for improvement of school practices in setting intercultural and inclusive attitudes and practices delivered in up to 10 target communities (2011). Baseline: Findings of KAP study (2009) |  | Improved tolerance in target communities by Year III. | UNICEF | Universities | 2.1.2 | Analysing and addressing barriers to cross-cultural tolerance. | 27049.3806 | 16229.6284 | 27049.3806 | 70328.3897
| Indicator: # of recommendations implemented from the Report on existing Curricula from an Intercultural Prespecitve and from the Mapping of Teacher's Competencies for intercultural and inclusive education (2011) Baseline: Report on existing Curricula from an Intercultural Prespecitve and from the Mapping of Teacher's Competencies for intercultural and inclusive education | [5 empty] | Conduct a gender-sensitive KAP (Knowledge, Practices, Attitudes) study on behavioural attitudes about interculturalism.
2.2 | Enhanced local initiatives delivering positive cross-cultural messages. |  | Up to 40 community-based culture projects undertaken, which address barriers to cross-cultural tolerance, by Year III. | UNDP | CSOs, Local Development Agencies, other | 2.2.1 | Supporting community-based creative initiatives that improve cross-cultural understanding. | 186757.8 | 561536 | 267599.19 | 1015892.99
Indicator: # of intercultural projects supported (up to 40) specifically at community level. Baseline: Situation analysis provided in project proposals (2009)
Indicator: Good practice community projects with replicable potential documented and promoted widely, and experiences from the field level provided to policy makers as valuable inputs for policy debate (2011) Baseline: ToRs of selected community projects and KAP study (2009)
| Indicator: # of local decision makers and NGO actors participated in public debates and trainings on promotion of interculturalism (2009-2011). Baseline: 0 |  | Strengthened local capacities in management of cultural diversity and promotion of interculturalism. | UNESCO | Universities & CSOs | 2.2.2 | Reinforcing stakeholder capacities in the field of intercuturalism. | 58614.8568 | 49959.0597 | 48418.4523 | 156992.3688
Build capacity of local level decision-makers to manage cultural diversity in their communities focusing on intercultural education and mediation skill using gender sensitive approach.
Build capacity of community-based organisations in approaches to cultural sensitivity (focus on intercultural mediation).
Organise in partnership with universities and civil society, workshops and public debates about cultural diversity.
Engage civil society in European and regional cooperation projects and networks.
| Joint Programme Outcome | 3: | Strengthened cultural industries. | [7 empty] | 1637448.499
3.1 | Increased employment and profitability levels within the cultural industries. |  | Improved competitiveness of cultural industries sector in selected municipalities in BiH aiming at enhanced income-generation and employment opportunities. | UNESCO | Private Sector | 3.1.1 | Supporting artistic-entrepreneurs through strategising, marketing and vocational training. | 75974.1409 | 98302.8581 | 0 | 174276.999
Indicator: Tentative List* of Intangible Cultural Heritage, and inventory of cultural products of BiH prepared and utilised for training purposes in year III. * according to the 2003 Convention for the Safeguarding of the Intangible Cultural Heritage Baseline: Culture Sector Mapping and identification of business skills in demand by artisans in BiH (2010)
Create a directory of intangible cultural heritage of Bosnia and Herzegovina.
| Indicator: At least 80 artisans and culture sector subject trained (2010). Baseline: Other UNESCO trainings. | [5 empty] | Build capacities of artistic entrepreneurs.
Assist the development of wholesaling targeting local and international markets.
Provide training for artists on quality standards, labelling, regulatory frameworks and copy-rights.
| Indicator: Up to 30 local cultural industry, including tourism, projects implemented (2011). Baseline: 0 |  | Increased income-generation and local economic development potentials through culture-industry/culture tourism project implementation in BiH. | UNDP | MoCA/ Local Communities | 3.1.2 | Promoting cultural industries and culture tourism. | 235421.4 | 736759.2 | 490990.9 | 1463171.5
| Joint Programme Outcome | 4: | Improved tolerance levels towards diversity. | [7 empty] | 1879524.6633
4.1 | Increased number of positive public discourses on interculturalism. |  | Increased cultural sensitivity of the media by Year III | UNDP | Media | 4.1.1 | Promoting intercultural awareness and sensitivity through media and stakeholder partnerships. | 89674.025 | 145742.025 | 75649 | 311065.05
Indicator: Improved capacity of media professionals in delivering messages in a culturally and gender sensitive manner through trainings Baseline: Media analysis (2009) and findings of KAP study (2009)
Indicator: Increased dissemination of positive and affirmative messages that promote cultural understanding and contribute to social cohesion, greater tolerance and appreciation of cultural diversity in BiH (2011) Baseline: Media analysis (2009) and findings of KAP study (2009)
| Indicator: Increased cultural understanding, tolerance and appreciation of cultural diversity in project’s focus communities (2011) Baseline: findings of KAP study (2009) |  |  |  | Media company |  | Analyse the degree to which messages in the media are delivered in a culturally-sensitive and gender-sensitive manner and present findings.
| Indicator: # of Documentary films promoted intercultural understanding. Baseline: Academy of Film Arts official records (all relevant centers in BiH) |  | Communication strategy implemented through targetted interventions by Year III |  | Film artists/screen writers (NGOs) |  | Undertake gender-sensitive informational campaign and support media production of cultural diversity, tolerance and understanding.
Indicator: Communications strategy developed and implementated in coordination with media representatives, cultural opinion leaders and stakeholder groups (2010). Baseline: KAP study (2009)
| Indicator: Behavioural Change Campaign (BCC) designed (2010) and implemented (2011) in accordance with baseline findings. Baseline: Report on curricula from an intercultural perspective (2009) and findings of KAP study, section focussing on schools, pupils, parents, and teachers (2009) |  | Issues regarding discrimination in education recorded in Year II and addressed in Year III. | UNICEF | Schools, Media | 4.1.2 | Promoting intercultural sensitivity in the education sphere. | 48532.1441 | 118834.721 | 19001.7346 | 186368.5997
Organise a gender-sensitive Behaviour Change Communication (BCC) campaign.
| Indicator: # of recommendations implemented from the Report on existing Curricula from an Intercultural Perspective by 2011. Baseline: Report on existing Curricula from an Intercultural Perspective with recommendations (2009), KAP Study section focused on schools, pupils, parents and teachers and focus groups (2009) | [5 empty] | Develop and disseminate specific messages at community level.
| Indicator: Rehabilitation of at least five important symbols/tangible heritage which are common good of BiH. Baseline: 3 symbols/monuments selected by the PMC from the list of 767 national monuments of BiH (2009) |  | Increased awareness of BiHs rich interucltural traditions through the restoration and rehabilitation of important symbols | UNESCO | MoCA | 4.1.3 | Rehabilitating and restoring major symbols of interculturalism. | 425382.5393 | 700269.5143 | 256438.96 | 1382091.0136
Initiate the restoration of five (5) major tangible symbols of BiH interculturalism.
Prepare a cultural tourism framework for restoration activities.
|  |  | Monitoring and Evaluation | [7 empty] | 214388.53
Monitoring and Evaluation |  |  | Strengthened accountability of the joint programme. | UN RC | UN Agencies | M&E | Monitoring and Evaluation | 73679.369 | 57993.2011 | 82715.96 | 214388.53
Total | [7 empty] | 2500328.7607 | 3636751.5947 | 1862919.6432 | 7999999.9986
[7 empty] | UNICEF | 573344.4138 | 726087.9539 | 410757.6558 | 1710190.0235
[7 empty] | UNESCO | 610374.2721 | 877500.2162 | 304857.4123 | 1792731.9006
[7 empty] | UNDP | 1316610.0747 | 2033163.4247 | 1147304.5751 | 4497078.0744
[8 empty] | 2500328.7607 | 3636751.5947 | 1862919.6432 | 7999999.9986
16909.51
17690.54
44570.17
79170.22