CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

March 2008

| Participating UN or Non-UN Organization: | International Organization for Migration (IOM) |
| --- | --- |
| UNCAPAHI Objective(s) covered: | Objective 6: Continuity under Pandemic Conditions |
| Implementing Partner(s): | International Organization for Migration |
| Programme Number: | CFIA - B4 |
| Programme Title: | Pandemic Preparedness for Migrants and Host Communities |
| Total Approved Programme Budget: | US$ 990,000 |
| Location: | Cairo, Cambodia, Geneva Thailand and Vietnam |
| MC Approval Date: | 20 February 2008 |
| Programme Duration: | 12 months | Starting Date: | October 2007 | Completion Date: | September 2008 |
| Funds Committed: | US$ 990,000 | Percentage of Approved: | 100% |
| Funds Disbursed: |  | Percentage of Approved: |  |
| Expected Programme Duration: | 12 months | Forecast Final Date: | 30 Sept 2008 | Delay (Months): |  |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| 1. Project focal point and consultants to implement project in Cairo identified | IOM project focal point in Cairo has engaged with relevant stakeholders and shared the workplan of activities. IOM participate in pandemic and disaster management team meetings in Cairo Target population-urban Sudanese Migrants identified and contact being made with community leaders Technical support provided by IOM Geneva Head Quarters Baseline survey questionnaire and Focus Group Discussion FGD guides prepared and reviewed. These instruments will be tested in April. Community mobilization activities being defined to meet needs of identified target population | As planned |
| 2. IOM Asia Regional Coordinator identifies focal points and consultants in Cambodia and Vietnam | Orientation meetings on pandemic preparedness for migrants held with stakeholders in Cambodia and Vietnam | As planned |
| 3. Preparations for the implementation of a Knowledge, Attitudes and Practices (KAP) assessment on AHI among Vietnamese migrants construction working in Vientiane and Borikhamsai provinces | October – December 2007 AHI-IEC materials produced by UN agencies (UNICEF and FAO) and NGOs (CARE mainly) in Laos were collected for information. IOM has developed the research tools to be used for the baseline assessment. NAHICO agreed upon a proposed field-visit and meeting with provincial authorities in Bolikhamxay and Vientiane Provinces. The trip was scheduled for 8-10 January 2008. |  |
| 4. Meetings to collaborate with UN partners and the national government to ensure the inclusion of the needs of migrants and mobile populations in the avian influenza and human pandemic contingency plans. | IOM met NAHICO and UN agencies to share the project activities and workplan. IOM actively participates in AHI meetings and events in Laos and the region. |  |

Qualitative achievements against outcomes and results:

During this reporting period, IOM has made the following qualitative achievements: Pandemic preparedness for migrants as part of ongoing IOM activities is being promoted in IOM missions worldwide Project focal points and a consultants have been identified to implement this project in Cairo, Cambodia, Thailand and Vietnam. The global coordinator and team members in Geneva provide technical support to project locations as required Coordination meetings have been held with key stakeholders- key government authorities, UN and /NGO partners

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.

This date refers to the effective date of USAIDs Grant Agreement for contributions to CFIA’s second window. Although expenditure are eligible for reimbursement as of 1st October 2007, the actual CFIA Management Committee approval date is 20 February 2008, following the finalization of USAID’s Grant Agreement with the MDTF Office under a special arrangement in January 2008.