

**[UN BHUTAN COUNTRY FUND]**

**BI-ANNUAL PROJECT/PROGRAMME UPDATE**

**AS OF [31st December 2010]**

|  |  |
| --- | --- |
| **Participating UN Organization(s)** | UNICEF & UNFPA |
| **MDTF Programme Number** | 00073262 |
| **Programme Title** | **Health** |
| **Approved Budget** **(by PO, if applicable)** | **UNICEF: 56,646 & UNFPA: 141,453** |
| **Expenditure** **(by PO, if applicable)** | UNICEF: 56,646UNFPA: 141,453 | **% of Approved Budget****(by PO, if applicable)** | UNICEF: 100%UNFPA: 100% |
| **Forecast Final Date:**  | 31st December 2010 | **Delay****(if applicable)** | NA |

|  |
| --- |
| **Qualitative achievements against objectives and results:** |
| **Human resources within the health system was strengthened through the training of:** * Two paediatricians and a member of the National Commission on Immunization Practices vaccinology (Seoul)
* Two EPI technicians on basic maintenance of cold chain equipments and transportation of vaccines (India)
* Two health officials on Child Health Supervision and monitoring (Thailand)
* Four nurses on critical neo-natal care management (Thailand). As a result the neo-natal intensive care units at the national and referral hospitals are now fully staffed with knowledgeable and skilful staff.
* Participation of health authorities and a member of parliament in South Asia Breastfeeding forum

**Supply for quality service provision**:-* Purchase of RH commodities and printing and distribution of advocacy materials
* TA support for RH review (ASHR consultant)
 |