**Brazil**

|  |  |
| --- | --- |
| **Programme Title:** | Security with citizenship: preventing violence and strengthening citizenship with a focus on children, adolescents and youths in vulnerable conditions in Brazilian communities |
| **Programme number & MDTF ref:** | MDGF-1954-F-BRA Peace Security (67220) |
| **Window:** | Conflict Prevention & Peacebuilding |
| **Approved Budget by NSC (US$):** | 6 million |
| **Participating Organizations:** | UNHABITAT, UNODC, UNICEF, UNESCO, ILO, UNDP |
| **First Tranche transferred on:** | 15-Oct-2009 |

**ACTIVITIES REPORTED:**

|  |
| --- |
|  |
| **Main Substantive Activities:** |
| Public nationwide selection of municipalities completed and being used as reference at the re-modeling of the National Programme of Citizen Security. Inception workshop held on the three selected municipalities. Local management committees formed and fully engaged with the community. Study tours were carried out to Colombia and Rio de Janeiro to look at citizen security issues. Joint diagnosis methodology developed and implementation in course. Selection and training of consultants to implement the joint methodology. Certificate course on Citizen Security held on the 3 municipalities. Identification of local partners (GO & NGO) for the implementation of specific actions. Development of a communication strategy for social mobilization in course. Mapping of the institutional capabilities for the application of socio-educational measures to adolescents in conflict with the law. Definition of topics for school teachers training regarding the Open School Programme. |
| **Problems and lessons learned:** |
| **Problems:** coordination among several partners due to different levels of response. Incapacity of promoting the alignment of expectations arisen from the communities and local government towards the JP’s activities. Changes in governmental partners (elections). Difficulties on data collection at local level. Lack of qualified professionals to implement methodologies.  **Lessons learned:** Social mobilization and systematization strategies should be implemented from year 1 and continue throughout the JP. All JPs must allocate budget for communication and advocacy strategies. Develop in advance mitigating strategies regarding political changes that may impact directly in the JP. Internal communication must be well-structured to avoid possible duplication of actions. M&E structures must allow different levels of monitoring (processes and results). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** under development |

CHARTS & FIGURES

As of 31 December 2010

