**Cambodia**

|  |  |
| --- | --- |
| **Programme Title:** | Joint Programme for Children, Food Security and Nutrition |
| **Programme number & MDTF ref:** | MDGF-1992-I-KHM(67236) |
| **Window:** | Children Food Security& Nutrition |
| **Approved Budget by NSC (US$):** | 5 million |
| **Participating Organizations:** | FAO, ILO, UNESCO, UNICEF, WFP,WHO |
| **First Tranche transferred on:** | 7-Jan-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main organizational Activities:** |
| Completed (with the exception of some recruitment at provincial level). |
|  |
| **Main Substantive Activities:** |
| Multiple TV and radio spots promoting various aspects of the JP were aired. Baseline data gathered. Workshop for journalists on Food Security and Nutrition completed.Roundtable on breast feeding completed. Nutrition policy guidelines completed. Feasibility study to map malnutrition in small areas was completed. Formulation research on maternity protection in enterprises and factories completed.15 Farmer Field School (FFS) from each province established and trained with agricultural inputs provided. The implementation Management of Acute Malnutrition started in the five selected health centers of Kampong Speu province and will scale up in 2011 to both provinces. Multiple Micronutrient Powder started in SvayReing in early 2011. The Food Security Nutrition Data Analysis team established and already produced two Food Security Quarterly Bulletins. |
|  |
| **Problems and lessons learned:** |
| Managerial (recruitment delays). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

