Joint Programme Monitoring Report:

China Climate Change Partnership Framework

Section I: Identification and Joint Programme Status

a. Joint Programme Identification and basic data

| Date of Submission: Submitted by: Name: Renata Lok-Dessallien Title: UN Resident Coordinator & UNDP Representative Organization: UNDP Contact information: renata.dessallien@undp.org |  | Country and Thematic Window China/ Environment and Climate Change |
| --- | --- | --- |

| MDTF Atlas Project No: 67144 Title: China Climate Change Partnership Framework |  | Report Number: 2 Reporting Period: January – June 2010 Programme Duration: 3 years Official starting date: 8th May 2008 |
| --- | --- | --- |

| Participating UN Organizations: FAO, ILO, UNAPCAEM, UNDP, UNEP, UNESCO, UNICEF, UNIDO, WHO |  | Implementing partners Department of Climate Change, National Development and Reform Commission (DCC/NDRC), China Council for International Cooperation on Environment and Development, Ministry of Environmental Protection (CCICED/MEP), China International Centre for Economic and Technical Exchanges, Ministry of Commerce (CICETE/ MOFCOM), China International Institute of Multinational Corporations, Ministry of Commerce (CIIMC / MOFCOM), China Society for Promotion of the Guangcai Programme, United Front Work Department (CSPGP/UFWD), Ministry of Human Resources and Social Security (MHRSS), Ministry of Water Resources (MOWR), National Energy Administration (NEA), Ministry of Agriculture (MOA), Ministry of Health (MOH) |
| --- | --- | --- |

The financial information reported should include overhead, M&E and other associated costs.

| Budget Summary |
| --- |
| Total Approved Joint Programme Budget | FAO: 1,592,160 ILO: 214,000 UNAPCAEM: 214,000 UNDP: 3,528,695 UNEP: 1,278,650 UNESCO: 999,915 UNICEF: 995,100 UNIDO: 1,748,000 WHO:1,492,650 Total: 12,000,000 |
| Total Amount of Transferred to date | FAO: 1,592,160 ILO: 214,000 UNAPCAEM: 214,000 UNDP: 3,528,695 UNEP: 1,278,650 UNESCO: 999,915 UNICEF: 995,100 UNIDO: 1,748,000 WHO:1,492,650 Total: 12,000,000 |
| Total Budget Committed to date | FAO: 964,616 ILO: 155,000 UNAPCAEM: 200,000 UNDP: 2,562,046 UNEP: 710,000 UNESCO: 369,000 UNICEF: 501,000 UNIDO: 948,599 WHO: 305,500 Total: 6,715,761 |
| Total Budget Disbursed to date | FAO: 641,928 ILO: 55,750 UNAPCAEM: 175,279 UNDP: 2,522,355 UNEP: 652,201 UNESCO: 340,330 UNICEF: 315,500 UNIDO: 246,406 WHO: 199,750 Total: 5,149,499 |

BENEFICIARIES

Direct Beneficiaries: “The individuals, groups, or organizations, targeted, that benefit, directly, from the development intervention”.

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Institutions | 35 | 52 | 20,030 | 20,043 | 80,100 | 80,150 | - | - |
| Local Institutions | 96 | 97 | 35 | 22 | 180 | 131 | - | - |
| Urban | 1 | 20 | - | 30 | - | 105 | - | - |
| Rural | - | 11 | 515 | 615 | 1,285 | 1,495 | 120 | 120 |
| Total | 132 | 180 | 20,580 | 20,710 | 81,565 | 81,881 | 120 | 120 |

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Institutions | 10 | 68 | - | 155 | - | 315 | - | - |
| Local Institutions | 84 | 95 | - | - | - | - | - | - |
| Urban | - | - | 980,000 | - | 1,020,000 | - | - | - |
| Rural | - | 11 | 2,455 | 1,355 | 4,765 | 3,965 | 500 | 300 |
| Total | 94 | 174 | 983,335 | 1,510 | 1,028,965 | 4,280 | 500 | 300 |

Indirect Beneficiaries: “The individuals, groups, or organizations, not targeted, that benefit, indirectly, from the development intervention”

- Joint Programme M&E framework

(See M&E Framework in the following page)

| Expected Results | Indicators | Overall JP Expected target (The desired level of improvement to be reached at the end of the reporting period) | Update June 2010 | Responsibilities |
| --- | --- | --- | --- | --- |
| 1.1 Improved policies and partnerships at national-level to mainstream climate change mitigation and adaptation into policy frameworks | Indicator a: No. of scientists and officials having capacity for the post 2012 negotiations Baseline: 50 | 80 | - At present, 30 officials and 52 scientists have capacity for post-2012 negotiations. | UNDP CICETE ONLGCC |
|  | Indicator b: No. of studies carried out and disseminated on post-Kyoto strategies Baseline: 0 | 7+ 3 | 7 studies completed and presented at a UNFCCC COP15 Side Event. | UNDP CICETE ONLGCC |
|  | Indicator c: A knowledge hub for global best practices on mitigation and adaptation Baseline: No such information system | Commence preparations for High-Level Climate Change Adaptation Symposium, 3. Training (including CDM project development) | - The first activity of GCCC has been carried out (training on CDM for 20 participants from Southeast Asia and 80 domestic participants). The High-Level Climate Change Adaptation Symposium is scheduled for November 2010 during the UN Secretary General’s visit Beijing. | UNDP CICETE ONLGCC |
|  | Indicator d: No. of cooperative initiatives added into the south-south cooperation framework Baseline: 0 | Further training will take place after High-Level Adaptation Symposium and groundwork has been laid for establishment of GCCC | - Training on CDM carried out; 80 local and 20 international representatives from Pakistan, Laos, Nepal, Myanmar, Sri Lanka, and Bangladesh participated. | UNDP CICETE ONLGCC |
|  | Indicator e: A new high-level Climate Change Policy Task Force Baseline: No dedicated task force on climate change policy | One task force established. Research conducted and recommendations made at CCICED annual meeting | - The Task Force was established in September 2008. - Policy recommendations by Task Force were presented at 2009 CCICED annual meeting. | UNDP CICETE CCICED |
|  | Indicator f: Basic Energy Law draft Baseline: No basic energy law | Basic energy law drafted | - The draft Basic Energy Law was submitted to People’s Congress at end of 2009. | UNDP CICETE ONELG |
|  | Indicator g: Series of energy strategies Baseline: Lack of effective energy strategies | Eight special studies conducted | - Completed: detailed strategies presented in the report “Research on Relevant Rural Energy Issue”. | UNDP CICETE ONELG |
| 1.2 UN-business partnerships and new ‘green’ financing mechanisms to mainstream climate change and energy into investment frameworks and business practices | Indicator a: A UN-Business Compact on Climate Change, and series of high profile communication and awareness raising activities, including citizen engagement Baseline: No such compact | Two CEO forums organized Three climate change CSR workshops held. Three pilot enterprises trained on how to develop climate change CSR operational policies and how to develop CSR reporting | - The UN-Business Compact on Climate Change was launched. One CEO forum has been held. As of June 2010, the planned three climate change CSR workshops have been held. These workshops introduced climate change, CSR and the benefits that be realized by improving energy efficiency and reducing GHG emissions in terms of strengthening corporate image and increasing financial returns through energy cost savings. To date, three UN Global Compact pilot enterprises have been trained on how to develop climate change CSR operational policies and how to develop CSR reporting. Pilot enterprises have already applied or are in the process of applying to join UN Compact. | UNDP/UNIDO CICETE Guancai, CIIMC UNCTAD |
|  | Indicator b: No. of climate change-friendly designs and products from multinational firms Baseline: To be identified during the first year of the project implementation | Development of materials for dissemination | As of June 2010, one of the three main project publications is ready for release with the following two publications being finalized over the summer of 2010. The publications are: CSR Guidelines on Climate Change for Chinese Enterprises Climate Friendly Investment Financing for Chinese Enterprises Energy Efficiency and GHG Mitigation Best Practices for Chinese Enterprises In addition to these publications the CSR reports from the three UN Global Compact pilot enterprises have been produced and the Guangcai Programme website has been readied to launch a new GHG and climate change CSR sub-domain to host and continue the project concepts and materials. | UNDP/UNIDO CICETE Guangcai, CIIMC UNCTAD |
|  | Indicator c: Number of training institutes where GBO has been piloted Baseline: 0 | Commence training in 11 pilot provinces | Training of Trainers workshop has been completed, pilot training is ongoing in 11 provinces. | ILO MHRSS |
| 2.1 Development and dissemination at the local level of innovative models for energy efficiency | Indicator a: Partnership and financing for one pilot clean coal power plant Baseline: No clean coal power plant in the province | 10 pilots established, with three power plants. | - Partnerships have been formed with three pilot clean coal power plant and seven other coal-related enterprises. | UNDP CICETE, Shanxi Government, Earth Institute, CIIMC |
|  | Indicator b: Finalization and publication of China's Blue Paper on Clean Coal Technology | Volume One of China’s Blue paper on Clean Coal published | List of Contents finalized | UNDP CICETE, Shanxi Government, Earth Institute, CIIMC |
|  | Indicator c: Energy and resources efficiency model developed Indicator: model finalized Baseline: no model available Timeframe: 1st semester | CGB Sectoral Model Package ready for release by end of 2010. | - A sectoral study of the coal-gangue brick sector and the heat-recovery power generation sector in China has been completed. - Construction of the Coal-Gangue Brick Heat Recovery Power Generation Model Package is still ongoing pending completion of the first pilot upon which time an evaluation can be built in the model package. | UNIDO MOA Counterpart companies |
|  | Indicator d: Pilot bricks making factories established Indicator: Number of the pilots established: 2 Baseline: No enterprises using energy efficiency coal gangue technology Timeframe: 3rd semester | The first pilot fully operational and the second pilot selected and under construction. | - One pilot – Juyi Industrial is nearing construction completion with expected commissioning to occur in July 2010; Feasibility studies on 3 selected possible second pilot factory is ongoing and nearing completion. Upon completion and acceptance of these studies, the second pilot will be selected and the procurement process begun. | UNIDO MOA Project staff for pilot sites Counterpart companies / project staff from replication sites |
|  | Indicator e: Pilot bricks making factories performance Indicators (pilot sites): - Coal gangue brick production: No. 150 Millions/year - Energy production: 20,000 MW/year - Coal gangue recycled: 300,000 tonnes/year - Energy saving: 3,000 TCE/year - CO2 emission reduction: 6,000 tonnes/year - Unit energy consumption: 0 (Zero) TCE/ 1 Mil bricks (Coal gangue brick) Baseline: - Unit energy consumption: 132TCE/ 1 Mil bricks (Clay brick) Timeframe: 4th semester | The first pilot fully operational and the second pilot selected and under construction. | - As above, pilot will be operational at the end of July 2010. This will be a production line of 120 million bricks per year. Note: all other indicators will be addressed post pilot commissioning under the evaluation of the pilot HRPG plant. A major CDM assessment has been undertaken to determine feasibility of the CGB sector in regard to CDM. Unfortunately, the study has determined that the sector is not so feasible in terms of CDM. | UNIDO MOA Project staff for pilot sites Counterpart companies / project staff from replication sites |
|  | Indicator e: Technical competences upgraded Indicators: - Number of technicians trained and licensed: 60 Baseline: - No technicians available Timeframe: 5th semester |  | - Training of technicians commences in July 2010 for the Juyi Industrial plant. | UNIDO |
|  | Indicator f: New policy set up and financial tools established Indicators: - Energy generate has access to the grid and is marketable - Local policy and financial incentives available for power generation through waste heat recovering in coal gangue brick manufacturing Baseline: - No access to the grid - No specific policy and financial incentive to promote power generation through waste heat recovering in coal gangue brick manufacturing Timeframe: 4th semester | Findings to central Government by focus group. | - Significant investigations and consultations in regard to grid connection have taken place in 2009 and are continuing in 2010 within policy focus groups of relevant Government ministry officials. The first pilot needs to commissioned and evaluated before this process can be concluded and recommendations made to central Government. | UNIDO MOA |
|  | Indicator g: Public awareness campaign, rural areas Indicators: - Number of people aware of the problem and potential remedies Baseline: - Number of people aware of the problem and potential remedies Timeframe: 6th semester | One of three regional workshops held (by December 2010). | - The public or rather sectoral awareness campaign has begun with the documentary film. - Once the evaluation of pilot one has been completed three regional workshops will be held to attending CGB enterprise owners/operators. | UNIDO MOA |
|  | Indicator h: Monitoring and assessment of working condition and working environment. Set up efficiency management protocol and mitigation measures Indicators: - No. of enterprises monitored Set up protocol productivity parameters Baseline: - Baseline productivity parameters Timeframe: 3rd semester | Interim report made available to central Government on health and safety aspects in the CGB sector. | - This has been initiated under a joint UNIDO/WHO/ILO partnership. | UNIDO MOA ILO/WHO Enterprises |
|  | Indicator i: Specific conclusions and recommendations for application of CDM in biogas and conservation agriculture. Baseline: No recommendation | Final reports completed | - Conclusions and recommendations for the application of CDM in household biogas and conservation agriculture (CA) have been made in the final study report; - Methodological guidelines for the application of CDM in biogas and CA and are also available. | APCAEM FAO MOA, CAAE, CTRC |
| 2.2 Development and dissemination at the local level of innovative models for renewable energy in rural areas | Indicator a: No. of households surveyed for biomass supply; Baseline: 0 | 308 households surveyed and one survey report drafted | 308 households were surveyed and the report has been finished. | UNDP CICETE Energy Bureau of NDRC |
|  | Indicator b: No. of suppliers of pellet machinery surveyed; Baseline: 0 | 11 suppliers surveyed and one survey report drafted | 11 suppliers of pellet machinery were surveyed and the report has been finished. | UNDP CICETE Energy Bureau of NDRC |
|  | Indicator c: No. of households with stoves and boilers surveyed; Baseline: Not available | 308 households surveyed and one survey report drafted | 308 households were surveyed and the report has been finished. | UNDP CICETE Energy Bureau of NDRC |
|  | Indicator d: Feasibility study completed on rural biomass pellets; Baseline: no such study | One feasibility study report drafted | Feasibility study completed on rural biomass pellets | UNDP CICETE Energy Bureau of NDRC |
|  | Indicator e: No. of off-grid rural renewable power plants surveyed; Baseline: 0 | Five provinces surveyed | Since the indicators of 2.2.1 were not approved until NSC meeting in Q2 2010, work on off-grid rural renewable power plants has not yet started. | UNDP CICETE Energy Bureau of NDRC |
|  | Indicator f: No. of rural renewable power plants, TVEs and rural individuals trained. Baseline: 0 | Five provinces surveyed | Since the indicators of 2.2.1 were not approved until NSC meeting in Q2 2010, work on off-grid rural renewable power plants has not yet started. | UNDP CICETE Energy Bureau of NDRC |
| 3.1 Climate proofing of poverty reduction in less developed areas of West China and vulnerable coastal areas of Southeast China | Indicator a: Situation analysis report of glacier in Himalayas (2008) Baseline: no situation analysis report | Peer review conducted | - Two reports: “Adaptation Needs and Social-economic Analysis of Climate Change” and “Impact of Glacier Melting in Himalayas” have been completed and a peer review conducted. | UNEP, ONLGCC/MEP/MOST/CAS /local government |
|  | Indicator b: Adaptation strategy for glacier melting (2008-2010) Baseline: no adaptation strategy | Peer review conducted | - The final draft of the report “Impact Assessment of Glacier Melting in Himalaya Regions on Social-Economic Development of Northwest Region and Adaptation Strategy” has been completed and a peer review conducted - The two provincial impact assessments of glacier melting on social-economic development and adaptation strategies in Xinjiang and Gansu should be completed in Q2 2010. | UNEP/ONLGCC/MEP /MOST/CAS /local government |
|  | Indicator d: Situation analysis report of sea-level rising in the selected coastal areas (2008) Baseline: no situation analysis report | Peer review conducted Training materials completed | - Two reports: “The Impact of Rising Sea Level on Yangtze River Delta” and “Social-economic Analysis of Impact of Rising Sea Level in Yangtze River Delta” have been completed and a peer review conducted. - Training materials have been completed. | UNEP/ONLGCC/MEP/ SOA/MOST/ Local government |
|  | Indicator d: Adaptation strategy for sea level rising (2009-2010) Baseline: no adaptation strategy | Peer review conducted | - The final draft of “Impact Assessment of Rising Sea Level on Social-Economic Development of Coastal Region and Adaptation Strategy” has been completed and a peer review conducted. - The two provincial impact assessments of rising sea-level on social-economic development and adaptation strategies in Zhejiang and Guangdong Province should be completed in Q2 2010. | UNEP//ONLGCC /MEP/ SOA/MOST/ Local government |
|  | Indicator e: - Outreach materials - no. of individuals received information (2009-2010) Baseline: limited publications and no. of individuals aware of the issues | Training materials completed | - Training materials have been completed. - 40 officials were trained on the impacts of rising sea level and climate change adaptation. . | UNEP/ONLGCC/MEP/ MOST/CAS/SOA/Local government |
|  | Indicator f: - Number of feasibility studies, comparative studies and needs assessments conducted; - Geographical areas covered; - Number of policy recommendations given Baseline: - 0 | All work completed | - One comprehensive research report was completed incorporating four separate reports: a macro economic analysis and projection of employment impacts up to 2020 and three sectoral analysis reports on impacts in energy, forestry and cement industries. In addition, the employment impacts of China’s green stimulus measures in response to the financial and economic crises were analysed. | ILO MHRSS CASS |
| 3.2 Policies and capacities developed to manage environmental health issues from climate change | Indicator a: Institutional capacity for management of climate change risks to health at national and provincial levels Baseline: -no comprehensive knowledge base (KB) -no toolkit or capacity building model adapted to China's need -need for developing a national EH management systems in NEHAP | Four provincial training workshops held | - Training packages for development of Local Environmental Health Action Plans (LEHAPs) completed. - Four workshops held for 209 participants to improve knowledge on LEHAP development. Necessary strategic planning tools and climate change adaptation and mitigation strategies for environment and health. | WHO MOH |
|  | Indicator b: Local action plans to protect human health from climate change risks Baseline: -no local EH action plan | Four provincial training workshops held | - As above | WHO MOH |
|  | Indicator c: Capacity for climate risk assessment and specific policy recommendations Baseline: -Strategic analysis of environmental risks to health in China is out of date -Limited skills, access to tools and knowledge on EH impact assessment, risk assessment or cost benefit analysis | Training materials completed | - Course materials for training programs on promoting technical capacity in health risk assessment completed. | WHO MOH |
|  | Indicator d: Health related climate impact monitoring capacity Baseline: -assessment of current EH monitoring system in China is out of date -limited skills, access to tools and knowledge on EH monitoring | Continued work on assessment of monitoring system | - Assessment of the environmental health monitoring and information system is on-going. | WHO MOH |
|  | Indicator e: No. of pilot EH monitoring systems established and made functional, and lessons shared Baseline: no EH monitoring system | N/a | - N/a. | WHO MOH |
| 3.3 Capacities enhanced and policies developed for understanding and adapting to impacts of water resources changes on China’s environment and development | Indicator a: Policy recommendations and development of key indicators on the 11 identified challenges; Baseline: Fragmented, sector based policy papers | Basin policies reviewed and analysis conducted. Stakeholder consultation held Results shared in the Yellow River Water Resources Bulletin | - Basin-scaled policies on integrated water resources management and allocation, prevention of sedimentation etc have been reviewed jointly by experts from the project technical taskforce and analysis conducted to explore strategic point of intervention. - A small scale stakeholder consultation held, a plenary stakeholder consultation is scheduled Q3 2010. - Project research outputs, including and recommendations from the scenario development and modelling calibration have been submitted for inclusion in the Yellow River Water Resources Bulletin | UNESCO MWR, Yellow River Conservancy Commission, ONLGCC, and NDRC |
|  | Indicator b: Strategies and methodology to monitor groundwater quality developed Baseline: National standard on groundwater quality index. Regional strategies and methodologies, No existing national strategies & methodologies | Methodology of groundwater analysis established based on the historical data. | - Data on groundwater has been collected and an analysis methodology established. The characteristics of climate change drivers and the impacts of climate change and human activities on groundwater level were analyzed based on the historical data and three papers published based on the results. | UNICEF, MWR, GCM, local water and Geological sectors |
|  | Indicator c: Improved strategies and methodology to monitoring groundwater level Baseline: weak existing national strategies & methodologies | Technical Standards for Groundwater Monitoring recommended for national wide adoption. | - The second round meeting for revision of the Technical Standards for Groundwater Monitoring has been finished and recommended for national-wide adoption. | UNICEF, MWR, GCM, local water and Geological sectors |
|  | Indicator d: An integrated groundwater system in high alter areas Baseline: weak integrated system on water quality and level in part of the areas | Analysis of groundwater quality and level for three pilot areas completed. | - Analysis of basic data for groundwater quality and level has been finished for three pilot areas. | UNICEF, MWR, GCM, local water and Geological sectors |
|  | Indicator e: Partnerships at national level Baseline: Weak cooperation among sectors | Continued strengthening of strategic partnerships. | - Partnerships have been established and groundwater management experience exchanged. | MWR, IWHR, CGM MOA, MOH, MEP, CDS |
|  | Indicator f: Model of management and control of groundwater level Baseline: No such model | Validation and calibration of model in three pilot areas completed. | - Conceptual Hydrogeologic Model and Mathematical Model of Groundwater have been built. | MWR, CGS, local water and Geological sectors |
|  | Indicator g: Long-term sustainable capacity after the end of the programme Baseline: No enough specific training on groundwater and climate change | Capacity continuously enhanced through the technical support and application training for groundwater modelling. | - Training has been provided to a total of 256 local technicians and professionals from 7 River Basin Committees as well as 31 Provinces. | MWR, CGS, local water and Geological sectors |
| 3.4 Enhanced strategies for climate-proofed and environmentally sound agricultural production: Agricultural development in selected agro-ecosystems of the Yellow River Basin | Indicator a: National and provincial MDTs working with stakeholders (1st year) Baseline: MDTs not available currently | National and provincial MDTs established | - National and provincial MDTs established and dialogue has been ongoing with stakeholders. | FAO MOA, CAAS, YRB authorities |
|  | Indicator b: A multi-sector information system for eastern provinces of the YRB facilitating the analysis and exchange of information (1st year) Baseline: No such information and knowledge system | Multi-sector information system established and open for public’s access | - The Information System (IS) has been established but has not been made public under the domain: www.cpesap.net. Contents are still being uploaded and edited | FAO MOA, CAAS, YRB authorities |
|  | Indicator c: Guidelines to involve communities and farmers associations in planning for C-PESAP (2nd year) Baseline: No guidelines available | Guidelines to involve communities and farmers associations in planning for C-PESAP prepared | - Inputs on how to involve communities and farmers in planning for C-PESAP are being discussed for compilation from lessons learned and experiences of the farmers training and demonstration activities at pilot sites ongoing until fall 2010. | FAO MOA, CAAS, YRB authorities |
|  | Indicator e: Technical advice to local authorities to implement C-PESAP by trained MDTs (2nd year) Baseline: Lack of C-PESAP advice | Technical advice to local authorities to implement C-PESAP by trained MDTs provided | - Technical advices provided by provincial MDTs to local authorities on how to implement C-PESAP during training and demonstration implementations | FAO MOA, CAAS, YRB authorities |
|  | Indicator f: Menu of C-PESAP practices and options for implementation at local level available (2nd year) Baseline: Practices dispersed or not documented | C-PESAP practices compiled and documented | - A menu of C-PESAP practices at the provincial level has been developed and is being fed into IS for reference and selection for implementation | FAO MOA, CAAS, YRB authorities |
|  | Indicator g: No. of trained field technicians, farmers and farmer associations in C-PESAP (2nd year) Baseline: 0 | At the end of 2nd year, 240 field technicians and 1,200 farmers trained in C-PESAP | - A total of 240 field technicians and 1,300 farmers from 4 provinces were trained in C-PESAP. | FAO MOA, CAAS, YRB authorities |
|  | Indicator h: Pilot testing of suitable C-PESAP practices (2-3rd year) Baseline: No such plan previously | Ongoing demonstration activities that began Q4 2009, to continue until Q4 2010 | - Ongoing – pilot testing of suitable C-PESAP practices already commenced in some of the pilot sites during the period October 2009 -Spring 2010, and will continue until autumn 2010. | FAO MOA, CAAS, YRB authorities |
|  | Indicator i: Four to five provincial adaptation action plans for C_PESAP (3rd year) Baseline: No provincial action plan | Planning of formulation of the four provincial adaptation action plans for C-PESAP | - Began discussion and making plans to conduct action-planning workshop in the provinces with provincial teams | FAO MOA, CAAS, YRB authorities |

- Joint Programme Results Framework with financial information

Definitions on financial categories

- Total amount planned for the JP: Complete allocated budget for the entire duration of the JP.

- Estimated total amount committed: This category includes all amount committed and disbursed to date.

- Estimated total amount disbursed: this category includes only funds disbursed, that have been spent to date.

- Estimated % delivery rate: Funds disbursed over funds transferred to date.

(See Results Framework with financial information in next page)

| Annual Targets | Activity | Year | UN Agency | Responsible Party | Estimated Implementation Progress (“Total planned budgets” below reflect these latest changes to total allocations approved at NSC meeting in May2010.) |
| --- | --- | --- | --- | --- | --- |
|  |  | Y1 | Y2 | Y3 |  |  | Total amount planned | Total amount committed | Total Amount Disbursed | Estimated % Delivery rate of budget |
| Six studies on key issues in international negotiations have been carried out and presented or circulated at UNFCCC meetings; A series of workshops and roundtables have been held. | 1.1.1 |  |  | X | UNDP | NDRC | 430,612 | 220,000 | 261,061 | 61% |
| Capacity building activities for different stake holders and promotion of south-south cooperation have been implemented; Training sessions have been carried out; Workshops have been held. | 1.1.2 |  |  | X | UNDP | NDRC | 508,995 | 299,210 | 299,210 | 59% |
| Meetings have been held with relevant parties on the medium term progress report and listen to advice; To revise and improve the medium-term report by field trip; Draft of project report has been submitted and discussions held; Meeting has been held to review the Task Force policy report. | 1.1.3 |  |  | X | UNDP | CCICED | 375,049 | 375,049 | 344,596 | 92% |
| Series of roundtables, workshops to collect comments on draft energy law; Draft energy strategy be finished and comments collected through workshops. | 1.1.4 |  |  | X | UNDP | NDRC | 586,386 | 586,386 | 576,948 | 98% |
| UN-Business Compact launched and promoted; Compact support materials produced and published; Findings on best practice on green employment from ILO Activity 1.2.3 have been shared with UNDP, UNIDO and Guangcai to strengthen outputs under Activities 1.2.1-2. | 1.2.1 |  |  | X | UNDP | CICETE/ Guangcai | 88,657 | 75,486 | 75,486 | 85% |
|  | 1.2.2 |  |  | X | UNIDO | CICETE/ Guangcai | 231,821 | 220,490 | 220,490 | 95% |
| Green Business Option Training has been piloted in 20 universities; Findings on green employment best practice have been shared with UNDP, UNIDO and Guangcai and disseminated in as part of UN-Business Compact on Climate Change and used to strengthen outputs under Activities 1.2.1 – 2. | 1.2.3 |  |  | X | ILO | MOHRSS | 120,000 | 75,000 | 27,750 | 23% |
| Partnership and financing for one pilot clean coal power plant; Demonstration achieved through replication of Activity results; Information and best practice on cleaner coal technology has been shared with UNIDO to strengthen outputs under Activity 2.1.2. | 2.1.1 |  |  | X | UNDP | CICETE | 292,697 | 234,500 | 234,500 | 80% |
| Coal-Gangue Brick Heat Recovery Model has been released; CDM Potential Assessment for the Coal-Gangue Brick Sector has been carried out; Two Pilot Sites have been established; Supporting Policy Analysis has been completed; Paper on Promoting Heat Recovery Power Generation has been issued; Information and best practice on cleaner coal technology has been shared with UNDP to strengthen outputs under Activity 2.1.1. | 2.1.2 |  |  | X | UNIDO | MOA | 1,389,071 | 728,109 | 25,916 | 2% |
| Specific conclusions have been drawn and recommendations made for application of CDM in biogas and conservation agriculture; Findings on CDM application in the agricultural sector have been shared with FAO and UNDP to strengthen outputs under Activities 2.2.1 and 3.4.1-5. | 2.1.3 |  |  | X | UN-APCAEM | MOA | 200,000 | 200,000 | 175,279 | 88% |
| Building 1-2 biomass pellets production projects; Suggestions have been provided for incentive policies for biomass pellet technology; Findings have been shared with UNAPCAEM and FAO and used to strengthen outputs under Activities 2.1.3 and 3.4.1-5. | 2.2.1 |  |  | X | UNDP | Energy Bureau of NDRC | 368,104 | 227,939 | 227,939 | 62% |
| Best practice for climate change adaptation has been identified and demonstrated in Himalaya region; Two local and national training courses have been organized for 100 government officials and technical staff; Adaptation practice has been incorporated in governmental planning; Expertise of UNESCO and ILO have been brought in to this Activity; Findings from UNEP Activities 3.1.1 -2 have been used to strengthen outputs of WHO Activities 3.2.1-4. | 3.1.1 |  |  | X | UNEP | NDRC | 593,332 | 357,000 | 328,137 | 55% |
| Best practice for climate change adaptation has been identified and demonstrated in coastal regions; Two local and national training courses have been organized for 100 government officials and technical staff; Adaptation practice has been included in the governmental planning; Expertise of UNESCO and ILO have been brought in to this Activity; Findings from UNEP Activities 3.1.1 -2 have been used to strengthen outputs of WHO Activities 3.2.1-4; | 3.1.2 |  |  | X | UNEP | NDRC | 592,339 | 353,000 | 324,064 | 55% |
| The knowledge base on employment impacts of transition to low carbon economy is improved significantly by making this information available; Expertise of UNESCO and UNEP have been brought in to this Activity. | 3.1.3 |  |  | X | ILO | MOHRSS | 80,000 | 80,000 | 28,000 | 35% |
| Final report on comparative assessment of Environmental Health Management and practices with experiences in China has been completed; Advance skills learnt and knowledge acquired on environmental health management and best practices and experiences have been shared through the study tour to the selected provinces in china; EH managers and officers have improved skills and knowledge; Findings from UNEP Activities 3.1.1 -2 have been used to strengthen outputs of WHO Activities 3.2.1-4. | 3.2.1 |  |  | X | WHO | MOH | 322,463 | 17,000 | 17,000 | 5% |
| Draft Local Environmental Health Action Plan with a focus climate change has been developed in the 4 selected provinces. Local Environmental Health officials and managers have been trained on EH Planning, and have substantially improved capacity on EH planning (150 officials or managers trained). Findings from UNEP Activities 3.1.1 -2 have been used to strengthen outputs of WHO Activities 3.2.1-4. | 3.2.2 |  |  | X | WHO | MOH | 215,802 | 106,750 | 80,750 | 37% |
| Training workshop conducted on Environmental Health Risk Assessment with focus on Climate Change and Health in 4 Provinces (150 officials, managers and professional staff trained); Review of the local environmental health services completed for 4 provinces; Findings from UNEP Activities 3.1.1 -2 have been used to strengthen outputs of WHO Activities 3.2.1-4. | 3.2.3 |  |  | X | WHO | MOH | 573,984 | 117,750 | 70,000 | 12% |
| Assessment of the existing EH monitoring system in china and definition of EH indicators for monitoring system has been completed; Draft report available on Environmental Health Monitoring System Assessment and indicators in China by the end of December 2009; Training materials on EH monitoring and indicators developed by the end of December 2009; Findings from UNEP Activities 3.1.1 -2 have been used to strengthen outputs of WHO Activities 3.2.1-4. | 3.2.4 |  |  | X | WHO | MOH | 271,861 | 64,000 | 32,000 | 12% |
| Inception workshop held in the 1st quarter, 2009, due publicity and research expertise mobilized; Data analysis of past hydrological alterations due to climate change in the yellow river basin has been completed; GIS techniques and modelling process have been used to complete projecting of future risk scenarios due to climate change; Stakeholder meeting and consultation meeting have been held to ensure a holistic approach for the assessment; Expertise of UNEP and ILO have been brought in to this Activity. | 3.3.1 |  |  | X | UNESCO | MOWR | 927,205 | 369,000 | 340,330 | 37% |
| Field and lab testing equipments for three pilot areas has been procured; Computers for three pilot areas has been procured; Field technical support for groundwater monitoring and quality analysis has been put in place; Supplies and field work are being effectively coordinated; Findings from UNICEF Activities 3.3.2 -4 have been used to strengthen outputs of WHO Activities 3.2.1-4. | 3.3.2 |  |  | X | UNICEF | MOWR | 233,165 | 131,000 | 68,500 | 29% |
| Analysis of the impacts of climate change on groundwater has been completed; Groundwater management model has been developed and tested; The project is being effectively managed and monitored; Findings from UNICEF Activities 3.3.2 -4 have been used to strengthen outputs of WHO Activities 3.2.1-4. | 3.3.3 |  |  | X | UNICEF | MOWR | 461,370 | 228,000 | 160,000 | 35% |
| International experience exchange and training for developed countries (USGS) (8-9 persons including: 1 government official,2 experts and 6 academics/ 2 weeks) have been carried out; National training/workshop for groundwater monitoring has been held; Findings from UNICEF Activities 3.3.2 -4 have been used to strengthen outputs of WHO Activities 3.2.1-4. | 3.3.4 |  |  | X | UNICEF | MOWR | 228,204 | 142,000 | 87,000 | 38% |
| IS has been established and is functional; Suitable agricultural practices to address climate-proof and environmentally sound agricultural production (C-PESAP) have been identified and a publication has been compiled on the best practices; A training manual has been produced and at least 120 government officials, 240 field technicians and 640 farmers have received training; One national workshop for best practice collection has been conducted, and information and knowledge exchange strengthened; Capacity of county, region and provincial authorities to implement multidisciplinary and participatory approaches towards C-PESAP has been strengthened; Workshops and other events have been held to ensure greater visibility of outcomes of Activities 3.4.1-5; Findings on C-PESAP have been shared with UNAPCAEM and UNDP to strengthen outputs under Activities 2.1.3 and 2.2.1. | 3.4.1-5 |  |  | X | FAO | MOA | 1,476,384 | 964,616 | 641,928 | 43% |
| Management, coordination, monitoring and evaluation | 4.1.1 |  |  | X | UNDP | NDRC | 180,000 | 180,000 | 180,000 | 100% |
|  | 4.1.2 |  |  | X | UNDP | NDRC | 118,762 | 118,762 | 118,762 | 100% |
|  | 4.1.3 |  |  | X | UNDP | NDRC | 250,000 | 159,853 | 123,853 | 50% |
|  | 4.1.4 |  |  | X | UNDP | NDRC | 80,000 | 80,000 | 80,000 | 100% |
| Total Planned Budget without management fee* *not including USD 20,000 for programme document formulation | 11,196,262* | 6,710,900 | 5,149,499 |  |
| Management Fee for MDG-F (7%) | 783,738 | 469,763 | 360,465 |  |
| Grand-Total | 12,000,000 | 7,200,663 (60.0%) | 5,529,964 (46.1%) |  |

SECTION II: Joint Programme Progress

- assessment (250 words) of the extent to which the joint programme components are progressing

- Narrative on progress, obstacles and contingency measures

Are there difficulties in the implementation? What are the causes of these difficulties? Please check the most suitable option

b.

UN agency Coordination

Coordination with Government

Coordination within the Government (s)

√    Administrative (Procurement, etc)  /Financial (management of funds, availability, budget revision, etc)

Management: 1. Activity and output management 2. Governance/Decision making (PMC/NSC) 4. Accountability

Joint Programme design

√ External to the Joint Programme (risks and assumptions, elections, natural disaster, social unrest, etc)

Other. Please specify:

- Please, briefly describe (250 words) the current difficulties the Joint Programme is facing. Refer only to progress in relation to the planned in the Joint Program Document. Try to describe facts avoiding interpretations or personal opinions.

- Please, briefly describe (250 words) the current external difficulties (not caused by the joint programme) that delay implementation. Try to describe facts avoiding interpretations or personal opinions.

Please, briefly explain (250 words) the actions that are or will be taken to eliminate or mitigate the difficulties (internal and external referred B+C) described in the previous text boxes b and c. Try to be specific in your answer.

- Inter-Agency Coordination and Delivering as One

The MDG-F Secretariat asks the office of the Resident Coordinator complete this subsection,  briefly commenting on  the joint programme, providing its perspective from within the broader country context. The aim is to collect relevant information on how the joint programme is contributing to inter-agency work and Delivering as One.

You will find some multiple choice questions where you can select the most appropriate to the case, text boxes to provide narrative information and 2 indicators on common processes and outputs to measure interagency coordination. These indicators have been already used to measure progress on the One UN pilot countries. Please, refer to the examples in the subsection to complete the information requested.

- Is the Joint Programme still in line with the UNDAF? Please check the relevant answer

√ Yes No

- If not, does the Joint Programme fit into the national strategies?

Yes No

If not, please explain:

What types of coordination mechanisms and decisions have been taken to ensure joint delivery?

Are different joint programmes in the country coordinating among themselves? Please reflect on these questions above and add any other relevant comments and examples if you consider it necessary:

In addition to coordination mechanisms detailed in the programme document i.e PMC meetings etc., CCPF makes use of existing coordination mechanisms within UN system in China, including UN Theme Group on Climate Change and Environment’s core and expanded groups to share information across different CCPF Outputs and promote advocacy of the programme as a whole.

Coordination takes place also through output-level meetings involving just those Agencies working on substantively similar issues.

For example, coordination meetings have been held between:

- UNIDO and UNDP to develop materials, deliver trainings and raise awareness on UN Compact (Output 1.2).

- FAO and UNESCO which have led to an agreement on data sharing and the pooling of expertise and are exploring the role of GIS application in development of sustainable agriculture. UNESCO and UNICEF are also looking for synergies in the piloting groundwater pollution models in some pilot sites selected in the Yellow River Basin.

- UNIDO WHO, ILO and MOH on the development of an occupational health and safety assessment for the coal gangue brick sector (Output 2.1). The results of this work will be presented at three joint UNIDO/WHO/ILO regional workshops (the three main coal producing regions in China).

In addition, the Programme Coordinators from all China MDGF Joint Programmes in China and the RCO meet regularly to share information and experiences on management and implementation as well as cross-cutting issues.

Please provide the values for each category of the indicator table described below:

| Indicators | Baseline | Current Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| Number of managerial practices (financial, procurement, etc) implemented jointly by the UN implementing agencies for MDG-F JPs. | 0 | 8 | Quarterly M&E and annual reports, newsletters etc. Meeting agendas and minutes | Compiling of quarterly and annual reports |
| Number of joint analytical work (studies, diagnostic) undertaken jointly by UN implementing agencies for MDG-F JPs. | 0 | 5 | Joint reports | Submission of reports to PMO |
| Number of joint missions undertaken jointly by UN implementing agencies for MDG-F JPs. | 0 | 3 | Mission reports | Compiling of quarterly and annual reports |

Please provide additional information to substantiate the indicators value (150 words). Try to describe qualitative and quantitative facts avoiding interpretations or personal opinions.

Managerial procedures include PMC meetings, Output-level meetings, PMC Co-Chairs’ hotline, CCPF Newsletter and Joint Programme Coordinators’ meetings.

Regarding joint analytical work, research is led by Government counterparts and often involved numerous local academic/Government research institutes. However, in each instance, drafts were shared with other UN Agencies and inputs provided.

Joint missions were conducted under Outputs 1.2 and 2.1.

- Development Effectiveness: Paris Declaration and Accra Agenda for Action

This subsection seeks to gather relevant information on how the joint programme is fostering the principles for aid effectiveness by having appropriate ownership, alignment, harmonization and mutual accountability in the last 6 months of implementation.

You will find some multiple choice questions where you can select the most appropriate to the case, text boxes to provide narrative information and 2 indicators on ownership ad alignment. These indicators have been used extensively to measure progress on the Paris Declaration. Please, refer to the examples in the subsection to complete the information requested.

Ownership: Partner countries exercise effective leadership over their development policies, and strategies and co-ordinate development actions

Are Government and other national implementation partners involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

√  Fully involved

In what kind of decisions and activities is the government involved? Please check the relevant answer

√ Policy/decision making

√ Management: √ budget  √procurement  service provision  other, specify

Who leads and/or chair the PMC and how many times have they met?

Institution leading and/or chairing the PMC: _Chair of UNTGCCE______      Number of meetings. 3

Is civil society involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

√ Fairly involved

Fully involved

In what kind of decisions and activities is the civil society involved? Please check the relevant answer

√ Policy/decision making

Management:  budget  procurement  service provision  other, specify

Are citizens involved in the implementation of activities and the delivery of outputs?

√ Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are citizens involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Where is the joint programme management unit seated?

√ National Government  Local Government  UN Agency  By itself  other, specify

Based on your previous answers, briefly describe the current situation of the government, civil society, private sector and citizens in relation of ownership, alignment and mutual accountability of the joint programmes, please, provide some examples. Try to describe facts avoiding interpretations or personal opinions.

- Communication and Advocacy

Has the JP articulated an advocacy & communication strategy that helps advance its policy objectives and development outcomes?  Please provide a brief explanation of the objectives, key elements and target audience of this strategy, if relevant, please attach (max. 250 words).

√  Yes   No

## At the programme level, the PMC and PMO are working based on suggestions from MTE to compile all results and make them readily available online. To ensure joint advocacy of programme results, a CCPF Forum is planned at the end of the programme to present results to Government, academia, other potential donors and the broader international community.

What concrete gains are the advocacy and communication efforts outlined in the JP and/or national strategy contributing towards achieving?

X  Increased awareness on MDG related issues amongst citizens and governments

X  Increased dialogue among citizens, civil society, local national government in relation to

development policy and practice

X New/adopted policy and legislation that advance MDGs and related goals

X Establishment and/or liaison with social networks to advance MDGs and related goals

X Key moments/events of social mobilization that highlight issues

X Media outreach and advocacy

X Others (use box below)

What is the number and type of partnerships that have been established amongst different sectors of society to promote the achievement of the MDGs and related goals? Please explain.

x  Faith-based organizations     	Number 1

x  Social networks/coalitions    	Number 1

x  Local citizen groups                	Number 1

x  Private sector 		      	Number 30

x  Academic institutions              	Number 34

x  Media groups and journalist   	Number 9

Others (use box below)          	Number

What outreach activities do the programme implement to ensure that local citizens have adequate access to information on the programme and opportunities to actively participate?

√ Focus groups discussions

√ Household surveys

√ Use of local communication mediums such as radio, theatre groups, newpapers, etc

√ Open forum meetings

√ Capacity building/trainings

Others

Section III: Millennium Development Goals

- Millennium Development Goals

The MDG-F main objective is to contribute to progress to the attainment of the Millennium Development Goals worldwide. This subsection aims to capture data and information on the joint programmes contribution to 1 or more Millennium Development Goals and targets.

For this purpose the Secretariat has developed a matrix where you should link your joint programme outcomes to 1 or more Millennium Development Goals and Targets. This matrix should be interpreted from left to right. As a first step you should reflect on the contributions that each of the JP outcomes is making to one or more MDGs. Once this linked is established, it needs to be further developed by connecting each joint programme outcome to one or more MDG targets. As a third step you should estimate the number of beneficiaries the JP is reaching in each of the specifics outcomes. Finally you should select the most suitable indicators from your joint programme’s M&E framework as a measure of the Millennium targets selected. Please, refer to the example provided below.

| MDG 7 | Joint Programme Outcome 1 | MDG Target 7.A | # Beneficiaries reached | MDG Indicators | JP Indicator |
| --- | --- | --- | --- | --- | --- |
| Goal 7: Ensure environmental sustainability | Mainstreaming of climate change mitigation and adaptation into national and sub-national policies, planning, and investment frameworks | Integrate the principles of sustainable development into country policies and programmes and reverse the loss of environmental resources | 82 | N/a | 1.1a: No. of scientists and officials having capacity for the post 2012 negotiations Baseline: 50 1.1b: No. of studies carried out and disseminated on post-Kyoto strategies 1.1f: Basic Energy Law draft 1.1g: Series of energy strategies |
|  | Joint Programme Outcome 2 | MDG Target 7. A | # Beneficiaries reached | MDG Indicators | JP Target |
|  | Establishment of innovative partnerships and dissemination of technologies to mitigate climate change and increase local access to sustainable energy: | Integrate the principles of sustainable development into country policies and programmes and reverse the loss of environmental resources | 200 representatives of different enterprises (and local Government) selected from the Guangcai Programme’s network. 6 coal gangue brick enterprises | N/a | 1.2a: A UN-Business Compact on Climate Change, and series of high profile communication and awareness raising activities, including citizen engagement 2.1a: Partnership and financing for one pilot clean coal power plant 2.1c: Energy and resources efficiency model developed 2.1f: New policy set up and financial tools established |
|  | Joint Programme Outcome 3 | MDG Target 7.A | # Beneficiaries reached | MDG Indicators | JP Target |
|  | Accelerated action by China in assessing vulnerability to climate change and developing adaptation plans and mechanisms. | Integrate the principles of sustainable development into country policies and programmes and reverse the loss of environmental resources | Capacity building in the form of training workshops takes place in YIII 209 local and provincial health professionals 1,800 to date | N/a | 3.1b: Adaptation strategy for glacier melting 3.1d: Adaptation strategy for sea level rising 3.2a: Institutional capacity for management of climate change risks to health at national and provincial levels 3.4h: Four to five provincial adaptation action plans for C_PESAP |
|  | Joint Programme Outcome 3 | MDG Target 7 C | # Beneficiaries reached | MDG Indicators | JP Target |
|  | Accelerated action by China in assessing vulnerability to climate change and developing adaptation plans and mechanisms. | Halve, by 2015, the proportion of people without sustainable access to safe drinking water and basic sanitation |  | Proportion of total water resources used Proportion of population using an improved drinking water source | 3.3: Improved strategies and methodology to monitoring groundwater level |
|  | Joint Programme Outcome 3 | MDG Target 7 C | # Beneficiaries reached | MDG Indicators | JP Target |
|  | Outcome 3.4 Enhanced strategies for climate-proofed and environmentally sound agricultural production (C-PESAP): Agricultural development in selected agro-ecosystems of the Yellow River Basin. | Goal 1: Eradicate poverty and hunger | 1,800 to date | Halve, between 1990 and 2015, the proportion of people who suffer from hunger | 3.4h: Four to five provincial adaptation action plans for C_PESAP |

Additional Narrative comments

Please provide any relevant information and contributions of the programme to the MDGs, whether at national or local level.

Please provide other comments you would like to communicate to the MDG-F Secretariat:

Section 4: General Thematic Indicators

| Number of sectors or mainstreaming laws, policies or plans supported by the joint programme: Applies Does not apply, if so move to section 2 |
| --- |
| On Environmental Management | On Climate Change |
| Policies Laws Plans | No. National 2 No. National 0 No. National 0 | No. Local 1 No. Local 0 No. Local 4 | Policies Laws Plan | No. National 7 No. National 2 No. National 1 | No. Local 3 No. Local 32 No. Local 4 |

| Please briefly provide some contextual information on the law, policy or plan and the country/municipality where it is (or will be) implemented (base line, stage of development and approval, potential impact of the policy): Climate change policy: formulation of seven post-Kyoto strategies, the establishing of Beijing International Climate Change Centre (BICCC) (Output 1.1) various vulnerability assessments on climate change effects on Yellow River Basin, groundwater (Output 3.2) and agriculture (Output 3.4), the impacts of glacial melting in Himalayas, sea level rising in the coastal areas of Zhejiang and Guangdong provinces (Output 3.1) could have an impact on future climate change policy and climate change vulnerability planning. National Environmental Health Action Plan (2007-2015): (Output 3.2) The National Environmental Health Action Plan (NEHAP) was endorsed by 18 Ministries and CCPF supports its implementation. Action plans are being developed in four provinces, Guangdong, Gansu, Jiangsu and Chongqing. National Energy-saving and emissions reduction plan under the 11th five year plan, under which each local region should formulate their own energy-saving and emissions reduction plan Basic Energy Law/ energy sector: (Output 1.1) support has been given under CCPF to formulate Basic Energy Law and series of Energy Strategies, in addition, (Outputs 2.1-2.2) pilots of clean coal technology, biomass pellets, and heat recovery power generation (HRPG) for brick sector, investigative work into off-grid rural renewable power generation could have an wide reaching effects on China’s energy sector. Technical standards for groundwater monitoring (SL183-2005): (Output 3.3) the technical standards have been revised to integrate water quantity and water quality which were previously less fully addressed. Regulations have been recommended to Ministry of Water Resources for adoption in the whole country. Private sector: (Output 1.2) the UN-Business Compact on Climate Change through a series of pilots and training materials created engage multinational and local companies to increase awareness on climate change issues in China while promoting the adoption of green investment and financing mechanisms to address climate change. Rural development: (Output 1.1) the CCPF High-Level Climate Change Task Force has produced policy recommendations on China’s rural development, energy, environment and climate change adaptation which were presented at the CCICED Annual General Meeting 2009. Green employment promotion/low carbon economy: (Output 3.1) CCPF activities help build knowledge base on climate change impacts on employment and need for coherent policy responses in the fields of employment, skills development and social security to ensure just transition to low carbon economy. Such research activities inform future policies on green employment promotion and green skills development. China does not currently have specific policies on these issues, but MOHRSS has included green jobs promotion on its agenda. |
| --- |
| Sector in which the law(s), policy(ies) or plan(s) is/are focused Nature conservation Water management Sanitation Sustainable management of natural resources Climate Change: Adaptation Mitigation Other , please specify: | Comments |
| Number of citizens and/or institutions that the law(s), policy(ies) or plan(s) directly affects |
| Citizens National Public Institutions Local Public Institutions Private Sector Institutions | Total No. All (1.1.4 Energy Law and 3.3.2-4 NEHAP) Total No. 21 Total No 111 Total No. 10,020 | No. Urban All (1.1.4 Energy Law and 3.3.2-4 NEHAP) No. Urban 0 No. Urban 0 No. Urban 0 | No. Rural All (1.1.4 Energy Law and 3.3.2-4 NEHAP) No. Urban 0 No. Rural 80 No. Rurl 10,00 |

a

| Government budget allocated to environmental issues before the implementation of the Joint Programme National budget: $ USD Total Local budget (s) : $ USD (in localities of intervention of the JP) | Comments Not available at present |
| --- | --- |
| % variation in government budget allocated to environmental policies or programmes from the beginning of the joint programme to present time: National budget: % Overall % Triggered by the Joint Programme | Comments Not available at present |
| Local budget: % Overall % Triggered by the Joint Programme |  |
| Government budget allocated to Climate Change before the implementation of the Joint Programme National budget: $ USD Total Local budget (s) : $ USD (in localities of intervention of the JP) | Comments Not available at present |
| % variation in government budget allocated to Climate Change from the beginning of the Joint programme to present time: National budget: % Overall: USD 3.2 mn % Triggered by the Joint Programme | Comments As result of CCPF activities under Output 3.2 |
| Local budget: % Overall % Triggered by the Joint Programme |  |

| 2.1. Number of km2 of land newly managed by a natural resource plan supported by the Joint Programme Applies Does not apply if so move to section 2.4 |
| --- |
| Total of the area managed in Km2. |
| By habitat: tropical forest Temperate forest Savannah Shrub land Grassland | Km2 Km2 Km2 Km2 Km2 | Wetlands Rocky areas Desert Sea/oceans Artificial terrestrial (pastoral land, arable land, etc) | Km2 Km2 Km2 Km2 Km2 Km2 |
| 2.2 Number of institutions, civil servants and citizens trained by the JP to take informed decisions on environmental issues (excluding climate change): |
| Does not apply Public Institutions Private Sector Institutions NGO/CBO’s Civil servants Citizens | Total No. 62 Total No. 125 Total No. 10 Total No. 390 Total No. 380 | Women Women | Men Men |
| 2.3. Number of citizens supported by the JP that have organised themselves to effectively participate in natural resource management initiatives: Applies Does not apply |
| Total No. | No. Women | No. Men | Ethnic groups |

| 2.4. Number of successful environmental service payment mechanisms that have been promoted by the JP : Does not apply |
| --- |
| Total No. | No. Of beneficiaries: | Sectors of application: Forest protection Water resources Management Pollution | Financing source: MDGF Public Fund NGO International Organization Others: |
| 2.5. Has the JP had an impact on the development of national and local policies or regulations that recognize schemes of Payment for Ecosystem Services as an environmental management tool, How? Under Output 1.1 a study was conducted on related to Reduced Emissions from Degradation and Deforestation. However, it is too soon to tell if it will have impact on the scheme of PES. The UN Compact under Output 1.2 has helped promote adoption of green investment and financing mechanisms to address climate change by the private sector and may have indirect impact on the PES in the long run. |

| 3.1 Number of Km2 and type of habitat covered by mechanisms and/or actions to adapt to climate change (implemented with the support of the joint programme: Applies Does not apply |
| --- |
| Tropical Forest Km2 Temperate Forest Km2 Savannah Km2 Shrub land Km2 | Grassland Km2 Wetlands Km2 700 Rocky Areas Km2 Desert Km2 Artificial terrestrial (pastoral land, arable land, etc) Km2 1 |
| 3.2 Adaptation measures supported by JP that are addressing the following climate change issues: Applies Does not apply |
| Land degradation Soil fertility decrease Atmospheric pollution | Change in native species dynamics Wildfire Drought, Storms/flooding | Alteration of rain patterns, Sea levels rise Acidification |
| 3.3 Based on available data, what kind of improvements on the population’s wellbeing have been achieved through JP supported adaptation measures?: |
| Health Vulnerability (in terms of natural disasters) Improved livelihoods Others |

| 3.4 Number of individuals and institutions with improved capacities to adapt to climate change or mitigate it: Applies Does not apply |
| --- |
| Adaptation Mitigation | Public Institutions Private Sector Institutions Civil servants Citizens | Total No. 157 Total No. 112 Total No. 569 Total No. 1,500 | Women 90 Women 325 | Men 270 Men 975 |
| 3.5 Interventions funded by the JP to improve capacities of individuals and institutions to adapt to Climate Change or mitigate it: Does not apply Adaptation Mitigation Capacity building Equipment Knowledge transfer |

3.6 Number of clean development mechanism projects registered to mitigate climate change: Does not apply

CO2 Emissions captured through conservation Total Number CO2 Emission reduction through the use of Renewable Energies Total Number 1 (Activity 2.1.3 to be confirmed) CO2 Emission reduction through the use of clean technologies Total Number 6.7 mn/year

# Footnotes

Please list all the partners actually working in the joint’s programme implementation, NGOs, Universities, etc

In this case climate proofing is taken as a process that can lead to minimize, if not eliminate potential disasters and to mitigate, if not prevent, the unwanted consequences of extreme weather events or climate change. Climate proofing is not meant in this context as product.

For indicators 1.5, 1.6, 1.7 and 1.8 the Secretariat acknowledges the potential difficulties to obtain the information requested. Therefore, if not available, please provide the best available estimate. The information requested refers to the budgetary year in which the monitoring report falls

Environmental issues should refer to budget allocated to natural resource management and conservation

IUCN categories

This indicator requires the use of baseline information from which a variation can be observed.  If this data is not available the Secretariat recommends collecting it in order to complete this impact indicator for next reporting period.

# Text boxes

3. Climate change adaptation and mitigation and development of institutional capacities

1. Environmental and Climate Change policy development and mainstreaming

Progress in outcomes:

## Five new studies have been identified for presentation at COP-16 which should help contribute to China’s international negotiations on climate change and to an improved policies and partnerships for mainstreaming climate change mitigation and adaption into policy frameworks. Preparations have commenced for the High-Level Adaptation Symposium under Outcome 1. While there has been great attention paid to mitigation, this will be the first time an event showcasing adaption efforts in China has been held.

## A peer review of national and provincial assessments and strategic plans was conducted under Outcome 3. Results were presented in international and national workshops and are being considered by national government and will be considered in the national and provincial development plans.

## As of June 2010, all capacity building activities under Output 3.4 have been completed and awareness of farmers and local technicians on climate change and agricultural pollution raised. Green Business Options (GBO) developed under Outcome 1 have been incorporated as a new training module in Start and Improve Your Own Business programme (SIYB). The International Seminar on Application of CDM Facility in Agricultural Sector held in May 2010 shared experience and ideas on promoting the CDM application to reduce GHG emissions and support sustainable development of agriculture.

Progress in Outputs:

## To date, three pilot enterprises have been trained on how to develop climate change CSR operational policies and meet reporting requirements. Pilot enterprises have already applied or are in the process of applying to join UN Compact (Output 1.2). Groundwork has been laid for survey of off-grid rural renewable energy stations and related analysis to commence in Q3 2010 (Output 2.2) and construction of the first heat recovery power generation coal gangue brick pilot completed (Output 2.1) with a second pilot enterprise already selected. The system is now being prepared for testing. Work has started on the joint occupational assessment by WHO and ILO in coordination with UNIDO for the coal gangue brick sector.

## Four workshops were held for 209 participants to improve knowledge on LEHAP development, necessary strategic planning tools and climate change adaptation and mitigation strategies for environment and health (Output 3.2). Yellow River Basin-related policies were reviewed, an analysis conducted and relevancy verified through a stakeholder meeting. Research outputs to date, including and recommendations from the scenario development and modelling calibration have been submitted for inclusion in the Yellow River Water Resources Bulletin (Output 3.3).

## Data on groundwater has been collected and an analysis methodology established. The characteristics of climate change drivers and the impacts of climate change and human activities on groundwater level were analyzed based on the historical data and three papers drafted based sharingresults. The paper “Analysis on Characteristics of Groundwater Level Changes in Yundong Plain from 1976” has been published and the two papers on groundwater research have already accepted by journals (Output 3.3).

## Measures taken for the sustainability of the joint programme

- All activities are implemented through Government: China has actively replicated pilots that have proven to be successful

- The programme places a strong emphasis on capacity building: beneficiaries include national and local government, government officials from SIDS and other developing countries, health professionals, farmers and farmers associations, university students, academia, etc.

- Policy-level interventions are made wherever possible: activities under Output 1.1 contribute to China’s strategies and positioning post-Kyoto and to China’s draft energy law, while Local Environment and Health Action Plans are developed under Output 3.2 based on NEHAP and work under Output 3.3 has resulted in revisions to technical groundwater monitoring  standards.  Policy recommendations will also be developed for coal gangue brick sector, Yellow River Basin and climate change adaptation.

Additionally, it should be noted that many of CCPF interventions are part of UN agencies’ country programmes and as opposed to stand alone or “one-off” activities, are linked to agencies’ core work and mandate thus ensuring sustainability of results.

The Government is fully involved as key implementers of all CCPF activities. Almost ill activities involve strong coordination with academia and mitigation activities, in particular, demand active participation of and consultation with the private sector. To date, stakeholder meetings and household/field surveys have been used to consult a broader range of stakeholders affected by programme interventions mostly under Outcomes 2 and 3.

2. Institutional capacities for environmental management developed and civil society participation increased

2. Institutional capacities for environmental management developed and civil society participation increased

- Environmental and Climate Change policy development and mainstreaming

Under (b), the CCPF PMO actively supports and assists both participating UN agencies and Government counterparts with reporting and budgetary issues. Additionally, UNTGCCE meetings are used to update UN agencies on latest reporting requirements, etc.

As for (c), second pilot enterprise has now been selected.

The main recurrent problem has been the global economic slowdown which has had a negative effect on the Chinese construction materials sector which resulted in the second of two pilot enterprise under Output 1.2 pulling out. A second pilot enterprise has since been selected and results of the engineering feasibility study are now pending.

Administrative/Financial: The differing administrative procedures of UN Agencies occasionally impede joint implementation. Partners usually need to sign a contract with each Agency, each with different budgeting and reporting requirements. In addition, different budgeting systems and requirements of UN Agencies and the MDG Achievement Fund overburden UN staff in budget reporting exercises.