CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

As of 31 December 2008

| Participating UN or Non-UN Organization: | World Food Programme |  | UNCAPAHI Objective(s) covered: |  | Objective 7 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): | NA |  |  |  |  |  |
| Programme Number: | CFIA- A12 |  |  |  |  |  |
| Programme Title: | Supporting the Humanitarian Common Services through provision of data management and mapping tools |  |  |  |  |  |
| Total Approved Programme Budget: | US$ 279,484 |  |  |  |  |  |
| Location: | AHI pandemic humanitarian response operations with focus and roll-out in candidate countries and logistic corridors |  |  |  |  |  |
| MC Approval Date: | 20 February 2008 |  |  |  |  |  |
| Programme Duration: | 12 Months | Starting Date: | 04/03/2008 | Completion Date: |  | 28/02/2009 |
| Funds Committed: | US$ 251, 460 |  |  | Percentage of Approved: |  | 90% |
| Funds Disbursed: | US$ 18,284 |  |  | Percentage of Approved: |  | 6% |
| Expected Programme Duration: | 12 Months | Forecast Final Date: | 28/02/2009 | Delay (Months): |  | None |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| An online user-friendly mapping and information dynamic mapping tool for provision of Humanitarian Common Services in a pandemic environment is created. | The initial demonstration model of the planned interactive software has been created. The tool links close-to-real-time WFP data on food and non-food assets to a forecasting programme designed to generate on-demand pandemic outbreak scenarios. Data on logistics corridors and supply chain related information is being processed. The preliminary tool was presented to major UN stakeholders for additional technical and data input. | 70% |
| Qualitative achievements against outcomes and results: |  |  |
| Currently, full time technical experts are committed to the continued development of the aforementioned mapping tool. This technical tool can assist the relevant stakeholders in simulating the outbreak and spread of a pandemic. WFP is working closely with WHO and PIC to ensure the tool can be utilized in an effective manner. There is significant potential for countries teams and agencies to use this mapping tool to support simulation exercises, in the readiness phase. Incorporated data sets are designed to interface with other sources of data. With additional time and resources, this tool may be further enhanced to permit additional application in the pandemic response and recovery phases, utilizing real time data. |  |  |