CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

30 September 2008

| Participating UN or Non-UN Organization: | World Food Programme |  | UNCAPAHI Objective(s) covered: |  | Objective 7 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): | N/A |  |  |  |  |  |
| Programme Number: | CFIA- A12 |  |  |  |  |  |
| Programme Title: | Supporting the Humanitarian Common Services through provision of data management and mapping tools |  |  |  |  |  |
| Total Approved Programme Budget: | US$ 279,484 |  |  |  |  |  |
| Location: | AHI pandemic humanitarian response operations with focus and roll-out in candidate countries and logistic corridors |  |  |  |  |  |
| MC Approval Date: | 20 February 2008 |  |  |  |  |  |
| Programme Duration: | 12 Months | Starting Date: | 04/03/2008 | Completion Date: |  | 28/02/2009 |
| Funds Committed: | US$ 140, 714 |  |  | Percentage of Approved: |  | 50% |
| Funds Disbursed: | US$ 18,284 |  |  | Percentage of Approved: |  | 6% |
| Expected Programme Duration: | 12 Months | Forecast Final Date: | 28/02/2009 | Delay (Months): |  | None |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| An online user-friendly mapping and information dynamic mapping tool for provision of Humanitarian Common Services in a pandemic environment is created. | Technical staff identified and tasked with implementation of the project based on agreed upon detailed technical criteria and methodology. | 50% |
| Qualitative achievements against outcomes and results: |  |  |
| In line with the outcome as outlined above, the implementation of the project is ongoing to produce a mapping tool featuring logistical corridors and key infrastructure. As outlined in the project proposal, the tool is being developed following technical specifications that will allow visualizing food assistance needs and assumptions specific to the requirements of humanitarian operations in a pandemic environment. |  |  |