CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

as of 31 March  2009

| Participating UN or Non-UN Organization: | World Food Programme | UNCAPAHI Objective(s) covered: | Objective: Humanitarian Common Services Support |
| --- | --- | --- | --- |
| Implementing Partner(s): | N/A |
| Programme Number: | CFIA-A1 |
| Programme Title: | Development of a Logistics Concept of Operations for Humanitarian Activities in a Pandemic Environment |
| Total Approved Programme Budget: | US$ 400,000 |
| Location: | Africa; Kenya & Mombassa Corridor, Southern Africa Corridor Asia: Pakistan and Afghanistan Indonesia and South East Asia Cluster |
| MC Approval Date: | 12 July 2008 |
| Programme Duration: | Initial 12 Months | Starting Date: | 14 July 2007 | Completion Date: | 26 July 2008 |
| Funds Committed: | US$ 400,000 | Percentage of Approved: | 100% |
| Funds Disbursed: | US$ 219,566 | Percentage of Approved: | 54% |
| Expected Programme Duration: | 21 Months | Forecast Final Date: | 31 March 2009 | Delay (Months): | 9 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Continuity under Pandemic Conditions Ensuring the community of essential social, Economic and governance services, and effective implementation of humanitarian relief under pandemic conditions. | The Pandemic Logistics Corridor Capacity Assessment (PLCCA) of the eastern and southern African logistics corridor has been completed. The PLCCA of the North-South [Economic] Corridor in south east Asia has been completed. Joint stakeholder hazard and risk analysis for the eastern and southern African and North- South Economic Logistics corridor have been undertaken. | 100% |
| Support provided to the preparation of a response plan in Southern Africa and South East Asia | Awareness raising efforts, which have resulted in the increased involvement of Government and other key stakeholders are on going. | 100% |
| Qualitative achievements against outcomes and results: |
| WFP has completed the Pandemic Logistics Corridor Capacity Assessment ( PLCCA) of the eastern and southern African and south east Asia logistics corridors. The assessments provide an analysis of transport modes and the capacity of the logistic networks, including a pandemic impact analysis on the logistic networks. The project has resulted in intensified collaboration of a network of stakeholders, which includes UN agencies, NGOs, IFRC, both the national and local authorities as well as critical partners from the commercial sector in the area of pandemic preparedness. Outcomes of the assessments have also been incorporated into a new hazard and risk analysis workshop to sensitise stakeholders to the operational and administrative issues that they may face under pandemic conditions. Following the completion of the PLCCAs, together with national planning maturing, it is envisioned that a more detailed supply chain analysis will be undertaken during the course of the next year. The draft WFP Logistics Concept of Operations (CONOPS) has been prepared using the PLCCAs. Activities funded and possible within this project have been completed as of 31 March 2009. Documents are posted on the Logistics Cluster website (http://www.logcluster.org/pru/pandemic-logistics-corridor-capacity-assessments-1/plcca). |