**Ethiopia**

|  |  |
| --- | --- |
| **Programme Title:** | Enabling pastoral communities to adapt to climate change and restoring rangeland environments |
| **Programme number & MDTF ref:** | MDGF-1679-E-ETH Enabling Commu (67150) |
| **Window:** | Environment & Climate Change |
| **Approved Budget by NSC (US$):** | 4 million |
| **Participating Organizations:** | FAO, UNDP, UNEP |
| **First Tranche transferred on:** | 21-Oct-2009 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Training in several areas such as climate change adaptation, planning, monitoring and evaluation, conflict prevention and management of pastoral areas has been provided. Project technical equipment procured. Detailed monthly action plans for regions completed. Advocacy and communication strategy prepared. Regional & District/Wereda/Project Officers recruited. Afar Region CC Adaptation program developed. CC related risks/vulnerability of pastoral communities identified and assessment report produced. Draft CC mainstreaming guideline prepared |
|  |
| **Problems and lessons learned:** |
| Managerial (delayed funds transfer to the field). JP design issues. |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS& FIGURES[[1]](#footnote-2)

As of 31 December 2010



1. These figures are provided by the Participating Organizations’ headquarters and may differ from information in the field. [↑](#footnote-ref-2)