# United Nations Development Group Iraq Trust Fund

# Project #:A5-23

# Date and Quarter Updated: (April –June -2011)2nd Quarter)

| Participating UN Organisation: Agriculture Organization of UN (FAO) | Sector: Agriculture, Food Security, Environment and Natural Resources Management |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Agriculture (MoA), Iraq |

| Title | Towards Sustainable Development of Inland Fisheries in Iraq |
| --- | --- |
| Geo. Location | Salah Al Deen , Al- Anbar ,Ninewa and Diyala governorates |
| Project Cost | US$ 3,000,007 |
| Duration | 30Months |
| Approval Date | 17/03/2008 | Starting Date | 26/03/2008 | Completion Date | Original: 26/9/2009 Extension30/06/2011 |
| Project Description | The project aims to build institutional capacity and the local capacity based on community participation in order to enable remote rural communities, and relevant state agencies to undertake a jointly sustainable development programme in inland fisheries development. This will include: (i) decentralization and delivery system of quality fish seed supply for stock enhancement to increase inland fish production, (ii) enhancement of aquatic food production through community participatory conservation and management of inland water resources, and (iii) community participatory resource assessment and action planning. The project will also focus on an extension delivery system in dissemination of knowledge on innovative approaches of management, education and training. |

Development Goal and Immediate Objectives

The long-term development goal of the project is to contribute towards the sustainable development of inland fisheries, in order to meet the domestic demand of fish and to enhance livelihood and employment opportunities and food security among rural and disadvantaged communities of central to northern parts of Iraq The immediate objectives of this project are as follows: To build capacity of General Board of Fish Resources and Development (GBFRD) of Ministry of Agriculture (MoA) to establish a fish seed supply network to reach remote and potential areas to support a sustainable inland fishery industry. To diversify inland fisheries practices that will contribute to national fish production and enhance employment/livelihoods of communities and to empower rural and marginalised communities by involving them in the planning, extension and development of sustainable inland fisheries. To strengthen an extension services system reaching remote rural communities.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | The key outputs of the project are as follows: Broodstock development programme for native carp species established and fish seed supply operational. Disease diagnostic and fish feed formulation and testing capacities of GBFRD personnel enhanced. Fish stock enhancement/restocking programme established. Community participatory methodologies for conservation and management of inland fisheries established. Extension capacity of GBFRD on inland fisheries management enhanced |
| Activities | The development of inland fisheries and thereby the offer of opportunities for communities associated with these water bodies to diversify their livelihoods and income generation avenues. Adoption of community participatory management strategies for the sustainability of fisheries and aquaculture practices. Capacity building through access to innovative inland fishery practices and technologies and information for dissemination. |
| Procurement | In order to enhance the institutional capacity, brood fish, chemicals, different equipment for disease diagnosis, genetic screening, and fish nutrition laboratories have to be procured under the project. |

| Funds Committed | 2,882,039 | % of approved | 96.1% |
| --- | --- | --- | --- |
| Funds Disbursed | 1,825,021 | % of approved | 60.8% |
| Forecast final date | 30/06/2011 | Delay (months) | 7 |
| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| Men* | 2,500 | 80 % |
| Women |  |  |
| Children |  |  |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries | 150 | 70% |
| Employment generation (men/women) | 40 | 10 % (not originally planned for) |

* In Iraq fisheries activities are done predominately by men. This programme targets the fishermen but indirectly benefits women and children, etc. Most of the beneficiary figures will only come after the completion of the construction of the brood fish centres due the project model.

| Quantitative achievements against objectives and results | % of planned |
| --- | --- |
| Procurement of GIS facilities | Completed | 100 |
| Purchase and installation of equipments to strengthen disease diagnosis, fish nutrition and brood stock genetic | Completed | 100 |
| Review of Iraqi fisheries legislation | Completed | 100 |
| Construction of One brood fish centres cum hatcheries buildings located at Salah Al-Deen governorates to maintain broodstock and produce larvae/fry of native Barbus | The contract for the building construction at Salah Al Deen site is signed. The civil work of the Salah Al-Din site started on 01/11/2010 and is still under process according to the contract . Delay of the work more than one month because of the security situations and bad weather in the governorate throw this period. | 85 |
| Purchase and installation of equipment for fish feed manufactory | Re-tendering was completed and the contract was sign by supplier, the Delivery of equipments under progress. | 80 |
| Preparation and Extension material | The manuals for fish breeding manuals are completed. | 100 |
| Workshop in Amman for Capacity building | Workshop for Decease and quality of fish seed, fish feed & production of life food was completed during 22-27 Nov. 2010. | 100 |
| Second Work shop in Amman | The work shop for fish breeding and genetic quality improvement and maintenance and Operation & troubleshooting of the Chinese Style Hatchery in June -2011 in Amman.Is completed. | 100 |
| Qualitative achievements against objectives and results |
| Completed activities as outlined in the project document have been listed below: Purchase of disease diagnosis equipment, fish nutrition and brood stock genetic completed. Workshop conducted and final Policy framework and the fisheries legislation approved by the Project Steering Committee (completed). The second workshop completed. The Delivery of equipments of feed manufactory under progress. Most of the project activities have been completed, however the construction of the brood fish centres (Salah Al- deen) remains balance activity. There were some delays due to bad weather and bad security situation. It is hoped the project will be completed by next two months. This is a major output for this project that will need to be finished within the next two months. |
| Main implémentations constraints & challenges (2-3 sentences) |
| The problem regarding the construction of brood fish centres delay has come up while doing the tenders for construction and due to the complex nature of construction needed, no company was willing to do it in less than 7 months, therefore the completion is due for August 2011. All project activities are being expedited to make sure it is completed on time. |