Peace building fund

Final PROGRAMME  Narrative report

| Programme Title & Number |  | Country, Locality(s), Thematic Area(s) |
| --- | --- | --- |
| - Programme Title: Support to the Implementation of the Sierra Leone Reparations Programme as Part of the Recommendations of the Truth and Reconciliation Commission - Programme Number: PBF/SLE/A-4 - MDTF Office Atlas Number: |  | Sierra Leone, Democracy and Good Governance |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| International Organization for Migration |  | National Commission for Social Action (NaCSA) |

| Programme/Project Cost (US$) |  |  | Programme Duration (months) |  |
| --- | --- | --- | --- | --- |
| MDTF Fund Contribution: - by Agency (if applicable) | 3,000,000 |  | Overall Duration | 15 months |
| Agency Contribution - by Agency (if applicable) | - |  | Start Date | October 2008 |
|  | - |  | Original end date | September 2009 |
| Government Contribution (if applicable) | 246,000 |  | Revised End Date, (if applicable) | December 2009 |
| Other Contribution (donor) (if applicable) |  |  | Operational Closure Date | February 2010 |
| TOTAL: | 3,246,000 |  | Expected Financial Closure Date | April 2011 |

| Final Programme/ Project Evaluation |  | Submitted By |
| --- | --- | --- |
| Evaluation Completed Yes No Date: __________________ Evaluation Report - Attached Yes No |  | - Name: - Title: - Participating Organization (Lead): - Contact information: |

# FINAL PROGRAMME REPORT

- PURPOSE

The signing of the Lomé Peace Agreement in 1999 in principle heralded the end of the 10 year conflict in Sierra Leone. In a bid to translate the Peace Agreement into law and make peace more permanent, the Sierra Leone Parliament in 1999 ratified the Peace Agreement (The Lomé Peace Agreement Act No, Act 3 1999). Lome Peace Agreement - Article VI paragraph 2 (ix) provided for the establishment of the Truth and Reconciliation Commission (TRC) to address the causes and victims of the war. The TRC Act (Act No 4, 2000) passed by Parliament in 2000, expressly mandated the Commission to inter alia respond to the needs of the victims. Consequent upon this mandate, the TRC report recommended the establishment of a Reparations Program to be implemented by NaCSA. This project to a very large extent, kick-start the process of addressing the needs of the victims irrespective of the type of harm they suffered and meet the obligations of the Government, as specified in the Lomé Peace Accord and recommended in TRC Report

The main outputs of this project are:

- A special Unit for Reparations is established at NaCSA

- Staff and technical consultant recruited

- The reparations unit provided with logistics capacity to implement the programme

- Capacity of staff build on how to manage reparations

- Five year strategic plan developed

- Data base on the profile of war victims established

- Government, civil society and donors sensitized for continued support to the reparations programme

- War victims trust Fund established

- Reparation benefit delivery sub project were implemented.

The main outcomes are:

- Contributed to an enhanced capacity of the Reparations Unit to implement the Sierra Leone Reparations Programme

- Contributed to enhanced recognition and improved human dignity for victims of the civil conflict

This project is linked to the strategic planning framework for the consolidation of peace in Sierra leone. The signing of the Lomé Peace Agreement in 1999 in principle heralded the end of the 10 year conflict in Sierra Leone. In a bid to translate the Peace Agreement into law and make peace more permanent, the Sierra Leone Parliament in 1999 ratified the Peace Agreement (The Lomé Peace Agreement Act No, Act 3 1999). The TRC Act (Act No 4, 2000) passed by Parliament in 2000, expressly mandated the Commission to inter alia respond to the needs of the victims. Consequent upon this mandate, the TRC report recommended the establishment of a Reparations Program to be implemented by NaCSA.

In furtherance to this recommendation, the Government of Sierra Leone officially designated NaCSA as the Government’s lead agency to implement the said program and approved of the setting up of a

Reparation Taskforce comprising NaCSA (as Chair), UNIOSIL, Representatives from Civil Society,

Victims, the TRC and the Office of the Vice President to advice on the establishment of a Special Fund for War Victims and the implementation of a Reparations Program in the country.

The war witnessed massive suffering and devastation on the lives of many. In the execution of its

mandate, the TRC identified five categories of persons as victims of the conflict with respect to

Reparations to wit; amputees, war wounded, war widows, victims of sexual abuse and children.

The Reparations Taskforce with technical assistance from consultants (REDRESS, a London based

NGO with long experience in managing reparations and IOM from Geneva) has developed plans and

strategies to implement the Reparations Program including the setting up of the Reparations Unit,

establishing and operationalzing of the Special Fund for War Victims, identifying and development of a database on beneficiaries and identifying the policy and legal framework required to enhance the

effective implementation of the reparations for war victims. The final report prepared by the Task Force has been approved by Government and made public to major stakeholders. The implementation of this project has, to a very large extent, kick-start the process of addressing the needs of the victims irrespective of the type of harm they suffered and meet the obligations of the Government, as specified in the Lomé Peace Accord and recommended in TRC Report.

The main implementing partner for this project is the National Commission for Social Action (NaCSA) and the main beneficiaries are over 32,000 registered war victims. Key stakeholders include victims groups, the international community, civil society, the government and families of the war victims.

- ASSESSMENT OF PROGRAMME/ PROJECT RESULTS

The project objective of contributing to increased justice, security and peace building and all

project outcomes and outputs were all fully achieved during implementation of the project. In

2009, through this project, the Reparations Programme was successfully kick-started. A

reparations unit was set up in NaCSA and its capacity in implementing; coordinating and

mobilizing support for the programme was built through training and experience. NaCSA was

capacitated with skills, logistics, structures, policies and a framework that enabled it to provide

social services to the five categories of victims. Thousands of victims received initial installment

of micro-grants, education support, medical examination and treatment and psycho-social

support in an effort to respond to their needs, to restore their dignity and to create relief.

The successful completion of this project, especially with the delivery of initial concrete benefits

to war victims as a way of acknowledging abuse suffered during the war, has started to cement

the peace process that was started after the end of the decade long conflict in Sierra Leone. The

reparations activities such as symbolic reparations and psychosocial counseling sessions gave

people the opportunity to express their feelings concerning the loss of loved ones and helped

restore dignity. The activities, which were well attended, promoted tolerance for victims and

their families, helped communities find common ground, created social cohesion and thus paved

the way for peaceful coexistence. Other forms of reparations like micro-grants, education support

and medical assistance helped in concretely acknowledging and addressing human right abuses

suffered by victims during the war.

All the project outputs were fully achieved. The number of war victims was higher than the

estimated caseload of 16,000 as anticipated by the project proposal.

The intensive and successful outreach that was organised by the reparations programme ensured

that more victims, especially those who suffered sexual violence, came out to register than

expected. There are some more war victims that remained unregistered, and NaCSA is reviewing

the cases on an individual basis when they come for registration.

Gains made as a result of the fall in the value of the Leone against the dollar allowed the

reparation programme to pay the first installment of micro grant and educational support as well

as the delivery of other forms of assistance to more victims than originally planned for this

project.

Payments were outsourced and conducted by the Sierra Leone Commercial Bank for security and

credibility reasons.

Instead of recruiting two international technical consultants, one national technical consultant

was hired to design the war victims’ database. This was due to financial reasons, and the

availability of such a consultant in the country. However the consultant did not have the

technical capacity required to develop a national data base. The database was finally developed

and made operational with the expertise rendered by the IOM’s Technical Assistance Project

funded by the German Government.

According to the project document 11 staff would be recruited for the reparations for 6-12

months as appropriate. Nine local staff (including two drivers) were hired plus approx. 63 staff in

the field who were given short contracts ranging from 3 to 6 months to register, validate, and

enter war victims applications into the data base and to supervise payments.

This project has two strategic outcomes: a)  to contribute to an improved capacity of the Reparations Directorate of National Commission for Social Action (NaCSA) for the implementation of the Reparations Program; b) contribute to improved human dignity of the victims of the conflict  through a reparations program. These outcomes were realized through specific project outputs shown in the table below.

The table below shows the relationship between planned outputs, activities and their achievement.

| Project Outputs | Planned Activities |  |  | Achievements |  | % achieved |
| --- | --- | --- | --- | --- | --- | --- |
| A Special Unit for Reparations is established, office spaces acquired and furnished | Revision of the NaCSA Act to incorporate the Reparations mandate. Expand the Board and extend NaCSA’s mandate beyond 2008. • Establish a Reparations Directorate within NaCSA provide office spaces, procure office furniture and equipments. • Establish a policy making body to provide relevant guidance to the management of the reparations programme.) |  |  | The NaCSA Act revised to incorporate the Reparations mandate. The NaCSA mandate was expanded till 2018. • A Reparations Directorate was established within NaCSA. Office equipment was procured and the office space was furnished. • A National Steering Committee composed of members from government, civil society, victims groups, religious bodies and UN agencies was established. This committee serves as the policy making and guidance body to oversee implementation of the project.. |  | 100% |
| Technical consultants recruited. National Staff recruited. | Recruitment of two international technical consultants. Recruit 11 national staff for the reparations directorate for 6-12 months as appropriate. |  |  | One (local) technical consultant was hired by NaCSA to design a war victim’s database. The consultant made the initial assessment regarding the IT requirements related to the reparation database that was later developed by IOM international staff in Geneva and Georgia. The national consultant did not have sufficient technical capacity to perform the task Nine permanent staff were recruited for the reparations programme. These included a programme Director, Programme manager, outreach officer, M&E officer, database Officer, Field supervisor, office assistant and two drivers. Approx. 63 temporary staffs were also recruited to assist in registration, validating, entering applications from war victims into the database, and supervising payments |  | 100% |
| NaCSA Management Unit provided with logistic capacity. | Provide reparations directorate with logistics capacity (two 4x4 vehicles and 1 motor bike). |  |  | Two 4x4 vehicles and one motor bike were procured to enhance the logistic capacity of the reparation programme Directorate |  | 100% |
| Capacity of Relevant Staff Built in managing reparations | Organize for and outsource capacity building trainings for project staff and other relevant partners on implementing successful and sustainable reparations programmes. |  |  | The Director of the Reparations unit attended a one-week symposium on reparations in Morocco. Trainings were organized for (registration/ validation/ payment) project staff at the NaCSA headquarters and in all regions |  | 100% |
| A five year strategic plan for continued support for reparations developed and operationalised. | Plan for and develop a five year strategic plan for the sustainability of the Reparations programme beyond the current project funding |  |  | A five year strategic plan on sustaining the reparations programme was developed and is been put to operation |  | 100% |
| A database on profile of war victims established |  | Registration, review and validation of five categories of war victims’ applications (a projected figure of 16,000 victims). • Develop and install a database. | Approx. 29,700 Applications from war victims were received and reviewed, and a total of 20,107 applications were validated. • A war victims database was designed by IOM and installed.2 However due to time constraints (end of project) the data base could not be tested and NaCSA staff only partially trained to its management. |  | 100% |  |
| Government, victims, Civil Society, donors and other stakeholders sensitized on the reparations programme |  | - Establish an outreach system nationwide to sensitize war victims for registration. • Continuation engagement with Government, victims and key stakeholders for the sustainability of the reparations. Develop communication/ outreach strategies for sensitization and dissemination of reparation messages through print and electronic media. | Key stakeholders were sensitized about the reparations programme and victims were widely encouraged to apply for the reparations programme. A two-day stakeholder sensitization/ consultation meeting was organized at Parliament. • NaCSA engaged with the government, donors and victims in regular meetings as well as the general public through radio programmes and publications to raise awareness and sustain the reparations programme |  | 100% |  |
| A Special Fund for War Victims established and operationalised. |  | Opening a bank account and set up a Special Fund for War Victims and mobilizing stakeholder to make contributions | A Special Fund for War Victims was launched on 5th December 2009. The fund currently has seven Trustees to manage the Fund and operates two accounts at the Rokel Commercial Bank. Cash donations and pledges were made of approximately 200 million Leones. |  | 100% |  |
| Reparations subprojects for War Victims implemented |  | Identify partners, projects and provide inputs for the delivery of multi-sectoral social services for victims: • Outsource the organization of community symbolic reparations activities in 40 communities. Facilitate screening and provide medical support including fistula surgery to 200 Victims of sexual Violence Provide free medical support to severely war wounded victims. Outsource the provision of psychosocial support to war victims in 4 communities Deliver first installment of micro grant and educational support to 16,000 victims. | - Community symbolic reparations activities designed to promote communal healing and reconciliation were held in 40 chiefdoms. Five NGOs specialized in undertaking the community based activates were recruited to implement the symbolic reparations. - 235 victims of sexual violence were screened and provided with financial assistance to treat various types of sexually transmitted infections. Five received fistula surgeries undertaken by the medical charity Mercy Ships at the Aberdeen West Africa Fistula Center. Others were treated at Marie Stopes clinics. 49 War victims received support for emergency surgery for injuries and other life threatening conditions sustained during the war (e.g. surgery to remove bullets). Community psychosocial support activities were completed in four communities in the country (north, south, east and west). Four NGOs with extensive experience in community work, trauma healing and counseling were recruited to implement the psychosocial support activities. 13,123 and 6,984 Victims received the first installments of micro grants and educational support respectively. The Sierra Leone Commercial Bank was contracted to perform the payment of the grants to beneficiaries. |  | 100% |  |

This project was implemented by NaCSA, which was able to achieve the desired results by establishing successful partnership with key organizations. The table below shows they list of key partners and how they impacted the results.

.

| Partners / Agencies |  | Impact on Results |
| --- | --- | --- |
| International Organization for Migration | Provided technical support to planning and implementation of the project as well as ensuring proper monitoring and fudiciary management- |  |
| West Africa Network for Peace Building (WANEP-SL | Conducted symbolic reparations in six chiefdoms in Moyamba and Kono Districts as well group psychosocial activities in the Southern province |  |
| Child Fund Sierra Leone | Conducted symbolic reparations in four chiefdoms in Kenema District as well group psychosocial activities Kambia District in the Northern province . |  |
| Graceland Counseling Services | Conducted group psychosocial activities for war victims in the Western Urban and Rural Districts |  |
| P.R.O.T.E.C.T. Sierra Leone | Conducted symbolic reparations in seven chiefdoms in the Bombali and Koinadugu Districts . |  |
| Work By Faith Development Association (WOFDA) | Conducted symbolic reparations in seven chiefdoms in Port Loko and kambia districts |  |
| Kailahun District Development Association (KADDF) | Conducted group psychosocial activities for war victims in the Kailahun, Kenema and Kono Districts in the Eastern province |  |
| Hope Sierra Leone | Conducted symbolic reparations in seventeen chiefdoms across the country |  |
| Sierra Leone Commercial Bank (SLCB | Paid micro-grants and educational support to 20,107 beneficiaries across the country |  |
| Mercy Ships | Conducted medical screenings and performed fistula surgeries to victims of sexual violence |  |
| Connaught Hospital | Performed surgeries to 49 war victims to remove bullets and cure other war related infections |  |

III. EVALUATION & LESSONS LEARNED

The successful completions of the Reparations project in 2009, has created hope and expectation among thousands of war victims who are eager to receive fully reparations as recommended by the TRC. However experience and lessons learned during the implementation of the project suggest that the reparations programme requires long term commitment and more funding. The government at the

present circumstance cannot provide the financial commitment needed to sustain this important process that has began to fulfill the recommendations of the Sierra Leone Truth and Reconciliation Commission to address the abuses faced by war victims. It is therefore imperative that donors should continue to provide funding for the reparations programme so that the capacity that has been developed by the project in 2009 would not be lost.

The Sierra Leone Reparation program 2010 needs a projected budget of $ US 8,000,000 to start sustaining the achievements of 2009, streamline benefits into existing government programs (i.e. health care, education), develop a benefit delivery policy and exit strategy and continue the implementation of reparations sub-projects reaching out affected communities and war victims.

IV. INDICATOR BASED PERFORMANCE ASSESSMENT

Not applicable

The term “programme’ is used for programmes, joint programmes and projects.

Priority Area for the Peacebuilding Fund; Sector for the UNDG ITF.

The start date is the date of the first transfer of the funds from the MDTF Office as Administrative Agent. Transfer date is available on the MDTF Office GATEWAY (http://mdtf.undp.org).

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.

In addition, staff of the unit and a member from the steering committee participated in two workshops organised by IOM in Geneva on

managing reparations programmes, as well as in other trainings organised in Freetown on the same theme. However, these activities were

not funded with PBF funding. The German government paid for the Geneva workshops as well as the trainings in Freetown in order to

support the PBF funded programme.