**Guatemala**

|  |  |
| --- | --- |
| **Programme Title:** | Alliances to Improve the Situation of Children, Food Security and Nutrition |
| **Programme number & MDTF ref:** | MDGF-1986-I-GTM Children (67234) |
| **Window:** | Children, Food Security & Nutrition |
| **Approved Budget by NSC (US$):** | 7.5 million |
| **Participating Organizations:** | FAO, WFP, UNICEF, PAHO/WHO, UNFPA |
| **First Tranche transferred on:** | 3-Dec-2009 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| 3000 families from 40 communities selected for JP.“Healthy Schools” plan implemented in 40 schools. School vegetable garden programmes underway. Study on nutrition in 8 municipalities completed. A fiveyearnationalnutritionalsurveyfor40 communities launched. 39 communities in 8 municipalities trained in issues related to chronic malnutrition.  |
|  |
| **Problems and lessons learned:** |
| UN Agency coordination (regulations). Managerial (delays in contracting project staff). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

