**Guatemala**

|  |  |
| --- | --- |
| **Programme Title:**  | Strengthening Women’s Institutions in Guatemala |
| **Programme number & MDTF ref:** | MDGF-1660-B-GTM Gender (67146) |
| **Window:** | Gender Equality & Women's Empowerment |
| **Approved Budget by NSC (US$):** | 7.2 million |
| **Participating Organizations:** | WFP, FAO, PAHO/WHO, UNDP, UNFPA, UNIFEM |
| **First Tranche transferred on:** | 5-May-2008 |
| **Second Tranche transferred on:** | 1-Oct-2009 |
| **Third Tranche transferred on:** | 2-Sep-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Diagnostic on knowledge of labor law by police women completed. Government approved National Policy for the Development of Women and the Equity and Opportunities Plan 2008-2023. Several manuals prepared, amongst them 10,000 copies of the “Protocol for the Treatment of Victims of Domestic or Sexual Violence” distributed. Extensive training and support in domestic violence provided.  |
|  |
| **Problems and lessons learned:** |
| UN agency coordination. Coordination within the government. JP design issues. Managerial (delays in fund transfers.)  |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** No |

CHARTS & FIGURES

As of 31 December 2010

