**Guinea-Bissau**

|  |  |
| --- | --- |
| **Programme Title:**  | Promotion of a multi-level approach to child malnutrition |
| **Programme number & MDTF ref:** | MDGF-2033-I-GIN (67251) |
| **Window:** | Children, Food Security & Nutrition |
| **Approved Budget by NSC (US$):** | 2.5 million |
| **Participating Organizations:** | FAO, UNICEF, WFP, WHO |
| **First Tranche transferred on:** | 2-Sep-2009 |
| **Second Tranche transferred on:** | 14-Dec-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Training provided to health and nutrition centres technicians, with provision and distribution of transport means and materials for communities’ outreach activities. Distribution of kitchen material for food preparation and take home food supplements in health and nutrition centres. Sensitization workshops organized for teachers and parents. Assessment of nutritional status and food intake of school children completed in other 77 schools. 48 schools-gardens operational, with parent-teacher school garden management teams. Two experts recruited and placed in the Ministry of Health.  |
|  |
| **Problems and lessons learned:** |
| **UN Agency coordination:** Difficulties identifying and recruiting international and national project staff has hinder operational coordination between actors.**Coordination within government:** Lack of available staff and qualified staff in some concerned Ministries and/or regional departments. |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

