### PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Award ID | : | 00047251 |
| Award Title | : | CEDRO – “Country energy efficiency and renewable energy demonstration project for the recovery of Lebanon” |
| Award Timeframe | : | Oct 2007 – Oct 2013 |
| Award Components | : | CEDRO 1 – 00056604 CEDRO 2 – 00060150 CEDRO 3 – 00071261 |
| Reporting Period | : | 1 October 2010 – 31 December 2010 |

I. PURPOSE

Project Summary:

The aim of the CEDRO project is to support Lebanon’s recovery, reconstruction and reform activities and to complement the national power sector reform strategy through the implementation of end-use energy efficiency and renewable energy projects and through the removal of barriers for the promotion of sustainable energy applications in Lebanon. To achieve this, the project will work on three levels: the first involves the establishment of a demonstrative model addressing public sector building and facilities, the second involves the activation of the replication process, and the third involves the triggering of a national sustainable energy strategy and action plan. The CEDRO project is financed through the Lebanon Recovery Fund, and is in-line with Lebanon’s ongoing efforts to improve national patterns of energy consumption and cost.

Project Phases and Outputs:

| CEDRO 1 2.73 million USD | Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities (50-60 sites in South, Bekaa and Akkar) |
| --- | --- |
| CEDRO 2 3.50 million USD | Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (app. 60 sites across Lebanon) Technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities |
| CEDRO 3 3.50 million USD | Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (app. 60 sites across Lebanon) Technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities Research and development to enable the formulation of a national sustainable energy strategy and action plan |

Project Linkages to National Priorities and Reconstruction Goals:

Lebanon imports around 97% of its energy needs in the form of fossil fuel. In 2004, the national energy bill amounted to around 1.6 billion USD (around 20% of the annual public expenditure and around 7.8% of the national GDP), and in 2005 it reached 2.1 billion USD (around 26% of the annual public expenditure and around 10% of the national GDP).

The government of Lebanon has placed the reform of the power sector among its highest national priorities, as outlined in the recovery, reconstruction and reform paper submitted to the Paris 3 conference after the 2006 conflict. However, given the enormity of the challenges faced by the power sector, the power sector reform strategy has concentrated on addressing the energy supply side, without extending the scope to the demand side of energy management.

Knowing that reform on the supply side needs to be accompanied by reform on the demand side, the proposed CEDRO program has sought to complement the national power sector reform strategy by targeting end-use energy conservation and renewable energy demonstrations which will assist in the above categories of demand-supply imbalance, security of supply, diversification of energy sources, economic cost and the environment.

Moreover, the current Lebanese government has set itself a goal of achieving 12% of its total energy needs from renewable energy sources. CEDRO is seeking to assist in achieving this goal through its demonstration projects of various zero carbon to low carbon technologies and its analysis of renewable energy resources.

This project is an initiative by the Government of Spain to assist the Government of Lebanon in its recovery and reconstruction efforts with a clear focus on promoting sustainable energy services and concentrating on public sector buildings and facilities.

This project is in inline with Lebanon’s recovery, reconstruction and reform objectives, and falls within the Ministry of Energy and Water’s main priority to meet national demand for electricity.

Project Implementation Partners:

International Partners: 	-     Spanish Agency for International Cooperation

National Partners: 	-     Ministry of Energy and Water

and Lebanese Center for Energy Conservation Project (LCECP)

- Ministry of Finance

- Council for Development and Reconstruction

- Project Management

- Coordination and follow-up on a regular basis with the Technical Backstopping Agency, TTA, on all technical assessments for the selection of new sites, installation designs, supervision and monitoring of works;

- Preparation of regular progress reports and financial management of expenditures;

- Carry-out  project review meetings with the LRF Technical Committee (LRF Donors meeting 28th of September 2010 and the Recovery Fund Workshop on Achievements and Lessons Learned, 8th of September 2010)

- Organization of field missions and stakeholder meetings (regular meetings with the Ministry of Energy and Water (MEW) and with EDL);

- Daily follow-up with site engineers and project staff;

- Coordination with all national stakeholders and beneficiaries;

- Providing technical and policy advice to decision-makers (MEW) and UNDP CO on renewable energy issues, in particularly CEDRO played an important role in;

- Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities (in 2010)

The following projects have been completed in the last quarter of 2010 (or at least initiated in Q 4 of 2010);

- 1 Photovoltaic (PV) system project has been initiated in Kfour Public School in South Lebanon; the school has approximately 40 students yet is expected to increase in number as it is a newly opened public school. This system is similar yet slightly larger than the 25 systems already implemented by CEDRO in 2009, consisting of PV modules, inverter, charge controller and data logger, and the rest of balance of system (BoS) components.  The PV system provides the school with renewable electricity for their lighting and for running their computers and equipment. The project is extremely important in Kfour given that they do not have, as of yet, connection to the public electricity grid.

- 10 sites across Lebanon for wind reading measurement studies are being implemented, using anemometers (wind speed reading equipment)for some, while relying on computer modelling for others.   After 6 months of wind readings, those sites with sufficient wind speeds will be selected for the implementation by CEDRO of a micro-wind system, or electricity from a small wind system, project.

- The installation of 5 solar hot water (SWH) systems in public hospitals have been completed. They are complete systems ranging from 2,000 liters to 12,000 liters with flat-plate collectors and storage tanks, including data recording equipment1. These systems will provide 60 – 75% of the hot water demand by these hospitals, and therefore save similarly on the fuel consumption, fuel cost, and reduction of CO2 emissions. These hospitals are currently serving 264 beneficiaries (patients), yet will be serving up to 400 in the near future.

- 2 large SHW sites have been initiated in 2010 and are currently being completed (exp. Completion Q1 2011);

- 33 light emitting diode (LED) street lighting fixtures have been installed in Moukhtara (Chouf Area). LED fixtures save 30-40% more energy than normal street lighting fixtures.

- Setting an enabling environment for the conversion of public sector buildings and facilities into energy efficient modalities

- Issuing of newspaper releases and magazine articles (national coverage);

- Networking and coordination with national project partners and stakeholders such as the Lebanese Order of Engineers, Ministry of Energy and Water, Ministry of Public Works, etc.,

- Synergy with the on-going UNDP project at the Ministry of Energy and Water, Lebanese Centre for Energy Conservation project (LCECP), on ongoing energy audits and activities to build on the project’s technical know-how, experience on the ground, and lessons learnt during the implementation of energy efficiency and renewable energy activities.  This entails exchange of technical data and lessons learnt as well as brainstorming session to coordinate and maximise efforts for project implementation;

- The CEDRO website (www.cedro-undp.org) is running and is being continuously updated with new events and projects as they happen.

- Actively participated in the Beirut Energy Forum with the LCEC in October

- Official opening of a SHW system in Saida in 2010, attended by representatives of the Ministry of Energy and Water, Ministry of Health, the Spanish Ambassador, UNDP Country Office,  along with local politicians from deputies to municipality heads1.

- 2 Newsletters were prepared and printed in 2010, Issue 3 and Issue 4, and the cover page of these newsletters are reproduced in Annex 4 3.

- Assisting the establishment of a sustainable Energy Strategy for Lebanon

- Wind Atlas for Lebanon was completed in the last quarter of 2010, although the official results will not be announced until the beginning of 2011. The wind atlas will indicate where the windiest sites in Lebanon are through a 100 meter resolution map, and will indicate how much potential Lebanon has in wind power generation, putting to rest all discussion on potential which has ranged from as little as 150 MW to 500 MW and more. Furthermore, the offshore wind power potential will be assessed and mapped as well. The wind atlas is a national document and has been adopted by the Ministry of Energy and Water

- National Bioenergy assessment Study for Lebanon underway. Again, bioenergy is a little understood yet highly important energy source that needs analysis in Lebanon. A study is underway to assess all the potential of various bioenergy sources in Lebanon, assess conversion options, set scenarios of bioenergy uptake into future, all under very strict sustainability criteria and with a focus on barriers in Lebanon for bioenergy uptake.

All in all, CEDRO aims to assist the government in Lebanon in deciding which energy source to utilize to reach its objective of 12% of its electricity mix to come from renewable energy sources by 2020 – an objective approved by the Council of Ministers and asserted in the Copenhagen Summit1.

II. RESOURCES

|  |  | CEDRO 1 | CEDRO 2 | CEDRO 3 |
| --- | --- | --- | --- | --- |
| Total budget approved | : | USD 2,732,240 | USD 3,500,000 | USD 3,500,000 |
| Total disbursements as for 31 Dec. 2010 | : | USD 2,696,741 | USD 1,290,584 | USD 129,701 |
| Commitments for next quarter | : | USD 35,499 | USD 250,000 | USD 150,000 |
| Available Balance | : | USD 35,499 | USD 2,209,416 | USD 3,370,299 |

Budget and Expenditure Breakdown per LRF Category:

|  | CEDRO1 | CEDRO2 | CEDRO3 |
| --- | --- | --- | --- |
| CATEGORY | Total Budget (USD) | Total Exp. to date (USD) | Total Budget (USD) | Total Exp. to date (USD) | Total Budget (USD) | Total Exp. to date (USD) |
| 1. Personnel (Incl. staff and consultants) | 177,000 | 206,000 | 220,000 | 220,000 | 214,000 | 0 |
| 2. Contracts (Incl. companies, professional services) | 220,000 | 238,004 | 440,000 | 79,497 | 835,700 | 125,186 |
| 3. Training (incl. AV printing / production) | 22,000 | 16,142 | 40,000 | 6,610 | 50,000 | 0 |
| 4. Transport (local) | 30,000 | 38,800 | 10,000 | 764 | 25,000 | 0 |
| 5. Supplies and commodities (Incl. IT equip and rental & maintenance) | 36,300 | 50,387 | 50,000 | 31,000 | 70,000 | 0 |
| 6. Equipment (including installation) | 2,030,000 | 1,995,265 | 2,450,000 | 926,713 | 2,111,500 | 0 |
| 7. Travel | 14,000 | 6,055 | 15,000 | 4,000 | 25,000 | 1,899 |
| 8. Miscellaneous | 11,683 | 11,885 | 30,000 | 7,000 | 21,000 | 0 |
| 9. Agency Management Support (7%) | 191,257 | 134,203 | 245,000 | 15,000 | 147,805 | 2,616 |
| TOTAL | 2,732,240 | 2,696,741 | 3,500,000 | 1,290,584 | 3,500,000 | 129,701 |

| CEDRO Project | CEDRO 1 2.73 million USD | CEDRO 2 3.50 million USD | CEDRO 3 3.50 million USD |
| --- | --- | --- | --- |
| Activity Results |  | Indicators |  |
| 1 - Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities | Identification and Implementation of 50-60 EE/RE demonstration projects in South, Bekaa and Akkar | Identification and Implementation of 60-80 EE/RE demonstration projects the remaining regions of Lebanon | Identification and Implementation of 60-80 EE/RE demonstration projects across Lebanon |
| 2 – Outreach and technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities | Development and implementation of technical workshops and awareness tools | Development and implementation of technical workshops and awareness tools Development of GIS energy data base and EE/RE procurement specs | Development and implementation of technical workshops and awareness tools Development of GIS energy data base and EE/RE procurement specs Validation of project results and development of replication schemes |
| 3 – Research and development to enable the formulation of a national sustainable energy strategy and action plan | - | - | Assessment of national renewable energy resources Assessment of national energy efficiency potential Development of national EE/RE strategy & action plan |

Progress in Project Implementation:

| Activity Results | Activity Actions | Targets for 2010 | Status for 2010 |
| --- | --- | --- | --- |
| 1 – Project Management | Technical Management Financial Management Operational Management | Organization of 2 technical workshops and end of year project board meeting |  |
|  |  | Organization of 5 international backstopping missions; | 3 missions completed, 1 mission scheduled for Jan 2011. |
|  |  | Issue a report on the status and results of the CEDRO I pilot projects that were already implemented | Task completed |
|  |  | Provide advisory support services on EE/RE policies and legislations | TTA providing policy recommendations for the large wind sector in Lebanon Expert on PV farm hired on board of CEDRO Expert on CSP farms hired on board of CEDRO |
|  |  | Attendance of capacity building workshops for CEDRO team | TTA provided PV training to project team Site engineers trained on “economics of RE systems” |
|  |  | Preparation of regular progress reports; | Quarterly reports submitted in timely manner; |
|  |  |  | Request for extension of CEDRO to end of 2013 submitted to LRF committee, acceptance of this extension has been granted. |
| Activity Results | Activity Actions | Targets for 2010 | Status for 2010 |
| 2 - Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities | 2.1 Undertake targeted assessment and identification of project beneficiary sites; 2.2 Develop tender documents and undertake bidding & procurement of goods/services; 2.3 Undertake commissioning of works and supervision and monitoring of sites; 2.4 Undertake testing of performance & data collection; | Undertaking second EOI for RE/EE suppliers Implementation of 32 demonstration projects; 15 for PV sites pending the acceptance of a donation of 30 kWp of PV modules by the owner of Suntech (which is expected); 10 energy efficient sites (works began); 7 SHW hospital sites 10 thermal insulation sites Preparation of 20 new demonstration projects for implementation; Particularly 10 microwind sites and 10 thermal insulation | Completion of installation on 30 sites featuring photovoltaic systems and solar water heaters, and including: Public Hospitals; 20 Public Schools; 3 Municipalities; 2 Community centers; 3 public street lighting sites; Successful supervision of works for 30 sites; Work for Baalbeck institute (SHW project) under way Work on EE ITB (energy efficient lighting) under way Roumieh prison SHW project implementation under way (many obstacle are being encountered) LED street lighting project is completed Work for 5 SHW hospitals under way and are completed Thermal insulation RFP being prepared |
|  |  |  | Networking with potential beneficiaries for the identification of new sites, around 25 new sites have been identified; New sites for potential microwind and PV projects have been identified by CEDRO Team and RFP for wind measurements tended out and contractor announced (see below). EOI 2010 completed and new winners posted online. Constant cooperation with LCEC and MEW to promote concept of net metering |
| Activity Results | Activity Actions | Targets for 2010 | Status for 2010 |
| 3 – Outreach and technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities | Develop and implement technical workshops and awareness activities; Develop GIS energy data base and EE/RE procurement specs; Validate project results and enable replication schemes; | Development and implementation of 2 technical workshops; |  |
|  |  | Continuation and expansion of CEDRO outreach and visibility; Newsletter three to be completed and dsitributed | Updating project website: www.cedro-undp.org (En/Ar); Issuance of third edition of Newsletter (En/Ar) has been completed Documentary on CEDRO on Future news TV show; Blue and Green Brief discussion on PV on Kaleem El Ness by CEDRO project Article on CEDRO in (1) Economy and Business and (2) Environment and Development magazine CEDRO project featured on “Talk in Numbers” on Future news TV |
|  |  | Set-up of GIS database for 200 public sector sites; | Set-up of GIS database for 100 public sector sites completed; |
| 4 – Research and development to enable the formulation of a national sustainable energy strategy and action plan | Asses national renewable energy resources; Assess national energy efficiency potential; Develop national EE/RE strategy & action plan; | Completion of the Wind ATLAS for Lebanon (expected mid-November 2010). Initiation of a bioenergy assessment of Lebanon Completion of a microwind potential assessmet in 10 different sites Net metering pilot to be implemented and policy/legal legislation updated accordingly | Wind atlas completed, dissemination of results out in January 2011.bioenergy study initiated, works on the ground have begun – Tasks 1 and 2 completed. microwind potential assessment: bid is out, 12 bidders have submitted, winning contractor informed and works began Net metering measuring devices have been purchased for testing and 2 meters were installed on-site for examination Recommendations to amend energy efficiency law to incoporate technical requirements for net metering submitted to the energy efficiency law committee for consideration/incorporation into draft EE law |

* EE/RE = Energy Efficiency and Renewable Energy

Implementation Constraints and Lessons Learned during this quarter:

In this last quarter of 2010, CEDRO has been focused on three main fronts; Completed on-going projects; 5 SHW sites have been completed, Baalbeck and Roumieh Prison well under way, LED Moukhtara completed. Data logging and monitoring of installations; a wide scoping of implemented CEDRO projects had been performed to ensure systems are running to standard, and that data logging files are accurately recording data. Preparation for 2011 in terms of planning and budgeting was initiated in this quarter and technical specification for those ITBs that will be launched in the first quarter of 2011 were developed

IV. FUTURE WORK PLAN

| Outputs and Activities | 2010 | 2011 | 2012 | 2013 |
| --- | --- | --- | --- | --- |
| 1. Implementation of end-use EE/RE demonstration projects Identification of beneficiary sites Development of tender documents Procurement of goods / services Site Supervision and hand-over Monitoring of system performance | Implementation of 30 demonstration projects Monitoring of installations | Implementation of 30 demonstration projects Monitoring of installations | Implementation of 30 demonstration projects | Monitoring of installation Termination of project |
| 2. Outreach and Technology transfer for the activation of EE/RE applications Establishment of energy saving data base for public sector facilities Development & Implementation of capacity building & awareness programs Development of relevant EE/RE policies and procedures Validation of project results | Implementation of 2technical workshops Development of 70% of GIS database Development of EE/RE procedures Two media campaign for street lighting and PV projects to be carried out with high officials attending Implementation of school awareness campaign on RE | Implementation of 3 technical workshops Development of 100% of GIS database Development of EE/RE procedures | Implementation of 2 technical workshops | Validation of project results |
| 3. Research and development for the formulation of a national EE/RE strategy and action plan Assessment of national RE potential Assessment of national EE potential Identification of viable EE/RE actions Identification of Implementation tools and funding mechanisms | Completion of wind energy resource assessment Launch of assessment of bioenergy potential Launch of wind sector regulatory and legal framework Assessment of net metering potential | Completion of other RE resource assessment Identification of implementation mechanisms |  | Identification of national EE/RE strategy of Lebanon (putting together the studies initiated by CEDRO. |

| CEDRO |
| --- |
| CEDRO 1 Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (50-60 sites in South, Bekaa and Akkar) | CEDRO 2 Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (60sites across Lebanon) Technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities | CEDRO 3 Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (60-80 sites across Lebanon) Technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities Research and development to enable the formulation of a national sustainable energy strategy and action plan |

V. ANNEX A – First list of Beneficiary sites

| Region | Site | System | No. of beneficiaries |
| --- | --- | --- | --- |
| Akkar (CEDRO 1) | Rajem Issa public school | PV - 1800 Wp | 345 |
|  | Mashta Hammoud public school | PV - 1800 Wp | 322 |
|  | Kherbet Daoud public school | PV - 1800 Wp | 85 |
|  | El Tleile public school | PV - 1800 Wp | 122 |
|  | Hekr El Dahiri public school | PV - 1200 Wp | 134 |
|  | Ouyoun El-Samak public school | PV - 1800 Wp | 124 |
|  | Kroum Arab public school | PV - 1200 Wp | 83 |
|  | Ain Yaakoub mixed public school | PV - 1800 Wp | 160 |
|  | Habsheit public school | PV - 1200 Wp | 85 |
|  | Meniara public school for girls | PV - 1800 Wp | 303 |
|  | El-Hakoor mixed public school | PV - 1200 Wp | 388 |
|  | Abdallah Rassi public hospital | SWH – 4000 Lit | 57 |
| Bekaa (CEDRO 1) | Baalbak first elementary public school | PV - 1200 Wp | 178 |
|  | Chmestar community center | PV - 1800 Wp | 18 |
|  | Hosh el Harime intermediate school | PV - 1800 Wp | 385 |
|  | Jeb Jennine Municipality and Library | PV - 1800 Wp | - |
|  | Mdoukha public school | PV - 1800 Wp | 75 |
|  | Hosh El-Oumara community center | PV - 1800 Wp | 21 |
|  | Aana Intermediate public school | PV - 1800 Wp | 21 |
|  | Tell Zounoub Intermediate public school | PV - 1200 Wp | 70 |
|  | Hermel public hospital | SWH – 4000 Lit | 26 |
| South (CEDRO 1) | Ayteet public school | PV - 1200 Wp | 315 |
|  | Kherbet Selem first public school | PV - 1800 Wp | 213 |
|  | Kfarkela first public school | PV - 1200 Wp | 171 |
|  | Kfarshouba Intermediate public school | PV - 1800 Wp | 150 |
|  | Houla municipality | PV - 1200 Wp | - |
|  | Ain Ebel municipality | PV - 1200 Wp | - |
|  | Saida public hospital | SWH – 6000 Lit | 64 |
|  | Jezzine public hospital | SWH – 2000 Lit | 20 |
| Mount Lebanon (CEDRO 1) | Jbeil municipality | EE lighting | - |
|  | Assia municipality | EE street lights | - |
|  | Batroun municipality | EE street lights | - |

PV: Photovoltaic system    	SWH: Solar Water Heating system

Second list of Beneficiary sites

Energy Efficiency

|  | Region | Facility Name |
| --- | --- | --- |
| 1 | Beirut | Bassel Fleihan Institute |
| 2 | Beirut | VAT Building |
| 3 | Beirut | Council for Development and Research |
| 4 | Beirut | Lebanese University Faculty of Agriculture |
| 5 | Bekaa | Lebanese Agricultural Research Institute |
| 6 | Bekaa | Zahleh Municipality |
| 7 | Mount Lebanon | Hammana Municipality |
| 8 | Mount Lebanon | Banque Du Liban- Bekfaya |
| 9 | Beirut | Regie- Hadath |
| 10 | Beirut | Ministry of Social Affairs |

Solar hot water

|  | Region | Facility Name | Number of beneficiaries (People using hospitals) |
| --- | --- | --- | --- |
| 1 | Tripoli | Tripoli governmental hospital | 150 |
| 2 | Keserween | Keserween governmental hospital | 100 |
| 3 | Ehden | Ehden governmental hospital | 12 |
| 4 | Sebline | Sebline governmental hospital | 100 |
| 5 | Sir El Donnieh | Sir El Donnieh governmental hospital | 45 |
| 6 | Baalbeck | Baalbeck Army Institute | - |
| 7 | Roumieh | Roumieh Prison | - |

Street Lighting

|  | Region | Facility Name |
| --- | --- | --- |
| 1 | Moukhtara | Moukhtara Street Lighting |

PV

|  | Region | Facility Name |
| --- | --- | --- |
| 1 | South | Kfour public school |