### PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Project No. | : | 00063594 |
| Project Title | : | LRF-18 Recovery Coordination Support in Lebanon |
| LRF Signature date | : | 24 October 2008 |
| Project Start date | : | 30 October 2008 |
| Project Timeframe | : | 36 months |
| Reporting Period | : | 1 July - 30 September 2011 |

I. PURPOSE

Project Summary:

The project aims at strengthening the coordination capacity of the Resident Coordinator‘s Sub-Offices in the north and south of Lebanon to ensure a more effective and efficient delivery of recovery and development programs in Lebanon: This goal contains three key immediate objectives:

(a) Coordination at the field and national level through the strengthening of existing RC Sub-Offices enhanced: the primary function of the sub-offices is to facilitate and promote coordination of recovery and development efforts at the field level to avoid duplication and promote synergy and complementarities, strengthen community outreach in the regions and act as interlocutors with different partners and stakeholders (decentralized units of line ministries and government agencies, NGOs, civil society organizations etc.).

(b) Comprehensive Information Management Unit established and products shared with stakeholders and public at large: one of the key coordination functions that can assist in making a difference in the recovery and development effort is to provide information on recovery and reconstruction to the national government, local and international partners, donors and media. A successful recovery response is dependent on the collection, analysis and distribution of information on the work of development partners on the ground to support the recovery and reconstruction efforts.

(c)   Support the coordination mechanism and visibility strategy of the Lebanon Recovery Fund (LRF): Taking into account the possible expansion of the Lebanon Recovery Fund and the new initiatives that will be joining this MDTF (e.g. Oil Spills, Peace building Fund), it is necessary to enhance the coordination of UN Participating Organizations in order to avoid duplication and promote joint activities that can achieve greater results.

The ultimate goal of the coordination support structure is to enhance coordination of recovery and development activities in the field towards strengthening national capacity and ownership.

Project Objective:

Enhance coordination of recovery and development activities at the field level;

Improve information sharing between actors and raise awareness on recovery activities, thus providing a gateway for various actors working or planning interventions;

Contribute to provision of linkages among various UN agencies, local and international NGOs, civil society entities, the communities, and the Lebanese government entities both at the central and local level;

Support the coordination mechanism and visibility strategy of the LRF; and

Work towards joint programming amongst various actors.

Project Outputs:

The project will support Coordination Mechanisms in the field and an Information Management Unit that would allow the Resident Coordinator to provide information to national and international; governmental and non-governmental; donors and actors involved in the recovery and development efforts.

Project Linkages to National Priorities and Development Goals:

Through sustained linkages between the UNRC Office in Beirut and the Government, the project was able to reflect government priorities in the work of the various UN and civil society organizations in the North and South.

Project Implementation Partners:

For the RCO Sub-Office in the North:

The main UN partners are UNRWA and the other UN agencies working in the NBC response operation, Akkar and MDGF Programme (ILO, UN Habitat, UNICEF, UNDP, UNESCO, FAO and UNFPA);

National and international NGOs participating in the Cluster system; national and international NGOs operating in Akkar; local authorities (i.e. authorities of the NBC surrounding municipalities and municipalities of the 3rd ring and border areas); LPDC; Palestinian representatives, and bilateral and multilateral donors (i.e. EC, KFW).

For the RCO Sub-Office in the South:

UN agencies with a presence in South Lebanon (UNIFIL, UNDP and ILO) plus others involved in sector meetings and emergency preparedness (UNRWA, UNICEF, FAO, UNSCOL and UN-Habitat);

Government officials at the central and regional level;

Local authorities, regrouped in Unions of Municipalities and Steering Committees including national and international NGOs; Local and international NGOs, and Donors.

II. RESOURCES

| Total budget approved | : USD 412,162.14 |  |
| --- | --- | --- |
| Total disbursements as for 30 September 2011 | : USD 268,446.33 |  |
| Commitments for next quarter | : USD 100,000 |  |
| Available Balance | : USD 143,715.81 |  |

| CATEGORY | TOTAL BUDGET (USD) | TOTAL EXP (USD) as of September 2011 | TOTAL EXP (USD) Jul-Sep 2011 |
| --- | --- | --- | --- |
| 1. Personnel (Incl. staff and consultants) | USD 258,192 | USD 173,645.48 | USD 41,787.16 |
| 2. Contracts (Incl. companies, professional services) | USD 30,000 | USD 6,580 | USD 6,580 |
| 3. Training | USD 20,850 | - | - |
| 4. Transport | USD 13,400 | USD 8,704.38 | USD 4,473.87 |
| 5. Supplies and commodities | USD 32,380 | USD 16,766.69 | USD 5,794.2 |
| 6. Equipment | USD 10,500 | USD 11,984.93 | USD (659.77) |
| 7. Travel | USD 13,376.26 | USD 30,267.97 | USD 1,265.83 |
| 8. Miscellaneous | USD 6,500 | USD 2,934.97 | USD 1,100 |
| 9. Agency Management Support | USD 26,963.88 | USD 17,561.91 | USD 4,223.89 |
| TOTAL | USD 412,162.14 | USD 268,446.33 | USD 64,565.18 |

III. RESULTS

Progress in Project Implementation:

| Project Outputs & Activities | Status |
| --- | --- |
| Output 1: Enhanced coordination at the field and national level through strengthening of existing Resident Coordinator Sub-Offices. |
| 1.1 Liaise with authorities at the central, regional and local levels to ensure overall coherence of development interventions in line with Government priorities: | RCO Sub-Office in the South (Tyre): The Sub-Office continued to liaise with central and local authorities on an information sharing level, assessing informally the possibility of a handover strategy to unions of municipalities when it will close down. An exit strategy was discussed with other UN partners as developed later in the report, but it was agreed that this might be too premature regarding logistics and the lack of capacity to carry out coordination functions which would be for the time being monitored by the central office in Beirut. With regard to the working groups, the involvement of regional authorities was pursued whenever possible. The new regional representative of the MoPH, Dr. Alaouie, expressed interest when contacted to participate in the work of the Health group chaired by IMC. Eventually, the Ministry would take ownership and co-chair meetings. The same applies to the Ministry of Education and Higher Education. RCO Sub-Office in the North (Tripoli): Within the context of the Syrian displacement in Akkar, the Sub-Office participated in several coordination meetings at the field and central levels on a weekly basis. These meetings gathered officials from the Ministry of Social Affaires (MoSA), the High Relief Committee (HRC), UNHCR, as well as international and local NGOs. The meetings in the field focused on coordinating FI/NFI distribution and health assistance. At the central level, UNHCR lead coordination meetings focusing on Shelter, WatSan, and Protection (including education, health, and psychosocial support). In addition, specialised Health meetings in Beirut are chaired by WHO. All meetings aim at coordinating services provided to displaced Syrians in North Lebanon, and serve as an information sharing platform. The Sub-Office liaised regularly with mayors and municipal council members on issues related to UN agencies’ activities in the North. The Sub-Office continued to liaise with the Lebanese Palestinian Dialogue Committee’s technical team on issues concerning Palestinians in the Nahr el Bared and Beddawi Camps. |
| 1.2 Liaise with civil society, national and international NGOs, donors and other multilateral partners to avoid duplications and promote synergies among the different development partners | RCO Sub-Office in the South : The Sub-Office pursued his collaboration with civil society, national and international NGOs and multiplied bi-lateral meetings in order to identify priority areas for the South to engage donors and relevant stakeholders. Outside the working groups composed mainly of Lebanese and Palestinian associations, discussions were held with Sadr Foundation, Terres des Hommes, Relief International, Premiere Urgence, NRC and UN counterparts namely UNDP, UNIFIL, UN-Habitat and UNRWA. The Sub-Office continued to respond to a number of inquiries and requests regarding UN agencies and NGOs (contact lists, funding and available data on villages and municipalities). RCO Sub-Office in the North: The Sub-Office maintained its collaboration with more than 30 stakeholders from the civil society, UN Agencies, national and international NGOs in both Nahr El Bared and Beddawi Camps to enhance the participation of local and international NGOs in the cluster meetings. The Sub-Office also maintained links with the organisations working in Akkar on the Syrian displacement situation. The Sub-Office provided technical and operational support to the MDG-F Programme “Conflict Prevention and Peace Building in North Lebanon”. The Sub-Office also continues to support the six UN agencies working on the Programme and actively participates in the interagency biweekly meetings. Participants in the meetings were briefed on the situation in Akkar in light of the influx of Syrian nationals into the area. Both Sub-Offices are still periodically updating the mapping of all activities undertaken by NGOs, INGOs and UN agencies in the North. The objective of this effort is two-fold: to define who is doing what, where and when and; determine the needs and gaps thus avoiding duplication. |
| 1.3 Strengthen coordination mechanisms through the establishment of interagency, general and or sector coordination platforms | RCO Sub-Office in the South : Technical working groups met five times in total during the reporting period. The Shelter WG chaired by PU-AMI created a google document page where minutes of meetings and reports could be shared on the following web site: http://docs.google.com. Since ECHO has announced it will not finance any more shelter or watsan projects in 2012, the group will focus on looking for new donors and/or partnerships. The Education WG discussed drop-outs, the Health WG chose to work on emergency preparedness and A presentation was given at the Livelihoods meeting by ADR and KDC commissioned by UNDP on capacity and needs assessment of 36 targeted communities in South Lebanon. This socio-economic assessment was shareed with all stakeholders including relevant ministries. Also discussions were held with UNIFIL Gender Unit and the NGO Abaad-Resource center for gender equality for the creation of a Gender working group for the South. A meeting was held with UNIFIL to discuss the revitalization of coordination meetings in Sector East and the engagement with MOSA centers and civil society in this regard. Finally, the Sub-Office assisted the Beirut Office with UNCT meetings held bi-monthly and other Integrated Working Groups meetings, namely Human Rights and Gender , the National Aids Strategy and the donors platform. RCO Sub Office in the North: The Sub-Office arranged for an Interagency meeting in September, during which UN agencies working in the North shared information on their activities and discussed possible ways of coordination and collaboration. The Interagency meetings aim at making sure that UN Agencies operating in North Lebanon share information on projects and activities for the purpose of identifying areas for cooperation and collaboration. Two General Coordination meetings for Akkar were held in July and September. These meetings were organised due to a need that was identified with UN agencies working in Akkar. Participants included UN agencies, the Council for Reconstruction and Development, the Economic & Social Fund for Development, international donors, local donor foundations, and INGOs. The first meeting tackled the procedural matters related to how coordination in Akkar will be organised, while the second constituted an information-sharing exercise on the activities of each participating organisation. It was decided that the next bi-monthly meeting will tackle coordination gaps. In addition to many bilateral meetings with organisations in Beirut and throughout the North to enhance our relationship with the local civil society, and promote our services, 4 cluster and working group meetings took place during the reporting period July – September 2011: 2 Education/Health/MHPS 2 Protection In addition to the bilateral and the multilateral coordination efforts that take place during and pursuant to the cluster meetings, these meetings are considered to be the only platform for the Palestinian organisations to share information and concerns with UNRWA. |
| 1.4 Support the implementation of joint assessments and joint programmes. | The North Sub-Office has been actively supporting the MDG-F joint-program. In addition to technical support, the office assists the various UN agencies with field work and monitoring on a needs basis. The North Sub-Office also prepared analytical briefs on the situation in Akkar in light of the Syrian influx into the region and shared them with the concerned organisations. One of them is titled “Socio-economic situation in Akkar in light of the crisis in Syria” and is available at http://www.un.org.lb/Library/Files/News/Akkar%20%20_Socio-Economic_Brief_July_20.pdf. The Sub-Office also assisted UNHCR, the High Relief Committee and INGOs in their relief efforts by assigning two staff members from the Sub-Office to work as part of the distribution team in Akkar for a period of three days. |
| 1.6 Support the implementation of a Contingency Planning/Response Plan at the regional level. | The Health Technical Working Group in the South identified emergency preparedness as a priority to work on. |
| Output 2: Comprehensive information Management Unit established. |
| 2.1 Develop, produce and post on the webpage a comprehensive database. | The North Sub-Office continued uploading information to ensure an accurate update of all recovery operations information on the NBC website www.lebanon-support.org/nbc. At the Beirut Office, the Information Unit continued to update and upload information (including the LRF subpage) on the website, through liaising with UN Agencies and their implementing partners, government ministries, national counterparts and civil society. |
| 2.2 Develop, produce and disseminate maps and related documents to support the recovery and development work | Sub-Offices were engaged in updating their contact lists and mapping the activities of local and international non-governmental organisations, UN Agencies and civil society organisations working in the North and the South. This information is being incorporated into the UNRCO central information management system including its on-line facility. RCO Sub Office in the North continued to maintain an updated contact list of all active stakeholders in Nahr el-Bared and Beddawi Camps, Akkar, Minnieh/Dinnieh and Tripoli. This list is shared with partners upon request. This list was used by UNRWA to consolidate its own list of invitees to the inauguration ceremony of Package I and 3 schools in NBC. |
| 2.3 Develop strong links with other GIS staff. |  |
| 2.4 Act as an information desk including the distribution of a daily media and situation review. | The information unit and Sub-Offices continued to respond to a number of inquiries and requests regarding UN agencies and NGOs (UNCT members, contact lists, funding and available data on villages and municipalities). RC Sub Offices prepared minutes of meetings and other information and disseminated them to all participants and posted them online at www.lebanon-support.org/nbc. The RCO in North Lebanon prepares daily media reviews on issues related to the North and disseminates it to all UN Agencies operating in the North. |
| 2.5 Support visibility, outreach and communications activities | The Information Unit continued to develop promotional material regarding joint programmes, UNCT, UNDAF and donors outreach. The RCO in North Lebanon built a network of media reporters and outlets to cover UN activities in the North. The Sub-Office also distributed UN publications in visibility bags to various stakeholders in the North, including NGOs, municipalities, unions, universities, etc. |
| Output 3: Support the coordination mechanism and visibility strategy of the Lebanon Recovery Fund |
| 3.1 Support the coordination of the UN agencies with regard to the implementation of the LRF. | The Beirut Office coordinated the implementation of LRF projects and continued to provide the link between UN agencies and the Steering Committee. |
| 3.2 Produce a quarterly newsletter of the LRF activities. | Sub-Offices continued to prepare quarterly reports consolidated by the Beirut Office. In order to increase the visibility of the LRF projects and to reach out to most of the UN Agencies, Government interlocutors and implementing partners, the Information Management Unit has designed and produced an LRF newsletter. The July-September issue is the first edition of the newsletter which includes an overview of LRF success stories and events. |
| 3.3 Produce a brochure and other hard copy visibility material for the LRF. |  |
| 3.4 Produce posters of the LRF. |  |
| 3.5 LRF documentation available in both UN System in Lebanon and MDTF websites. | The Information Unit redesigned the LRF subpage (http://www.un.org.lb/Subpage.aspx?pageid=465) .This subpage is divided into four pages: Overview; LRF Management Structure; LRF projects, and Publications. The IMU will continue to update and upload information on the LRF pages regularly. Latest and updated information can now be accessed on www.un.org.lb . |
| 3.6 Develop and produce necessary tools serving the LRF communication strategy. | The Information Unit continued to update the website and produce promotional material including presentations and brochures to enhance LRF visibility. |

Implementation Constraints

The South Sub-Office was already under constraints with reduced staff involved in lending support to the Beirut Office in addition to relocation to new shared offices with UNDP . The announcement of the closing of both Sub-Offices by the end of the year had a negative impact since the needs for coordination are felt even more with reduced resources on the ground. For both RCO Sub-Offices in Tyre and Tripoli, the continuing security instability impacts adversely on their working environment and on the willingness of donors and International NGOs to expand their programmes. Finally, the holy month of Ramadan witnessed a slowdown in activities, especially with municipal counterparts.

Key Partnerships & Collaboration

Key Partnerships & Collaboration

IV. FUTURE WORK PLAN

| KEY ACTIVITIES | July | August | September |
| --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Output 1 Enhanced coordination at the field level through strengthening of existing coordination sub-offices. |  |
| Liaise between the central and regional level | x | x | x | x | x | x | x | x | x | x | x | x |
| Strengthen relations with newly elected municipalities | x | x | x | x | x | x | x | x | x | x | x | x |
| Support advocacy campaigns regarding the rights of vulnerable groups, Set up a child protection platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Work towards the creation of a gender platform |  |  |  |  |  |  |  |  |  | x | x | x |
| Coordination of Shelter/WatSan Cluster meetings (including agendas, MoM, and Action Plan) |  |  | x |  |  |  |  |  |  |  | x |  |
| Coordination of Education, Health/MHPS Cluster Meetings (including agendas, MoM, and Action Plan) |  |  | x |  |  |  |  |  |  | x |  |  |
| Coordination of Education Sub-Working group (including agendas, MoM, and Action Plan) |  |  |  |  |  |  |  |  |  |  |  |  |
| Convening General Coordination Meetings (including agendas, MoM, and Action Plan) |  |  |  | x |  |  |  |  |  |  |  | x |
| Attending UNRWA NMU Meetings | x |  | x |  | x |  | x |  | x |  | x |  |
| Maintaining an updated contact list for active organizations in NBC | x | x | x | x | x | x | x | x | x | x | x | x |
| Liaising with local and international NGOs | x | x | x | x | x | x | x | x | x | x | x | x |
| Liaising with local authorities | x | x | x | x | x | x | x | x | x | x | x | x |
| Liaising with LPDC | x | x | x | x | x | x | x | x | x | x | x | x |
| Liaising with RRC |  |  |  |  |  |  |  |  |  |  |  |  |
| Liaising with UN Agencies | x | x | x | x | x | x | x | x | x | x | x | x |
| Hold UN inter-agency meeting in the North composed of all UN agencies working in the area |  |  |  |  |  |  |  |  |  |  | x |  |
| Providing technical support to UN agencies in the North on a needs basis | x | x | x | x | x | x | x | x | x | x | x | x |
| Output 2 Comprehensive information collection system at the field level established and shared with stakeholders and the public at large. |  |
| Re-design the data management system and upload relevant info on the website | x | x | x | x | x | x | x | x | x | x | x | x |
| Create promotional material and a newsletter | x | x | x | x | x | x | x | x | x | x | x | x |
| Liaising with Lebanon Support and uploading necessary cluster documents to the website | x | x | x | x | x | x | x | x | x | x | x | x |
| Releasing a regular newsletter that covers all UNRCO activities in Lebanon |  |  |  |  |  |  |  |  |  |  |  |  |
| Establishing a GIS system | x | x | x | x | x | x | x | x | x | x | x | x |
| Maintaining an updated contact list for active UN agencies, municipalities, donors and line ministries in Lebanon | x | x | x | x | x | x | x | x | x | x | x | x |
| Mapping the activities of all organizations working in North and South | x | x | x | x | x | x | x | x | x | x | x | x |
| Output 3 Support the coordination mechanism and visibility strategy of the Lebanon Recovery Fund |  |
| Produce a newsletter | x |  |  |  |  |  |  |  |  |  |  | x |
| Make available LRF documentation in both UN System Lebanon & MDTF websites | X | X | X | X | X | X | X | X | X | X | X | X |
| Develop LRF communications strategy |  |  |  |  |  |  |  |  |  |  |  |  |

Adjustments to strategies, outcomes or outputs:

RC Sub-Office in the North The Office has adapted its work plan to reflect the changes and demands of UN agency partners in the North. The Office is working very closely with the UNDP on coordination of development efforts and with UNHCR on coordination of humanitarian efforts in Akkar.

| INDICATOR BASED PERFORMANCE ASSESSMENT |
| --- |
|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Comments (if any) |
| Outcome 1 Enhance coordination of recovery and development activities in the field towards strengthening national capacity and ownership |
| Output 1.1 coordination at field and national level through strengthening of the existing RC office’s in Lebanon | General Coordination Meetings Sectorial Meetings Cluster Meetings UN Interagency Meetings Number of joint field visits Number of sectors reports produced Number of analysis/assessments produced and posted on the web-page | N/A | General Coordination Meetings are held on monthly basis Cluster Meetings are held on monthly basis Interagency Meetings are held on bi-monthly basis For South Sub-Office both General and Inter-agency coordination meeting are held on bi-monthly basis | North Sub-Office: 2 Education/Health/MHPS 2 Protection 1 Inter-agency meetings 2 General Coordination meetings for Akkar South Sub-Office: 1 Education TWG 2 Shelter/WatSan TWG 1 Livelihood TWG 1 Health TWG Bi-lateral meetings with UNIFIL, UNDP, UN-Habitat | Due to security issues and the Ramadan both General Coordination and Inter-agency meeting were postponed | Minutes of General Coordination Meetings Minutes of Sectorial Meetings posted on the web-page Minutes of Cluster Meetings Minutes of UN Interagency Meetings Minutes of TWGs meetings |  |
| Output 2.1 Comprehensive Information Management Unit established | Assessments/reports related to development issues posted and number of hits on the website 3Ws maps produced and posted on the webpage Sector intervention maps produced and posted on the webpage Number of registered new users; poll participation rate; and number of hits on the website | N/A | Quarterly maps of 3 Ws Quarterly maps for each sector in each district Quarterly Reports for basic services available Capacity to provide other reasonable “ad hoc” mapping services to clusters Mapping of all organizations working in North and South Minutes of meetings and relevant documentation of joint programme activities Dissemination of events and activities related to recovery and development activities at the national and local level Host a website where key documents, policies, best practices, assessments, cluster data, contact lists, news, impact monitoring, maps and other relevant documents and information can be shared with wider community Summary of local media reviews | North Sub-Office: Action Plans for NBC Clusters are continuously updated 3 Ws map for North area is done and under continuous update Sector or Sub-Sector mapping is being provided upon need and request Minutes of meetings is being prepared and timely disseminated The sub-office acts as a information dissemination hub in the region All relevant information and documents are being posted on www.lebanon-support.org/nbc website Daily media review is being prepared and disseminated to UN agencies acting in North Lebanon South Sub-Office: Four technical groups Education/Health/Shelter&WatSan/ Livelihoods | N/A | Comprehensive database is maintained and results available to partners and stakeholders through the recovery section of the RC webpage 3Ws maps per area produced and posted on the web-page Sector intervention maps produced for each of the sector working group |  |
| Output 3. Support the coordination mechanism and visibility strategy of the Lebanon Recovery Fund | No overlapping or duplication in activities of LRF Projects Awareness on LRF activities increased and disseminated |  |  |  |  |  |  |

# Text boxes

For the RCO Sub-Office in the South, The reporting period witnessed interaction between UN agencies and NGOs present in the South on specific themes of common interests identified by all stakeholders.

The RCO Sub-Office in the North continued to maintain its partnerships and collaboration with the communities, local authorities, civil society organisations, international and national NGOs, donors and UN agencies throughout the reporting period.