Lebanon Recovery Fund

Completion Report

FLOOD I

00059666

Completed as of May 31st, 2011

- Background Information

  - General project information

| Programme Title & Number |  | Country, Locality(s), Thematic Area(s) |
| --- | --- | --- |
| Programme Title: Flood Risk Management and Water Harvesting for Livelihood Recovery in Baalback-Hermel, phase I Programme Number: 00059666 MDTF Office Atlas Number: |  | Flood I: Baalback el Hermel Caza specifically the Towns of Aarsal and Fakeha. |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| UNDP |  | Ministry of Agriculture |

| Programme/Project Cost (US$) |  | Programme Duration (months) |
| --- | --- | --- |
| MDTF Fund Contribution: | $2.83 million |  | Overall Duration: | 4 years |
| Agency Contribution |  |  | Start Date: | Feb 2008 |
| Government Contribution |  |  | Revised End Date: | May 2011 |
| Other Contribution (donor) |  |  | Operational Closure Date | May 2011 |
| TOTAL: | $2.83 million |  | Financial Closure Date | May 2012 |

Number of extensions received and dates

1 no-cost extension obtained on July 1st 2010 to extend Flood I till 31st May, 2011.

| CATEGORY | TOTAL BUDGET (USD) | TOTAL EXP. TO DATE (USD) |
| --- | --- | --- |
| Personnel | 200,000.00 | 186,003.42 |
| Contracts | 250,000.00 | 130,849.80 |
| Training | 50,000.00 | 0 |
| Transport | 20,000.00 | 11,821.34 |
| Supplies & Commodities | 50,000.00 | 37,882.08 |
| Equipment | 2,000,000.00 | 2,256,140.48 |
| Travel | 50,000.00 | 1,556.00 |
| Miscellaneous | 37,833.00 | 27,875.77 |
| Agency Management Support (7%) | 186,048.00 | 185,649.02 |
| Total | 2,843,880.00 | 2,837,777.91 |

  - Attachments to be Provided

    - Financial statement

    - Project Deliverables (Final Reports)

    - Publications

    - Media coverage if any

    - Evaluation report (will be available in October 2011)

  - Background and Issues Addressed in the Project

The project aims at assisting the Government of Lebanon in its recovery and reform efforts in the conflict-affected and high-poverty region of Baalback-Hermel through better land management practices, namely flood risk reduction and improved access to irrigation water and networks to achieve crop diversification and improve productivity. This will be achieved through the construction of stone walls, check dams and water collection reservoirs to prevent runoff water from reaching villages and farms and through the restoration of land cover to reduce soil erosion. The objectives related to water management will be achieved through construction of membrane-lined reservoirs to collect unused water from springs, rainfall and snow melts and through installation of water-use efficient irrigation networks and systems that will be used by local farmers to improve their crop diversity and productivity. The project is financed by the Government of Spain through the Lebanon Recovery Fund established on the occasion of the Stockholm Conference, and is in line with the UNDP’s development goal of alleviating poverty in rural drylands of the conflict-affected Baalback Hermel area.

  - Name of responsible officer

The Flood Phase I Project is a UNDP executed project supervised by the Energy and Environment (E&E) Program Officer Ms. Jihan Seoud. The project Manager of the Flood Phase I was Dr. Hassan Machlab from 2008-2009, and Charbel Rizk from 2009- 2011.

  - Project partners and roles

- The Ministry of Agriculture (MoA) is the main partner of the project given that the mandate of this ministry includes the protection of soil and agricultural lands from flooding and other natural occurrences.  The project management team is housed at the MoA and coordinates with the national focal point at the Ministry on a regular basis.  The Ministry is also a member of the project board along with UNDP and the Council for Development and Reconstruction.

- Local partners are the Municipalities of Aarsal, Fakeha and Deir el Ahmar and the Agriculture Cooperative of Deir el Ahmar.  The local partners are the main stakeholders in this project and supported in the selection of the lands/areas where flood risk management structures were established, they took over the responsibility of maintaining the structures once built as well as irrigating and maintaining the reforested areas of land.  The municipalities also provided the project contacts with the local farmers, herders, military, land owners, military, etc.  The decision making process on the ground involved all local parties and decisions are taken in consensus. Progress of work is also shared with all partners.

- The Cooperative of Deir El Ahmar: The cooperative of Deir el Ahmar contributed the land on which the reservoir was built.  The Municipality provided also a section of an adjacent plot so that the reservoir would be extended beyond the land owned by the coop.  The cooperative was also a key in the contacts with the farmers, the municipality and local authorities.  They provided a much needed help in the acquisition of permits and approvals for construction.

- Project Implementation Details

  - Project Objectives

The objective of the project is to reduce flood risk and improve water harvesting and irrigation.  The activities include the construction of flood mitigation reservoirs and structures such as contour walls, check dams, and plant green areas in order to reduce flood risk in the villages of Aarsal and Fakeha. It will also train people on how to manage floods. Finally the project objective has improved irrigation through the construction of ponds for water harvesting and storage and irrigation lines for delivery of water to crops in an efficient manner.

  - Project activities

| Activities | Progress to date |
| --- | --- |
| Technical, financial and operational Management. Promote synergies with relevant on-going projects in target area. Exchange of information and coordination meetings | Project management was undertaken successfully at the technical and financial level. Coordination was ongoing with all stakeholders in the regions mainly the municipalities of Aarsal, Fakeha Deir el Ahmar and the agriculture cooperative of Deir el Ahmar. |
| 2.1 Data collection and identification of target area. 2.2 Modeling of target area and generation of maps. 2.3 Constructions for flood control and prevention. 2.4 Monitoring, evaluation and impacts assessment | Meteorological, soil, flow lines, etc… data was gathered for flood by ACSAD in collaboration with the project management unit. The watershed of Aarsal was delineated and flows were modeled in order to determine the size of reservoirs and flood mitigation structures (contour walls, check dams, etc…) Based on the above analysis, 8 reservoirs and 161 wall structures were designed by ACSAD and Mr. Mohammad Mudabber a soil erosion expert from Jordan. The total volume of the reservoirs was 330,000 m3. These reservoirs will help reduce the impact of floods at 60% for a 50 year flood and at 40% for a 100 year flood. The wall structures were designed based on terrain and needs flood and erosion control needs. The different types included check dams, contour stone walls and sediment traps. Please refer to annex 1 for details on the reservoirs and wall structures. The construction of reservoirs and walls was contracted to two separate companies Mechref and Al Jihad and supervision was done by ACSAD, Mr. Mudabber and the PMU. Refer Annexe 2 for pictures Currently the impact of flood is being monitored by the PMU. For each flood event data on extent, flows, damage etc… is collected and analyzed by the project team |
| 3.1 Field surveys and assessment of water resources 3.2 Identification of water-harvesting sites. Constructions of reservoirs and irrigation networks 3.4 Selection of beneficiaries and technical advice | The firm Rafik Khoury and Partners (RKP)was contracted to undertake an assessment of potential site for water reservoirs, design the reservoir and supervise the construction works. An assessment of 33 different locations for water harvesting was done by RKP and the PMU. 2 Locations were selected and designs for reservoirs in Deir el Ahmar and Chlifa were finalized by the consultants The selection of the sites for the construction of reservoirs was based on several criteria mainly: land availability, number of beneficiaries, and support by local communities and local organizations for the project. Finally, and due to budget constraints,. one reservoir was constructed in Deir el Ahmar. Main irrigation lines were also installed. The construction of the reservoir was contracted, through competitive bidding to Farhat Group The design package of the reservoir in Chlifa was given to Green Plan and CDR for potential execution by these bodies More than 300 farmers will benefit from the reservoir in Deir el Ahmar. The land irrigated by the reservoir will be planted mainly with vines for wine making. Vines require irrigation for the first two years of planting. The current stored volume of water can irrigate around 40 ha but passed the first two years the system can irrigate another 40 ha and finally all the available land area of around 200 ha. Training on water use and irrigation efficiency was undertaken by the project. The training covered the construction of the reservoir and its maintenance and efficient irrigation techniques. |
| 4.1 Identification of erosion-sensitive areas 4.2 Establishment of nurseries for seedling production 4.3 Crop diversification and increased productivity 4.4 Forestation and forage cultivation | An erosion map was developed by the project management unit. This map identified sensitive areas that are highly prone to erosion. A land selection matrix was also developed by the project staff in order to identify plots of land seedlings on and increase the ground cover. The matrix included land availability, possibility for protection by the municipality of Aarsal, ease of access for irrigation, type of soil, etc… Production of seedlings and planting was contracted to the local NGO ARDA. 15,000 seedlings were planted and inspected by the PMU. ARDA also planted an area with forage crops for grazing. The municipality of Aarsal has been contracted to provide maintenance for the seedlings A trial using seeds instead of seedlings was undertaken with high success rates. Using seeds instead of seedlings reduces the costs of reforestation. The project team is till monitoring the progress of the planted areas. |

  - Project Outputs

| Project Outputs | Progress to date |
| --- | --- |
| 1.Project management | The management of the project was undertaken successfully and in a timely manner All progress reports were presented to the LRF Financial management was undertaken successfully. All funds were disbursed. |
| 2. Flood Risk Management and Reduction | 8 reservoirs and 161 walls were constructed Reduction of flood risks for up to 40% for 100 year floods and 60% for 50year floods was achieved through this project. |
| 3. Water Harvesting and Irrigation Networks | 33 sites assessed, two reservoirs designed and one built The irrigation reservoir and irrigation network built in Deir el Ahmar will serve more then 300 farmers and will irrigate 200 ha over a period of 10 years. |
| 4. Land Cover Increase and Soil Erosion Reduction | 15,000 trees were planted in Aarsal covering an area of 21 ha Very good results through planting from seeds might have cost reduction implications on reforestation in Lebanon |

  - Immediate objectives, Desired Outcomes and Extent of Achievements

As presented above, the objectives of the projects were all achieved.   Flood risk reduction through the construction of reservoirs ad walls and the planting of trees was achieved. Improved access to water for irrigation through the reservoir in Deir el Ahmar was also achieved.  The project contributed to improved water storage in ground layers through recharge from  the water collected in the reservoirs  after flood events.  It also contributed to the improvement of the economic condition of people in Aarsal, Ras Baalback, Fakeha and Deir el Ahmar through the reduction of losses of livelihoods caused by flood events and the creation of income through irrigated agriculture.  It will reduce costs born by the Government of Lebanon and the tax payers amounting to 2.5 million dollars per flood event.  The project has also contributed to the increase in green cover which has positive implications on reduction in soil erosion, increased infiltration of water in soils and reduction of overland flow.  The impacts of greening plots of land in Aarsal have economic implications though conservation of top soil and environmental services such as water conservation.

Due to budget constraints and however, the number of water harvesting reservoirs was reduced from three to one and the number of trees to be planted in Aarsal was reduced from 20,000 to 15,000.  The selection process of sites for constructing reservoirs has led to the identification of only two sites: Deir el Ahmar and Chlifa.  The design of the Deir le Ahmar was complicated due to the location of the site on a slope and the need to use high standards in construction. Consequently, the cost of building the reservoir exceeded the allocated budget in the project resulting in the construction of only one reservoir.  As regards the trees to be planted, a costing constraint was also face by the contractor ARDA which led to the termination of the contract for only 15000 seedlings and the transfer of the maintenance contract to the municipality of Aarsal.

  - Constraints

    - Land ownership: Land ownership is a serious problem in the North Bekaa region.  Selection of land areas for planting trees has been affected by land ownership. The project was faced with the issue of identifying the land owners and getting their approval for the use of the land to construct reservoirs for flood mitigation.  The process of identification of owners is very tedious since these are almost abandoned and un-delimited lands and ownership has been passed from generation to generation without clear documentation.   The process of approval has also taken its toll on time.  The concept of flood mitigation is new in the area.  Accordingly it took a certain length of time to explain to owners the objectives of the project in order to acquire the acceptance of some of them.

    - Overgrazing:  The selection of planting sites has been strongly influenced by the capacity of the municipality of Aarsal to protect the planted areas from grazing herds.  Aarsal has the largest herd of sheep and goats in Lebanon.  Overgrazing is a major problem.  Plots were selected close to Aarsal with a possibility to be viewed and wardened from the village.  Far areas could not be planted because the municipality did not have enough capacity to guard the planted trees.

    - Availability of Data:   the design of flood risk management structure depends on the availability of weather data.  The lack of weather stations in the regions of Ras Baalback and Aarsal resulted in the need to use statistical modelling to develop the data needed in flood modeling.

    - Capacity of contractors:  The design of the water harvesting pond in Deir el Ahmar is almost unique in Lebanon and does not follow the usual design criteria used commonly for ponds in Lebanon.  The design most commonly used is a dug area of land covered with a lining membrane. The design of Deir el Ahmar is, first, unique in the fact that the pond is located on a slope and not in flat lands and this to ensure gravity feed for irrigation and second, the specification include drainage layers on slopes made of porous concrete and gravel. These drainage layers serve to protect the membrane and increase the time that the water is conserved in the pond in case of membrane failure. The design also includes a 13m by 170m dam structure.  The uniqueness of the design and the fact that it has not been done before by contractors has had a major impact on the execution schedule and the need for very close supervision by the PMU and coordination between the contractor and the consultant who has designed the reservoir.

  - Monitoring of Project Implementation

The project was monitored by the UNDP Energy and Environment programme staff directly and continuously and followed-up by the Ministry of Agriculture.

  - Development Impact

    - The project is mainly divided into three main components: flood risk reduction, water harvesting and irrigation, increased green cover.

    - The flood risk reduction component will reduce the risk of flood in the villages of Aarsal and Fakeha.  The direct cost of a flood event as estimated in the region by the Higher Relief Commission is 2.5 Million dollars.  Indirect costs have not been quantified and these are soil erosion, reduced livelihoods, loss of biodiversity and social disturbance. Flood reduction structures are permanent structures that will provide services beyond the project lifetime

    - The water harvesting component will provide irrigation water to around 50 ha of land.  These lands were previously left barren. The lands will be mainly planted with vines for wine.   Viticulture requires only two years of irrigation allowing for the plant to get established. After the first two years the irrigation system can be moved to irrigate another 50 ha and consequently over the lifetime of the pipes (10 years) the system will lead to the agriculture development of 250 ha and over the lifetime of the reservoir (assumed 30 years, can lead to the irrigation of 750 ha

    - The green cover component will lead to reduced soil erosion, increased infiltration rate of rainfall and reduced overland flow and floods.  Growing trees will help in sequestering carbon and ultimately and if properly managed, can produce biomass for energy production.  If left undisturbed the green cover will naturally expand due to natural propagation.

  - Cross-sectoral Impact

    - The project will help reduce poverty through reduction of flood risk and its impact on loss of livelihoods.  A flood event causes destruction of orchards and planted land, floods houses, destroys property, causes soil erosion and consequently reduces the capacity of land to be planted.  The damages caused by floods have heavy setbacks on the pockets of local communities.  Livelihoods take time to recover specially for those relying on agriculture for income.  The irrigation component of the project will help in creating a new income stream for around 300 farmers in Deir el Ahmar.  Because of the new availability of water, barren land can now become cultivated and produce income to the owners.

    - The project is balanced in terms of the negative impact of floods and the positive impact of mitigation measures.  Both genders are affected.   Farms are tended for by both women and men. The costs of damage to agriculture are borne by both sexes.

    - In terms of the impact on environment the project leads to the reduction of soil erosion, improved water recharge and storage in aquifers from the water accumulated in reservoirs after flood events. increased carbon sequestration

  - Sustainability

The main outputs of the flood project are the construction of infrastructure related to water harvesting and flood risk reduction and the increasing of green cover.  The sustainability of the infrastructure depends on maintenance.   For the flood reservoirs, maintenance consists of removal of sediments that might have accumulated after flood events.  UNDP has provided the Municipality of Aarsal with a large size excavator to undertake the removal of the sediments.  The Municipality of Aarsal has started undertaking maintenance works for the different reservoirs.

As for the irrigation reservoir, the agriculture cooperative of Deir el Ahmar charges a fee for water usage. This fee will be used to undertake maintenance works as per the maintenance program developed by UNDP and the consultant responsible for the design of the reservoir.

The flood and irrigation reservoirs are vital structures that either provide protection from loss of livelihoods from floods or generate income from agriculture.  It is in the best economic interest of the population to keep the structures functional.

The rational behind the green cover is to reduce floods through the minimization of overland flow.  At the present, the municipality of Aarsal is working on the maintenance of the already existing seedling stand and is convinced of the need to expand its green cover in order to stop soil erosion and increase water infiltration.  The village of Aarsal will benefit from increased water availability as it is situated in an arid region with very low precipitation volumes and where every drop of water counts.

  - Beneficiaries

For the flood component, the beneficiaries of this project are the villages and populations of Aarsal (35,000 people), Fakeha (17,000) and the surroundings of the Orontes (Aassi) River.  The project has also served, in terms of its outputs and lessons learned, to improve the design of the flood risk project in Ras Baalback and Qaa. For the water harvesting component the beneficiaries are more than 300 farmers in Deir el Ahmar

  - Feedback from recipients/stakeholders

The feedback from the recipients has been very positive.  This was ascertained during the visits undertaken by the evaluator assigned by the LRF for the extension request of Flood II.

The famers of Deir el Ahmar have immediately started connecting their drip lines to the irrigation mains and using the water for irrigation.

- Conclusions and Recommendations

  - Lessons learned

The lessons learned from the project are multiple.  The project has helped create flood management expertise at the level of the project staff.  The PMU has become experienced in the design and construction of flood mitigation structures be they walls, reservoirs or green cover. The flood staff is also undertaking evaluation of flood impacts further to flood events. These evaluations have helped improve the design of flood structures.  The PMU has also become proficient in the design and construction of water harvesting reservoirs of different sizes and construction configuration.

Lessons learned from Flood I have informed and influenced the design of structures for Flood II.  The location, shape, and overall design of the reservoirs and walls have been improved based on the experience in Flood I.

The experience generated in the project has been put at the disposal of the UNDP Disaster Risk Management project.  The project staff have supported the development of SOPs for flood response and   has participated actively in the different activities of the DRM project.

  - Recommendations

- Undertake a national assessment of flood risk areas and develop a flood risk map for Lebanon covering flash and riverine floods.

- Select priority watersheds and implement flood mitigation projects

- Develop a national water harvesting strategy

- Construct new water harvesting reservoirs

- Improve weather data collection in order to improve the design of flood and water harvesting structures

Annexes

Annex 1

List of established reservoirs

| Pond | location | Pond capacity (m3) |
| --- | --- | --- |
| 4 | Wadi Zaarour | 45000 |
| 7 | Wadi Zaarour | 106000 |
| 8 | Wadi Al dam | 23000 |
| 10 | Wadi Al dam | 32000 |
| 11 | Wadi Hmeed | 54000 |
| 13 | Mrah Al Cheikh | 134000 |
| 16 | Wadi Al-Hosn | 24000 |
| 17 | Wadi Arnab | 16000 |

Final list of established walls and performed modifications

| Structure No. | Structure Type | Planned Volume | As Built volume | Remarks |
| --- | --- | --- | --- | --- |
| 1 | stone wall | 55 | 64 | constructed and accepted |
| 2 | stone wall | 13 | 15 | constructed and accepted |
| 3 | repair wall | 75 | 77 | constructed and accepted |
| 4 | stone wall | 4 | 6 | constructed and accepted |
| 5 | stone wall | 43 | 43 | constructed and accepted |
| 6 | check dam | 22 | 23 | constructed and accepted |
| 7 | stone wall | 80 | 84 | constructed and accepted |
| 8 | stone wall | 6.5 | 74 | constructed and accepted |
| 9 | check dam | 14 | 15 | constructed and accepted |
| 10 | stone wall | 45 | 45 | constructed and accepted |
| 11 | stone wall | 19 | 19 | constructed and accepted |
| 12 | stone wall | 30 | 40 | constructed and accepted |
| 13 | stone wall | 30 | 30 | constructed and accepted |
| 14a | check dam | 16 | 16 | constructed and accepted |
| 14b | stone wall | 20 | 20 | constructed and accepted |
| 15 | check dam | 8 | 46 | constructed and accepted |
| 17 | stone wall | 39 | 20 | constructed and accepted |
| 19 | stone wall | 120 | 123 | constructed and accepted |
| 20 | stone wall | 16 | 16 | constructed and accepted |
| 21 | stone wall | 56 | 60 | constructed and accepted |
| 22 | check dam | 46 | 50 | constructed and accepted |
| 23 | stone wall | 32.5 | 31.5 | constructed and accepted |
| 24 | check dam | 5 | 5 | constructed and accepted |
| 25 | stone wall | 49 | 50 | constructed and accepted |
| 27 | check dam | 11.5 | 15 | constructed and accepted |
| 28 | stone wall | 51 | 53 | constructed and accepted |
| 33 | Trench | 11 | 15 | accepted and excavated |
| 34a | repair wall | 42 | 43 | constructed and accepted |
| 34b | Gabion | 100 | 119 | constructed and accepted |
| 34c | repair wall | 13 | 15 | constructed and accepted |
| 35 | check dam | 11 | 15 | constructed and accepted |
| 36 | stone wall | 35 | 39 | constructed and accepted |
| 37 | stone wall | 115 | 118 | constructed and accepted |
| 38 | stone wall | 180 | 182 | constructed and accepted |
| 39 | stone wall | 190 | 213 | constructed and accepted |
| 40 | stone wall | 67.5 | 70 | constructed and accepted |
| 41 | check dam | 28 | 30 | constructed and accepted |
| 42 | Gabion | 112.5 | 129 | constructed and accepted |
| 43a | Road | 0 | 0 | done and accepted |
| 43b | check dam | 27 | 29 | constructed and accepted |
| 44 | stone wall | 23 | 22 | constructed and accepted |
| 45 | stone wall | 10.5 | 14 | constructed and accepted |
| 46 | stone wall | 60 | 124 | constructed and accepted |
| 47 | check dam | 46 | 55 | constructed and accepted |
| 48 | stone wall | 20 | 0 | merged with another structure |
| 49 | stone wall | 135 | 152 | constructed and accepted |
| 50 | stone wall | 40.5 | 40 | constructed and accepted |
| 51 | stone wall | 20 | 23 | constructed and accepted |
| 52 | stone wall | 15 | 15 | constructed and accepted |
| 53 | stone wall | 30 | 31.5 | constructed and accepted |
| 55 | repair wall | 20.5 | 21 | constructed and accepted |
| 56 | stone wall | 30 | 30 | constructed and accepted |
| 58 | stone wall | 18 | 0 | merged with another structure |
| 59 | stone wall | 18 | 0 | merged with another structure |
| 60 | repair wall | 11 | 31 | constructed and accepted |
| 61 | stone wall | 13 | 13.5 | constructed and accepted |
| 62 | Gabion | 60 | 75 | constructed and accepted |
| 63 | Gabion | 12 | 8 | constructed and accepted |
| 64 | stone wall | 125 | 119 | constructed and accepted |
| 65 | repair wall | 65 | 65 | constructed and accepted |
| 66 | check dam | 9 | 20 | constructed and accepted |
| 67 | Gabion | 25 | 27 | constructed and accepted |
| 68 | stone wall | 16 | 17 | constructed and accepted |
| 69 | repair wall | 21 | 26.5 | constructed and accepted |
| 70 | stone wall | 44 | 51 | constructed and accepted |
| 73 | stone wall | 90 | 90 | constructed and accepted |
| 75 | stone wall | 32.5 | 33 | constructed and accepted |
| 80a | repair wall | 120 | 136 | constructed and accepted |
| 80b | stone wall | 49 | 80 | constructed and accepted |
| 82 | check dam | 9 | 11 | constructed and accepted |
| 88 | repair wall | 21 | 32 | constructed and accepted |
| 89 | stone wall | 79 | 80 | constructed and accepted |
| 92 | Gabion | 30 | 67 | constructed and accepted |
| 93 | stone wall | 25 | 30 | constructed and accepted |
| 94 | Gabion | 25 | 45 | constructed and accepted |
| 95 | stone wall | 15 | 105 | constructed and accepted |
| 96 | Gabion | 139 | 139 | constructed and accepted |
| 97a | stone wall | 30 | 30 | constructed and accepted |
| 97b | Gabion | 7 | 10 | constructed and accepted |
| 97c | stone wall | 57 | 57 | constructed and accepted |
| 98 | Gabion | 150 | 156 | constructed and accepted |
| 99 | check dam | 52 | 55 | constructed and accepted |
| 100 | check dam | 150 | 161 | constructed and accepted |
| 101 | repair wall | 21 | 21 | constructed and accepted |
| 102 | check dam | 21 | 22 | constructed and accepted |
| 103 | check dam | 16 | 52 | constructed and accepted |
| 104 | check dam | 14.5 | 14.5 | constructed and accepted |
| 105 | check dam | 32 | 32 | constructed and accepted |
| 106 | check dam | 13 | 51 | constructed and accepted |
| 107 | check dam | 30 | 30 | constructed and accepted |
| 108 | check dam | 21 | 21 | constructed and accepted |
| 109 | Gabion | 19 | 36 | changed to check dam |
| 110 | Gabion | 20 | 84 | constructed and accepted |
| 111 | check dam | 10 | 34 | constructed and accepted |
| 112 | stone wall | 10 | 45 | constructed and accepted |
| 113 | repair wall | 85 | 85 | constructed and accepted |
| 114 | repair wall | 22 | 23 | constructed and accepted |
| 115 | stone wall | 48 | 48 | constructed and accepted |
| 116 | stone wall | 84 | 84 | constructed and accepted |
| 117 | stone wall | 37 | 37 | constructed and accepted |
| 118 | stone wall | 30 | 30 | constructed and accepted |
| 119 | Gabion | 37.5 | 37.5 | constructed and accepted |
| 120 | check dam | 29 | 67 | constructed and accepted |
| 121 | check dam | 5 | 20 | constructed and accepted |
| 122 | Gabion | 38 | 38 | constructed and accepted |
| 123 | repair wall | 42 | 43 | constructed and accepted |
| 124 | repair wall | 46 | 169 | constructed and accepted |
| 125 | stone wall | 12 | 0 | merged with another structure |
| 126a | repair wall | 32 | 0 | merged with another structure |
| 126b | stone wall | 12 | 0 | merged with another structure |
| 127 | Gabion | 97 | 0 | merged with another structure |
| 128 | Gabion | 13.5 | 0 | merged with another structure |
| 129 | check dam | 37.5 | 41 | constructed and accepted |
| 130 | stone wall | 15 | 18.5 | constructed and accepted |
| 131 | stone wall | 30 | 31 | constructed and accepted |
| 134 | stone wall | 45 | 49 | constructed and accepted |
| 135 | check dam | 48 | 66 | constructed and accepted |
| 136 | check dam | 63 | 73 | constructed and accepted |
| 137 | repair wall | 19.5 | 19 | constructed and accepted |
| 138 | repair wall | 25 | 28 | constructed and accepted |
| 139 | check dam | 13 | 56 | constructed and accepted |
| 141a | Gabion | 13 | 13 | constructed and accepted |
| 141b | repair wall | 10 | 10 | constructed and accepted |
| 143 | check dam | 26 | 52 | constructed and accepted |
| 144 | check dam | 17.4 | 17.4 | constructed and accepted |
| 149 | stone wall | 72 | 75 | constructed and accepted |
| 150 | repair wall | 96 | 146 | constructed and accepted |
| 151 | repair wall | 200 | 205 | constructed and accepted |
| 152 | check dam | 6 | 25 | constructed and accepted |
| 153 | check dam | 34 | 70 | constructed and accepted |
| 154 | check dam | 6 | 15 | constructed and accepted |
| 155 | stone wall | 12 | 15 | constructed and accepted |
| 157 | check dam | 15.5 | 36 | constructed and accepted |
| 158 | check dam | 24 | 25 | constructed and accepted |
| 159 | check dam | 10 | 10 | constructed and accepted |
| 160 | stone wall | 16 | 17 | constructed and accepted |
| 161 | stone wall | 112 | 114 | constructed and accepted |
| 162 | stone wall | 10 | 12 | constructed and accepted |
| 163 | stone wall | 7 | 10 | constructed and accepted |
| 164 | stone wall | 6 | 6 | constructed and accepted |
| 165 | stone wall | 11 | 11 | constructed and accepted |
| 166 | check dam | 66 | 69 | constructed and accepted |
| 167 | check dam | 4 | 22 | constructed and accepted |
| 168 | check dam | 40.5 | 96 | constructed and accepted |
| 169 | stone wall | 20 | 21 | constructed and accepted |
| 170 | Gabion | 44 | 52 | constructed and accepted |
| 172 | check dam | 15 | 18 | constructed and accepted |
| 173 | stone wall | 66 | 72 | constructed and accepted |
| 174 | stone wall | 132 | 142 | constructed and accepted |
| 175 | check dam | 10.5 | 14 | constructed and accepted |
| 176 | stone wall | 10 | 26 | constructed and accepted |
| 177 | check dam | 42 | 43.5 | constructed and accepted |
| 178 | check dam | 41 | 46 | constructed and accepted |
| 179 | Gabion | 17 | 18 | constructed and accepted |
| 180 | Gabion | 28 | 29 | constructed and accepted |
| 181 | Gabion | 8 | 12.5 | constructed and accepted |
| 182 | Gabion | 36 | 49 | constructed and accepted |
| 183 | check dam | 14 | 16 | constructed and accepted |
| 184 | check dam | 39 | 44.5 | constructed and accepted |
| 185 | stone wall | 15 | 16 | constructed and accepted |

Annex 2 Photos

| Check Dam | Contour stone wall |
| --- | --- |
| Stone Check Dam | Stone Wall |
| Gabion construction | Gabion filling with stone |
| Gabion | Gabion |
| Sediment trap | Contour Wall with wings |

Annex 2: Maps of All Beneficiary Sites

# Footnotes

Priority Area for the Peacebuilding Fund; Sector for the UNDG ITF.

The start date is the date of the first transfer of the funds from the MDTF Office as Administrative Agent. Transfer date is available on the MDTF Office GATEWAY (http://mdtf.undp.org).

Poverty, gender and environment are internationally agreed cross-sectoral issues.