MDG-F Croatia Quarterly Progress Report – Y1/Q4 as of April 2010

Part I: Color-coded Work Plan for Closing the Chapter: Social Inclusion and Conflict Transformation in War Affected Areas of Croatia

Period (Covered by the WP)    April 2009 – April 2010

Color Code Key:

Completed

On track

Delayed/Cancel

| - JP Outcomes: - National policy coordination on conflict prevention, reconciliation and recovery strengthened - Enhanced community integration, safety & social cohesion - Enhanced socio-economic recovery of areas of Special State Concern |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UN organization-specific Annual targets | UN organization | Activities | TIME FRAME |  |  |  | Implementing Partner | PLANNED BUDGET |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| JP Output 1.1. Establishment of a coordination mechanism for regional development of war affected areas and violence prevention / safety mechanisms under Vice Prime Minister |  |  |  |  |  |  |  |  |  |  |
| At least 4 regional development & conflict prevention coordination meetings held annually, refugees/returnees legal cases resolved | UNDP | Facilitation of regular quarterly co-ordination meetings, legal cases review and assistance provided | X | X | X | X | Vice-Prime Minister’s Office | MDGF | Personnel I (staff) Personnel II (legal advisor) – 50% JP manager - 25% Formulation advance | 35,000 15,500 53,000 20,000 |
| Victims and witnesses provided support and protection | UNDP | Develop national policy and implementation mechanisms on victims rights and witness support |  | X | X | X | Ministry of Justice, Ministry of Interior | MDGF | Contracts (Court Administration salaries) Public Awareness services Personnel (travel) NGO training services M&E / Communications | 78,000 21,000 2,500 16,200 3,000 Total: 244,200 |

| JP Output 1.2. Support to the implementation of fundamental rights for returnees |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Regular quarterly coordination meetings on the implementation of the Law on Free Legal Aid; capacity building provided for NGOs for the provision of legal advice/aid under the Law; and resolved remaining ‘open issues’ on the Law on Free Legal Aid | UNHCR | Facilitation of meetings on the implementation and analysis of the shortcomings of the Law; On-the-job training for NGO’s providing legal aid; Co-ordination of the cross-border reintegration activities | X | X | X | X | Vice-Prime Minister’s Office, Ministry of Justice, Legal NGOs and legal experts | MDGF | Personnel (legal advisor) – 50% Logistics, transport, event mngt. services Personnel (travel) Training of counterparts M&E / Communications | 15,500 8,300 7,000 40,000 2,000 Total 72,800 |
| JP Output 2.1. Enhanced ability of local population to plan and realize Safe Community Plans in conjuncture with Community Policing |  |  |  |  |  |  |  |  |  |  |
| Crime-tackling projects identified, supported and initiated through Crime Prevention Councils in 5 medium-size urban / semi-urban locations with a focus on areas of return and counties with the highest level of armed crime per capita | UNDP | Development and improvement of the Safe Community Plans; Capacity building for Community Police in mediation, communication, negotiation, conflict resolution and community dialogue | X | X | X | X | Council for Communal Violence Prevention, Ministry of Interior – police, Local authorities, Women’s and Youth NGOs, | MDGF | Logistics, transport, event mngt. services Contracts (works & services) M&E / Communications | 2,000 96,500 2,000 Total: 100,500 |

| JP Output 2.2. War veterans’ and women’s associations enabled to actively support conflict prevention activities, rehabilitate and reintegrate communities in Areas of Special State Concern (ASSC) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Local level partnerships established to identify appropriate institutional arrangement for delivery of psycho-social and employment services; Network of regional/local veterans associations’ branches established and trained to provide psychosocial and employment services | IOM | Facilitation of the organization of a system of psychosocial and employment support services for veterans; development of vocational profiles and introduction of employment opportunities; provision of support to veterans’ associations and NGOs through conflict resolution and management training; improved access to business support services, counselling and job-search services |  | X | X | X | Ministry of Family, War Veterans and Intergeneration Solidarity Regional and local authorities Veteran’s NGOs | MDGF | Personnel I (Conflict resolution) Personnel II (Support staff/assistance) Contracts Training Contracts (Counselling services) M&E / Communications | 15,000 6,000 10,000 18,000 10,000 11,200 |
| Women-owned joint projects centered on awareness raising of gender issues and particular needs of marginalized and vulnerable groups; Improved access for women to leadership and decision-making positions in targeted communities | IOM | Assistance provided in technical development of project proposals and implement partnership projects (in direct link to Output 3.4) Training provided for women (organizations) in conflict prevention, reconciliation and peace building. | X | X | X | X | Ministry of Family, War Veterans and Inter-Generational Solidarity; Office for Gender Equality & Gender Task Force Regional and local authorities; Women’s NGOs. | MDGF | Personnel I (Gender coordinator expert) Personnel II (assistant) Other direct costs Contracts (Women NGO) Training of counterparts Personnel (Conflict prevention) M&E / Communications | 15,000 12,000 9,800 12,000 19,300 10,000 1,000 Total: 149,300 |

| JP Output 2.3. Protection of children & youth from peer violence & bullying in schools |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Violence prevention mechanisms introduced, implemented and coordinated | UNICEF | Integration of violence prevention and conflict resolution content into school quality standards | X | X | X | X | Ministry of Science, Education and Sports, Teachers’ Training Agency | MDGF | Personnel (Consultants) | 13,300 |
| Training program established and implemented; Teachers and parents educated on prevention, recognition and reaction to violence; National Network of ‘Violence-Free’ Schools meets annually and regional branches twice a year; | UNICEF | Development of training programme and direct implementation in 140 schools; educating pupils, teachers, parents and communities on how to prevent and/or recognize and react to violence/conflict; Development and strengthening of National Network of Violence-free Schools, with five regional branches | X | X | X | X | Ministry of Science, Education and Sports Education and Teachers Training Agency | MDGF | Personnel I (Edu. program in schools) Personnell II Contracts (design & print services) Contracts (Coordination of Networks of VFS) Supplies & field travel M&E / Communications | 40,000 13,000 35,450 38,000 2,000 1,000 Total. 142,750 |
| JP Output 2.4. Development of conflict resolution skills amongst grassroots groups, women and municipal/county authorities; |  |  |  |  |  |  |  |  |  |  |
| Targeted communities supported in development of conflict resolution and leadership skills, and reconciliation mechanisms, linked to projects | UNHCR | Provision of leadership training for local stakeholders and facilitation of joint definition of small-scale development projects | X | X | X | X | Vice-Prime Minister’s Office; Regional and local authorities; | MDGF | Contracts (leadership training) Contracts (Peace-building forum) Contracts (10 small community projects) M&E / Communications | 25,000 35,000 228,400 4,000 Total: 292,400 |

| JP Output 3.1. Capacity Development of local authorities, communities and regional development agencies to plan, prioritize and deliver projects for their communities |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| At least 4 training events organized on various aspects of development policy planning, financing and implementation, with special focus on the inclusion of vulnerable groups into the decision making mechanism; Direct on-the-job training provided for at least 12 regional and local development institutions provided | UNDP | Provision of raining for local authorities, communities and regional development agencies in conflict sensitive project development, management, implementation and fundraising for EU funds Provision of training of local/regional authorities on outsourcing social and communal services |  |  | X | X | Vice-Prime Minister’s Office Ministry of Regional Development, Forestry and Water Management Local and regional authorities Regional Dev. Agencies | MDGF | Personnel I (Training activity coordinator) 25% Contracts (trainers) Contracts (events) M&E / Communications | 10,000 24,200 6,000 500 Total: 40,700 |
| JP Output 3.2. Immediate support and provision of services to refugees, returnees and vulnerable populations in remote areas prior to their inclusion in national social protection schemes |  |  |  |  |  |  |  |  |  |  |
| Central and local coordination of social welfare providers established; Grass-roots volunteer initiatives strengthened and functional | UNHCR | Regular quarterly meetings on the local level organized to improve coverage of social services providers and identify solutions for vulnerable cases. Training, workshops and coaching for CRC teams and their volunteers’ programmes in the areas of return through training workshops and coaching. | X | X | X | X | Vice-Prime Minister’s Office; Ministry of Regional Development, Forestry and Water Management; Ministry of Health and Social Welfare; Croatian Red Cross; Local and regional authorities; NGOs providing care | MDGF | Training of counterparts (social services and care providers) Contracts (Support to operation of CRC mobile teams and local volunteers) Training of counterparts (volunteers) M&E / Communications | 8,800 76,000 19,710 1,000 Total: 105,510 |

| JP Output 3.3. Job creation and business development benefiting returnees, women, youth, elderly, war veterans |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| At least 40 co-operatives / associations in target area improve their business processes and access to market and finance Established or strengthened eight business support services At least 15 SMEs in target area increase employment and demand for local basic products through new investment |  | UNDP | Training and technical assistance to business development services for local businesses and agricultural cooperatives to scale up core business Competitive financing packages for medium-sized businesses including support for commercial lending, state incentives and guarantees, and 10-15% grants |  | X | X | X | Ministry of Economy and Ministry of Tourism Vice-Prime Minister’s Office Ministry of Regional Dev. Regional Dev. Agencies | MDGF | Personnel (Trainers/experts) Contracts (Small works and equipment contracts Contracts (Direct support / financing packages) M&E / Communications | 25,000 72,000 183,000 3,000 Total: 283,000 |
| 3.4. Community-identified sub-projects implemented to enhance the connectivity of divided communities and associated business development |  |  |  |  |  |  |  |  |  |  |  |
| At least 12 new objects of community, social or business infrastructure established or reconstructed At least 10 sets of project (technical) documentation prepared for submission to other sources of funding |  | UNDP | Joint identification and preparation of project documentation in areas of return to qualify for further funding from other sources i.e. IPA, WB, Government Small primary community infrastructure and other sub-project interventions for conflict affected communities |  | X | X | X | Ministry of Regional Development, Forestry and Water Management Vice-Prime Minister’s Office Local and regional authorities | MDGF | Contracts (works and services) M&E / Communications | 260,000 3,000 Total: 263,000 |
| Total Planned Budget |  |  |  |  |  |  |  |  |  |  | 1,694,160 |
| Including* | Total UNDP: 931,400 |  |  |  |  |  |  |  |  |  |  |
|  | Total UNHCR: 470,710 |  |  |  |  |  |  |  |  |  |  |
|  | Total IOM: 149,300 |  |  |  |  |  |  |  |  |  |  |
|  | Total UNICEF: 142,750 |  |  |  |  |  |  |  |  |  |  |

Part II: MDGF – Croatia Estimated delivery and committed funds by UN Agency

as of 15.April 2010.

| UN Agency | Funds Received 2009 | committed | expenditure | est. Delivery as of APR 2010 |
| --- | --- | --- | --- | --- |
| UNDP | 931,400 |  | 799,087.65 | 85.79% |
| UNHCR | 470,710 |  | 406,930.00 | 86.45% |
| IOM | 149,300 |  | 116,600.00 | 78.10% |
| UNICEF | 142,750 |  | 108,000.00 | 75.66% |
|  |  | AVG Delivery Rate |  | 81.50% |