Joint Programme Monitoring Report: Conflict Prevention and Peace Building

Section I: Identification and Joint Programme Status

a. Joint Programme Identification and basic data

| Date of Submission: 25 July 2010 Submitted by: RC Office Afghanistan Name: Robert Watkins Title: Deputy SRSG/RC/HC Organization: UNAMA Contact information Watkins@un.org |  | Country and Thematic Window Afghanistan Justice and Human Rights |
| --- | --- | --- |

| MDTF Atlas Project No: 00071109 Title: Peace through Justice |  | Report Number: 1 Reporting Period: January to June 2010 Programme Duration: 2.5 years Official starting date: 1 January 2010 |
| --- | --- | --- |

| Participating UN Organizations UNDP, UNAMA, UNICEF, UNODC and UNIFEM |  | Implementing partners Children in Crisis; Legal Aid Forum of Aghanistan; International Legal Forum of Afghanistan; others are TBA – process to finalize hiring of NGOs and prívate construction companies that will implement legal awareness and rehabilitation of facilities activities is still on-going |
| --- | --- | --- |

The financial information reported should include overhead, M&E and other associated costs.

| Budget Summary |
| --- |
| Total Approved Joint Programme Budget | UNDP: $5,663,288 UNICEF: $155,150 UNIFEM: $521,062 UNODC: $160,500 Total: $6,500,000 |
| Total Amount of Transferred to date | UNDP: $2,937,345 UNICEF: $104,860 UNIFEM: $281,396 UNODC: $85,600 Total |
| Total Budget Committed to date | UNDP: $2,937,347 UNICEF: $104,860 UNIFEM: $281,396 UNODC: $85,600 Total: |
| Total Budget Disbursed to date | UNDP:311,134 UNICEF: - UNIFEM: - UNODC: - Total: 311,134 |

BENEFICIARIES

Direct Beneficiaries: “The individuals, groups, or organizations, targeted, that benefit, directly, from the development intervention”.

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Institutions | 6 | 6 |  |  |  |  |  |  |
| Local Institutions | 10 |  | 1140 | 3360 |  |  |  |  |
| Urban |  |  |  |  |  |  |  |  |
| Rural | 5 |  | 18000 | 42000 |  |  |  |  |
| Total | 21 | 6 | 19140 | 45360 |  |  |  |  |

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Institutions |  |  |  |  |  |  |  |  |
| Local Institutions | 3 |  |  |  |  |  |  |  |
| Urban |  |  |  |  |  |  |  |  |
| Rural | 2 |  |  |  |  |  |  |  |
| Total | 5 |  |  |  |  |  |  |  |

Indirect Beneficiaries: “The individuals, groups, or organizations, not targeted, that benefit, indirectly, from the development intervention”

- Joint Programme M&E framework

The Programme cannot at this stage provide information on the value for the indicators in many areas until a baseline assessment is carried out. A consultant to do this work has been hired and should commence work in August. Information on the value for indicators will therefore, be provided in the next reporting period.

| Expected Results (Outcomes & outputs) | Indicators | Baseline | Overall Expected Target | Achievement of Target to date | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 - Local community capacity to understand the justice system, demand access to justice, and protect its vulnerable members’ rights is strengthened | Indicator: Number of participants in training courses and awareness raising activities, desegregated by location and gender. |  |  |  | Project progress reports, Awareness raising program reports | Quarterly from implementing partners | UNDP, UNIFEM, UNICEF | De functioning of justice sector due to security situation in some provinces |
| Joint Output 1 - Community members have a greater awareness of constitutional and human rights. | Indicator (UNDAF): Number of advocacy and media campaigns launched on the constitutional and legal rights of all citizens Number of districts covered by media campaigns for access to justice and rights awareness . | Baseline: pilot awareness raising activities conducted in some provinces. Some awareness raising resources developed and field tested | In each of 42 districts `12 dramas, 12 panel debates, 24 interviews, 12 talk-back shows, 5 songs, 30 community service broadcasts 21 |  | Project progress reports, Awareness raising program reports | Quarterly from implementing partners | UNDP, UNIFEM, UNICEF | De functioning of justice sector due to security situation in some provinces Risk of raising community expectations which cannot be met by the formal justice system |
| 1.1 Awareness of the general public raised regarding constitutional and human rights in 7 districts in each of 6 provinces | Number of awareness programs conducted Number of people received full information on human rights disaggregated by gender Increase in the percentage of population in target districts who can correctly describe their constitutional and human rights. |  | 60,000 |  | Project progress reports, Awareness raising program reports | Quarterly from implementing partners | UNDP, UNIFEM, UNICEF | Challenges of monitoring implementation due to security situation Limited number of national CSO partners in provinces and districts |
| 1.2. Human rights awareness of young people and their families raised through human rights activities in primary and secondary schools and non-formal classes for out-of-school children and adolescents. | Human rights awareness raising initiatives in place in formal and non-formal schools Number of young people received full information on human rights disaggregated by gender |  | 240 30,000 |  | Project progress reports, Awareness raising program reports | Quarterly from implementing partners | UNICEF, UNIFEM | Challenges of monitoring implementation due to security situation |
| 1.3 Technical advice and inputs into curriculum development, training and monitoring gender components for awareness raising of community members. | Technically sound community awareness materials available |  |  |  | Technical inputs provided by UNIFEM (Reports on technical inputs, awareness raising) | Quarterly | UNIFEM | Community awareness activities are based on assessments and relevant to communities. |
| Joint Output 2. Community representatives and leaders have improved knowledge of human rights and skills to manage disputes. | Indicator: Number of beneficiaries participating in training courses Number of Provincial Councils trained and applying Afghan laws and international obligations in dispute resolution Increase in the proportion of disputes observed during monitoring where Afghan laws and international obligations are correctly applied. | Baseline: pilot human rights awareness activities conducted in some provinces | 840 6 |  | Knowledge level, attitudes and behaviours (project evaluation report) Pre-training and post-training observation by CSO partners. | End of the project Reports from CSO partners | Joint UN program | Challenges of getting community participation and ownership Community leaders allow access to dispute resolution fora for NGO monitoring |
| 2.1. Knowledge of human rights (including women’s rights and the role of the formal justice system) of 840 community representatives and opinion shapers (community leaders, religious leaders, teachers) raised through training conducted in 7 districts of 6 provinces. | Number of awareness programs conducted Number of people received full information on human rights disaggregated by gender |  | 840 |  | Project progress reports, Awareness raising program reports | Quarterly from implementing partners | UNDP, UNIFEM, UNICEF, Government of Afghanistan | Challenges of monitoring implementation due to security situation Challenges of getting community participation and ownership Limited number of CSO partners in provinces and districts |
| 2.2. Community members responsible for dispute resolution (including women and young people) receive paralegal training enabling them to assist other community members with advice and referrals in relation to legal rights and dispute resolution. | Number of community members trained in paralegal disaggregated by gender, province |  |  |  | Project progress reports, paralegal training reports | Quarterly from implementing partners | UNDP, UNIFEM, UNICEF | Challenges of monitoring implementation due to security situation Challenges of getting community participation and ownership |
| 2.3. Capacity of 6 Provincial Councils and 6 local CSOs to monitor and report regarding local dispute resolution fora to promote compliance with Afghan laws and international obligations | Number of provincial council representatives trained in dispute resolution, Afghan law and international obligations Well defined and functioning monitoring and reporting mechanism in place | 6 |  |  | Monitoring activities Training records Reporting formats and completed reports | Quarterly reports from and monitoring CSOs Annual reports from provincial councils. | UNIFEM, UNICEF | Provincial councils are committed in the initiative |
| 2.4 Technical advice and inputs into curriculum development, training and monitoring gender components for community representatives and leaders. | Technically sound, need based training curriculum available |  |  |  | Technical inputs provided by UNIFEM (Reports on technical inputs, training curriculum) | Quarterly | UNIFEM | Training curriculum is based on needs |
| Joint Output 3. Government officials and CSOs demonstrate greater capacity to respond to victims of violence. | Indicator (UNDAF): Number of beneficiaries in human rights and civic education Development and introduction of SOPs dealing with cases of violence against women Increase in the proportion of cases of violence against women where the SOPs are correctly followed in the justice system. | Baseline: pilot activities conducted in some provinces |  |  | Project progress reports, training reports. | Quarterly from implementing partners | UNIFEM | SOPs can be negotiated with stakeholders Stakeholders will support, adopt and implement SOPs |
| 3.1 Capacity of local justice and social service sector CSOs to provide timely and appropriate responses to victims of violence and at-risk children is built. | Level of capacity of CSOs providing timely and appropriate responses to victims |  |  |  | Efficiency, cost effectiveness, trained human resources etc (Performance assessment reports) | Performance assessment at the beginning and end of the project | UNIFEM, UNICEF | Committed organizations are selected Challenges from culture and religious groups |
| 3.2 Standard Operating Procedures to deal with cases of violence against women and children are integrated within the justice system. | SOPs exist and have been adopted by Government institutions |  |  |  | Activity reports | Quarterly progress reports | UNICEF, UNIFEM | Ability of Government institutions to implement the SOPs once developed |
| Outcome 2 -- The professionalism and accountability of district-level formal justice system actors is strengthened. | Indicator: Number of participants in training courses desegregated by institution, location and gender. | Baseline: Some curricula developed and tested in pilot activities conducted in some provinces |  |  | Activity reports Training records | Quarterly | UNDP, UNICEF, UNIFEM, UNODC, Government of Afghanistan |  |

- Joint Programme Results Framework with financial information

|  | JP output: |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
|  | 1.1.1 | 435,490 |  |  |  |  | 435,490 |  | 0 | 0% |
|  | 1.1.2. | 160,500 |  |  |  |  | 160,500 |  | 0 | 0% |
|  | 1.1.3. | 123,051 |  |  |  |  | 123,051 |  | 0 | 0% |
|  | 1.1.4. | 258,940 |  |  |  |  | 258,940 |  | 2,880 | 1% |
|  | 1.1.5. | 1,358,900 |  |  |  |  | 1,358,900 |  | 196,660 | 14% |
|  | 1.1.6. | 600,466 |  |  |  |  | 600,466 |  | 111,594 | 19% |
|  | Total |  | 2937,347 |  | 311,134 | 11% |

SECTION II: Joint Programme Progress

- Narrative on progress, obstacles and contingency measures

Regarding the recruitment of Programme staff, the International Programme Coordinator came on board early March. Interviews for a consultant to carry out a baseline analysis of the programme and the formulation of monitoring and evaluation tools were conducted end of June and the selected candidate is expected to commence work early in the second half of 2010. The Programme is in the process of recruiting candidates for the Deputy National Coordinator, National Regional Coordinators and another International Consultant to review and develop human rights education materials as well conducting train the trainer activities for the Human Rights Education component. UNICEF UNICEF focuses on strengthening the response and referral system for child victims of violence through CPAN, training community workers on basic social work and skills in relation to responding and, referring child victims and strengthening the recording and reporting mechanisms on CPAN caseload: and strengthening the capacity of officials and service providers to provide timely and appropriate responses to victims of violence. An LOA with Children in Crisis in Afghanistan was signed in June to implement CPAN activities in Daikundi and Panjsher and orientation initiatives at the national planned will be conducted in July. A draft publication on CPAN, including guidelines for case planning committees has been completed and is currently being translated into Dari. The process of hiring ILF-A and LAOA to conduct capacity development initiatives of officials and service providers on CPAN is being finalized and LOAs will be signed by July. UNIFEM UNIFEM have been providing invaluable technical support on gender in all the inception processes, including mainstreaming gender in recruitment of a consultant to conduct basement assessment and developing M&E& tools, Request for Proposals for legal awareness activities, architectural designs for justice institutions facilities etc. UNODC UNDOC are focusing on training prison and detention centre officials on the Prison Act and Regulations and international standards on how to handle detainees and prisoners, with particular attention of the rights of women and children. The Agency is finalizing the recruitment of the national coordinator to implement the activities. Measures taken for the sustainability of the joint programme: Although the Joint Programme is still establishing, experience has shown that sustainability of the programme will be achieved through extensive use of local institutions and professionals for purposes of skills transfer and capacity development. Against this background, the Peace through Justice (PtJ) is currently recruiting a National Deputy Programme Coordinator and national regional coordinators to work alongside the International Programme Coordinator. Further, implementation of activities will be done largely through national organizations. The programme has been involving government counterparts in all stages of the inception phase and processes (that include recruitment and procurement, joint coordination meetings, planning, field missions etc) as a way of creating ownership of the programme and transferring skills to ensure sustainability.

Are there difficulties in the implementation? What are the causes of these difficulties? Please check the most suitable option

b.

UN agency Coordination

Coordination with Government

Coordination within the Government (s)

Administrative (Procurement, etc) /Financial (management of funds, availability, budget revision, etc)

Management: 1. Activity and output management 2. Governance/Decision making (PMC/NSC) 4. Accountability

Joint Programme design

c.

External to the Joint Programme (risks and assumptions, elections, natural disaster, social unrest, etc)

Other.  Please specify:

- Please, briefly describe (250 words) the current difficulties the Joint Programme is facing. Refer only to progress in relation to the planned in the Joint Program Document. Try to describe facts avoiding interpretations or personal opinions.

- Please, briefly describe (250 words) the current external difficulties (not caused by the joint programme) that delay implementation. Try to describe facts avoiding interpretations or personal opinions.

Please, briefly explain (250 words) the actions that are or will be taken to eliminate or mitigate the difficulties (internal and external referred B+C) described in the previous text boxes b and c. Try to be specific in your answer.

- Inter-Agency Coordination and Delivering as One

- Is the Joint Programme still in line with the UNDAF? Please check the relevant answer

Yes No

- If not, does the Joint Programme fit into the national strategies?

Yes No

If not, please explain:

What types of coordination mechanisms and decisions have been taken to ensure joint delivery?

Are different joint programmes in the country coordinating among themselves? Please reflect on these questions above and add any other relevant comments and examples if you consider it necessary:

Please provide the values for each category of the indicator table described below:

| Indicators | Baseline | Current Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| Number of managerial practices (financial, procurement, etc) implemented jointly by the UN implementing agencies for MDG-F JPs. |  |  |  |  |
| Number of joint analytical work (studies, diagnostic) undertaken jointly by UN implementing agencies for MDG-F JPs. |  |  |  |  |
| Number of joint missions undertaken jointly by UN implementing agencies for MDG-F JPs. |  |  |  |  |

Please provide additional information to substantiate the indicators value (150 words). Try to describe qualitative and quantitative facts avoiding interpretations or personal opinions.

- Development Effectiveness: Paris Declaration and Accra Agenda for Action

Ownership: Partner countries exercise effective leadership over their development policies, and strategies and co-ordinate development actions

Are Government and other national implementation partners involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the government involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Who leads and/or chair the PMC and how many times have they met?

Institution leading and/or chairing the PMC GoAf/ RCO_____         Number of meetings.

Is civil society involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the civil society involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Are citizens involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are citizens involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Where is the joint programme management unit seated?

National Government  Local Government  UN Agency  By itself  other, specify

Based on your previous answers, briefly describe the current situation of the government, civil society, private sector and citizens in relation of ownership, alignment and mutual accountability of the joint programmes, please, provide some examples. Try to describe facts avoiding interpretations or personal opinions.

- Communication and Advocacy

Has the JP articulated an advocacy & communication strategy that helps advance its policy objectives and development outcomes?  Please provide a brief explanation of the objectives, key elements and target audience of this strategy, if relevant, please attach (max. 250 words).

Yes

No X

What concrete gains are the advocacy and communication efforts outlined in the JP and/or national strategy contributing towards achieving?

Increased awareness on MDG related issues amongst citizens and governments

Increased dialogue among citizens, civil society, local national government in relation to

development policy and practice

New/adopted policy and legislation that advance MDGs and related goals

Establishment and/or liaison with social networks to advance MDGs and related goals

Key moments/events of social mobilization that highlight issues

Media outreach and advocacy

Others (use box below)

What is the number and type of partnerships that have been established amongst different sectors of society to promote the achievement of the MDGs and related goals? Please explain.

Faith-based organizations     	Number

Social networks/coalitions    	Number

Local citizen groups                	Number

Private sector 		      	Number

Academic institutions              	Number

Media groups and journalist   	Number

Others (use box below)          	Number

What outreach activities do the programme implement to ensure that local citizens have adequate access to information on the programme and opportunities to actively participate?

Focus groups discussions

Household surveys

Use of local communication mediums such as radio, theatre groups, newspapers, etc

Open forum meetings

Capacity building/trainings

Others

Section III: Millennium Development Goals

- Millennium Development Goals

| MDG 3 | Joint Programme Outcome 1 | MDG Target 3.A | # Beneficiaries reached | MDG Indicators | JP Indicator |
| --- | --- | --- | --- | --- | --- |
| Goal 3: Promote gender equality and empower women |  |  |  |  |  |
|  | Joint Programme Outcome 2 | MDG Target 3 B |  | Indicator | JP Target |
|  | Joint Programme Outcome 3 | MDG Target 3 C |  | Indicator | JP Target |
|  |  | Does not apply |  |  |  |

Additional Narrative comments

Please provide any relevant information and contributions of the programme to the MDGs, whether at national or local level.

Please provide other comments you would like to communicate to the MDG-F Secretariat:

Section 4: General Thematic Indicators

| Type/number of new mechanisms (supported by the joint programme) that respond to popular demands/dissatisfaction related to existing and/or potential sources of conflict (i.e. denial of rights, urban violence, discrimination, etc.) Applies Does not apply. if so, please move forward to section 2 |
| --- |
| Policies Laws Plans Forums/roundtables Working groups Dialog clubs Cooperation agreements Other, pls. specify: | No. National No. National No. National No. National No. National No. National No. National No. National | No. Regional No. Regional No. Regional No. Regional No. Regional No. Regional No. Regional | No. Local No. Local No. Local No. Local No. Local No. Local No. Local No. Local |
| Please briefly provide some contextual information on the above mentioned mechanisms and the country/municipality where it will be implemented (base line, stage of development and approval, potential impact): |
| Number of citizens benefiting from the above mentioned mechanisms to channel their concerns: Applies Does not apply |
| Total No. Citizens Youth under the age of 25 years IDPs/refugees other, pls. specify: | Total No. ( % of ethnic groups ) Total No. Total No Total No Total No | Total Women Men Urban Urban Urban Urban | Total Women Men Rural Rural Rural Rural |

| Number of local and/or community plans for violence prevention implemented targeted to: Total No. Youth No. ( % of ethnic groups ) Women No. ( % of ethnic groups ) Ethnic groups No. other, pls. specify: No. ( % of ethnic groups ) | Comments |
| --- | --- |

| Number of organizations and individuals with strengthened capacity in the following areas: |  |
| --- | --- |
| Violence prevention/conflict Conflict mediation Conflict resolution Resolution and settlement of disputes Cooperation agreements Create dialogue | Religion leaders No. ( % of ethnic groups ) Community leaders No. ( % of ethnic groups ) Citizens: women # men No. ( % of ethnic groups ) Judges No. ( % of ethnic groups ) Policeman No. ( % of ethnic groups ) Civil servants No. ( % of ethnic groups ) Government representatives No. ( % of ethnic groups ) Youth organizations No. ( % of ethnic groups ) Community based organizations No ( % of ethnic groups ) |

| Number and type of violent incidents reported in the area of intervention through formal and informal channels: | Comments |
| --- | --- |
| Social incidents (e.g. riots) No. Crime (Theft, etc) No. Ethnic groups related No. Other, pls. Specify No. |  |

# Footnotes

Please list all the partners actually working in the joint’s programme implementation, NGOs, Universities, etc

# Text boxes

Progress in outcomes: The programme is just starting implementation and the full developmental impact will only be measured with time.

Progress in Outputs: Since the Programme is at its inception phase, focus has mainly been on establishing its structures and processes in order to commence implementation of activities as well as socializing the programme to create national ownership. At this stage, it is still very much early to measure progress in the outputs of the programme.

UNDP

On human rights and legal awareness raising for the public and community/ religious leaders; human rights education for primary and secondary school students as well as young school leavers and the training of formal justice institutions professionals, an RFP was advertised on 18 May and evaluation of proposals commenced by the end of the reporting period. Contract award to selected NGOs will be done by July.

As for rehabilitation and construction, the Ministry of Justice, Attorney-General’s Office and the Supreme Court were allocated land to construct justice facilities in Sherastan District, Daikundy Province and Dara District, Panjsher Province.  Daikundi and Panjsher are newly Provinces and all districts in both do not have justice facilities at all, save for the provincial capitals. As the Programme Document only provides for rehabilitation of facilities, it was agreed after consultation with all the stakeholders that the two provinces be an exception as long as construction costs are kept within the budget. The facilities to be constructed in both Provinces include joint office buildings for the Ministry of Justice and Attorney-General’s Office and primary courts. In Panjsher a detention centre with separate facilities for women and children will also be constructed.  For the primary court in Sherastan, an ITB to invite bids from companies to construct the court was advertised on 23 June and will close on 12 July. Regarding the joint buildings for the Ministry of Justice and the Attorney-General’s Office in both provinces, architectural designs were completed and await relevant Government authorities to approve in order to advertise the ITBs.

The Programme managed to carry out socialization activities in Daikundi and Pansjer to provincial justice sector institutions, provincial governors and other key stakeholders including civil society organizations, religious and community leaders as well as women organizations in the provinces. This was also a way of assessing justice sector service delivery capacity, the state of the justice sector facilities as well as securing the critical political support and buy-in at the provincial and district levels. On both occasions, representatives from the Supreme Court and the Attorney-General’s Office from Kabul took part in the activities.

Implementation of the programme delayed due to the recruitment of the International Programme Coordinator that took longer. There were also delays in approving the Annual Work-Plan and the entire first quarter of implementation of the programme was lost.

Due to low capacity levels on CPAN in Afghanistan, it has been difficult to find suitable partners to implement CPAN activities in Ghor and Badghis.

The security situation remains the main external challenge to the implementation of the programme. During the Peace Consultation Jirga, a number of planned activities were cancelled (i.e. socialization and infrastructural assessment of justice institutions facilities in some of the provinces and districts. The situation will remain like this as there is still the Kabul Conference coming along in July and elections in September.

There is still very weak coordination between the Programme’s government partners in Kabul and also in the provinces and districts, as well as between Kabul and sub-national justice institutions.

Regarding the security challenges, the Programme partners have agreed to recruit national regional coordinators to be based in targeted provinces and oversee the implementation and monitoring of activities. Local NGOs and private companies will also be hired to monitor rehabilitation and construction work and awareness activities as these can move in districts more freely.

There is greater need to put more hard work towards improving coordination within the Programme’s government partners in Kabul as well as between the national and sub-national partner institutions.

It is also important to involve government partners more at all levels of the implementation of the programme to create the necessary ownership of its objectives.

In terms of the MDGs, the Joint Programme has not yet implemented any activity that contributes to the attainment of the relevant ones as it is still at the inception phase. However, it should be noted that the programme design provides for empowerment of women to enable them to access justice and also claim their rights. Technical designs of the justice facilities so far completed, do very much take into consideration specific needs of women. Women will also participate in the implementation of the activities. Gender is also a specific consideration in the hiring of implementing agencies that will be responsible for conducting legal awareness activities and baseline assessments as well as development of M&E tools.

- National capacities to prevent, reduce, mitigate and cope with the impact of violent conflict strengthened

- National capacities to prevent, reduce, mitigate and cope with the impact of violent conflict strengthened

- Capacity to prevent, reduce, mitigate and cope with the impact of violent conflict strengthened

- Impact of violent conflict reduced and/or  mitigated